SECTION – 3 – SPECIFCATION OF PUMPS

CONTENTS

CLAUSE. NO.	                              DESCRIPTION	  PAGE NO.

A.		GENERAL	  1

A-a		CODES AND STANDARDS	  1

A-b		SYSTEM DESCRIPTION	  1

A-c		SCOPE OF SUPPLY	  3

A-d		SCOPE OF SERVICES	  5

A-e		EXCLUSIONS	  5

A-f		TERMINAL POINT	  5

B.		DESIGN & CONSTRUCTION REQUIREMENT	  5

C.		QUALITY CONTROL & QUALITY ASSURANCE	  6

D.		INSPECTION & TESTING	  7

E.		DRAWINGS / DOCUMENTS TO BE SUBMITTED	  9

ANNEXURES

ANNEXURE-3-2	:	TECHNICAL DATA SHEETS

- General

This specification covers the design, engineering, manufacture, assembly, testing at manufacturer's works, supply and delivery to project site properly packed for transportation, including shop painting, freight, transit insurance, all taxes, duties, octroi, other charges/levies as applicable, supervision of erection, testing and commissioning at site of all materials and equipment inclusive of electrical as specified and as required for various Pumps alongwith AC Drives, Couplings, Baseframes,foundation bolts, Inlet and Outlet counterflanges withnuts, bolts, gaskets and complete with suction and discharge piping, valves, NRVs , instruments etc complete with all materials and accessories for safe and trouble-free operation of the system.

- Codes and Standards : The design, manufacture, inspection and testing of the equipment covered under this specification shall conform, in general, to the standards and codes (latest editions) mentioned below:

- Bureau of Indian Standards (BIS)

1-1) IS-5120- Technical Requirements– Rotodynamic special purpose pumps.

1-2) IS-5639: Pumps for handling chemical and corrosive liquids.

1-3) IS-5659: Pumps for process water.

1-4) IS-6536: Pumps handling volatile liquids.

1-5) IS-9137: Code for acceptance for centrifugal, mixed flow and axial flow pumps - Class "C”.

1-6) IS-1710 - Vertical Turbine Pumps for Clear, Cold, Fresh Water.

- Hydraulic Institute Standards (HIS)

- American National Standards (ANSI).

3-1) ANSI B 73.2 - Vertical inline centrifugal pumps for chemical Process

- Steel Pipe Flanges & Flanged Fittings (ASME B 16.5)

- ASTM. Standards for materials

- API : American Petroleum Institute

6-1) API 610 - Centrifugal pumps for general refinery services

- ASME: American Society of Mechanical Engineers.

- BS-5316, Part-I, (ISO 2548): Acceptance tests for Centrifugal, mixed flow & axial flow pumps - Class C Tests.

- BS-5316, Part-II, (ISO 3555): Acceptance tests for Centrifugal, mixed flow & axial flow pumps - Class B Tests.

- PTC 8.2 : Performance Test Codes - Centrifugal pumps.

- In case of any contradiction between the above standards and data specification sheets, the stipulations in the data sheets shall prevail and shall be binding on the Supplier/ Bidder.

- System Description : The pumps under this specification shall be used for transferring of process liquids from one point to the other as indicated below :

- Acid Transfer Pump - The 2 x100% Acid Transfer pump shall be used for transferring of low concentration acid solution in the Wash recycle tank to the Acid Concentration Plant.

- Recovered Water Return Pump - The 2 x 100% Recovered Water Return Pump shall be used for transferring of recovered water from the Acid Concentration Plant to the Process Water tank.

- Acid Loading Pump - The 2 x100% Acid Loading pump shall be used for transferring of concentrated acid to tanker for dispatching outside plant.

- Scope of supply , and supervision of erection and commissioning :

The scope of supply under this specification for Pumps shall be as follows :

- Two (1w+1s) nos Horizontal, Centrifugal Acid Transfer Pump complete with drive motors and all accessories

- Three (2w+1s) nos Horizontal, Centrifugal Recovered Water Return Pump complete with drive motors and all accessories.

- Two (1w+1s) nos Horizontal, Centrifugal Acid Loading Pump complete with drive motors and all accessories.

- Scope of supply – general :

The scope supply common for all pumps indicated above shall be as follows :

- Sets of Heavy Duty flexible coupling for connecting Pump and Motor shaft, foundation bolts, base frame, support plate, grounding pad, lifting lugs, eye bolts, for each pump and motor set.

- All inlet and outlet counterflanges with nuts, bolts and gaskets.

- Set of special tools and tackles.

- First fill of lubricants and oil.

- Mandatory spares if specified. Price of same shall be evaluated.

- Erection and commissioning spares.

- List of recommended spares with Unit Rate for three (3) years of trouble-free operation. The Price of Recommended spares shall not be evaluated.

- Scope of services :

The following services shall be provided by the bidder for all equipment and accessories listed above:

1) Engineering of equipment & submission of all necessary documentation, drawings, civil assignment detail and operation and maintenance manuals.

2) Inspection and testing of all equipment at manufacturer's shop.

3) Supply and application of painting at shop.

4) Packing for road transportation.

5) Transportation of all equipment including transit insurance up to site.

6) Supervision of Erection and commissioning of items supplied.

7) Witnessing of Performance test of equipment at site and fulfilment

Of Guaranteed Data /Parameters.

- Exclusions :

Following items are out of scope of Bidder:

- Recovered Water Return Pump – Discharge piping to main plant.

- Terminal Point :

- As per Tender Scheme drg.

- Design and construction requirements

1)For selection and sizing of equipment the technical data sheets (Annexure-1) may be referred.

2) Material of construction – The material of construction shall be minimum as indicated in the datasheets. However the bidder may select higher grade based on requirement of the specific function as deemed suitable.

3) Adequate margin shall be considered for selection and sizing of equipment.

4) Pump Casing- Pump casing shall be provided with adequate number of vents unless the pump is made self-venting.  Casing drain, as required, shall be provided complete with drain valves. Pump design must ensure that the nozzles are capable of withstanding external reactions more than those specified in API-610.

5)Impeller - The rotor assembly shall be dynamically balanced and designed with critical speed substantially above the operating speed.

6)Shaft - Shaft size shall be so selected that the critical speed shall be away from the operating speed as recommended in applicable Code/ Standard.  The critical speed shall also be at least 10% away from runaway speed.

7)Bearings - Bearings shall be easily accessible without disturbing the pump assembly.  A drain plug shall be provided at the bottom of each bearing housing. Heavy duty sleeve/ ball/ roller type bearings shall be provided to take care of the radial loads.

8)Mechanical seal - Mechanical seal shall be provided. The seal material shall have low co-efficient of friction and shall be suitable for fluid handled.

9) Performance Guarantee –

9-1) The pump shall be suitable for continuous operation at any point within the "Range of Operation" as stipulated in the data specification sheets.

9-2) Pump shall preferably have a continuously rising head-capacity characteristics from the specified duty point towards shut-off point, the maximum being at shut-off to enable parallel operation. Under all circumstances, the 'range of operation' of the pump shall exclude any unstable operating zone of the head - capacity curve. The power capacity characteristics shall be non-overloading type for the range of operation specified.

9-3) The pump set along with the drive motor shall run smoothly without undue noise and vibration.  Acceptable peak to peak vibration limits shall be generally guided by the Hydraulic Institute Standards of USA.

9-4) The contractor under this specification shall assume full responsibility for the operation of the pump and motor as one unit.

9-4) The following parameters shall be guaranteed - Pump rated capacity, Pump TDH, efficiency at design point and power consumption at the rated point at motor terminal.

- Quality Control Plan (QCP)/ Quality Assurance Plan (QAP)

The Supplier shall be responsible for assuring that his and his sub-suppliers quality control program meets the specified requirements.

The Supplier shall develop a recommended Purchaser inspection point program. This program shall include the design, manufacturing, inspection and testing operations that the Supplier believes may be of interest to Purchaser in demonstrating product quality, whether performed in his own or his sub-suppliers' facilities.  The inspection point program shall be submitted to the Purchaser/Purchaser's Engineer within four weeks of Letter of Intent being issued.

Purchaser and/or his designated representative shall have full access to the Supplier's and sub Supplier's facilities and work area for reviewing conformance to the approved QCP/QAP and records and for witnessing of inspections and tests. Purchaser/Purchaser's Engineer shall be notified ten (10) working days if inspection is in India and twenty one (21) working days if inspection to be carried outside India prior to the start of the tests and inspection points as specified by Purchaser.

Supplier shall have methods in place to assure that items and services including subcontracted items and services, comply with this Specification.  Supplier shall describe these methods in his proposal.

All manufacturing, processing, testing and inspection operations affecting the equipment or material may be subject to surveillance by Purchaser or Purchaser's Engineer.

Prior to production, Supplier shall submit to Purchaser a fabrication sequence describing inspection and/or tests to be performed, for use in determining inspection points that Purchaser may desire to witness.  The Purchaser shall advise the Supplier, prior to production, of those fabrication steps and shop inspection points that the Purchaser desires to witness, and shall identify which of these points require work to be stopped pending written authorization to proceed from Purchaser/Purchaser's Engineer.

For fabrication steps and tests that Purchaser desires to witness, Supplier shall give ten (10) working days if in India and twenty one (21) working days if in abroad for notice of witness points, and fifteen (15) working days if in India and twenty eight (28) working days if in abroad for notice of hold points.  Notification of hold or witness points shall not be considered to have been given until Purchaser has acknowledged receipt of such notification.

In the event of non-conformance of materials or equipment, the Supplier is to prepare a `Non-conformance Report'.  This will be signed jointly by the Supplier and the Purchaser's Engineer.  Each Non-conformance Report shall be dealt with on a `VERY URGENT' basis.  All deviations from this Specification must be documented and referred to Purchaser for written disposition.

The Supplier shall indicate the name of the manufacturer and place of test and inspection for each equipment supplied by him in the offer.

- Inspection and Testing

# Given below a Standard Inspection and Testing requirement (ITR). The relevant test for the specified equipment shall be applicable as per this document

1)	The Supplier shall conduct all tests and inspections required to ensure that the equipment furnished shall conform to the requirements of this specification and in compliance with requirements of applicable Codes and Standards. The particulars of the proposed tests and the procedures for the tests shall be submitted to the Purchaser for approval before conducting the tests. The Purchaser's representative shall be given full access to all tests. The Supplier shall intimate the Purchaser well in advance (at least 15 days notice) so that if desired his representative can witness the test.

2)	Where stage inspection is to be witnessed by Purchaser, in addition to above, the Supplier shall submit to the Purchaser at the initiation of the contract, the detailed PERT-Chart showing the manufacturing programme and indicating the period where Purchaser or his authorised inspecting agency is required at the shop.

3)	Shop Tests

3-1)Material Test

i) 	All materials used for construction shall be of tested quality. Physical and Chemical tests of materials shall be conducted as per the relevant standards and test certificates shall be made available to the Purchaser. If demanded by Purchaser’s inspector, proof of use of only tested quality material shall be furnished.

ii) 	Where stage inspection is to be witnessed by Purchaser, all material test certificates shall be correlated and verified with the actual material used for construction by Purchaser’s inspector who shall stamp the material. In case mill test certificates for the materials are not available, the Supplier shall carry out physical and chemical tests at his own cost from a testing agency, approved by the Purchaser, as per the requirement of specified material standard. The samples for physical and chemical testing shall be drawn up in presence of Purchaser’s inspector who shall also witness the testing.

iii) 	All castings shall be sound, clean and free from porosity, blow holes, hard spots and other harmful defects.

iv) 	The equipment system components shall be subjected to non-destructive testing (NDT) like Radiography, Ultrasonic test, Magnetic particle test, Liquid penetration test etc. as required & QAP must be approved by the Purchaser before  all tests. The accepted limit shall be as stipulated therein. All components subjected to NDT shall be identified and stamped by Purchaser’s inspector on successful completion of testing.

v)	Control panel sequence tests to be done.

- During assembly all clearances and alignments shall also be checked and recorded.

- All major components shall be tested for chemical composition and mechanical strength.

3-2) Hydraulic Test

All pressure parts shall be hydraulically tested at shop as per relevant code and at not less than 150% of design pressure where not specified, prior to painting and lining, if applicable. The pressure parts shall be kept pressurised for at least one (1) hour at this test pressure, unless contradicted by the relevant  test code.

3-3)Dynamic Balancing Test

All rotating components and the assembly of the shall be subjected to dynamic balancing test, as applicable.

3-4)Test for capacity, pressure drop and efficiency of equipment shall be made as per manufacturer’s standard.

3-5)Performance Test at shop

Type test/routine test for the system / equipment shall be done for satisfactory performance in accordance with the relevant IS/BS/ASME or equivalent standard.

Tests shall be conducted with actual driver being furnished.

Reports and test certificates of the above tests shall be submitted to the Purchaser.

3-6) All drive motors shall be tested as per Electrical standards and codes.

4)Performance Test at Site – Given below are the general requirement of site test.

Applicable items shall be considered.

4-1) After the equipment along with all accessories are installed at site, the following tests shall be conducted at site by the supplier with his own calibrated testing equipment:

- To check capability of each equipment to deliver rated performance specified & guaranteed by the supplier.

- To check proper and continuously reliable operation of the control/regulation/sequence of the equipment furnished.

c)	To check proper operation, freedom from excessive temperature rise, unsatisfactory vibration noise.

d)	The tests shall be carried out for a minimum period of eight (8) hours or as directed by the Engineer.

e)	To check the loaded and unloaded shaft horse power (BHP)

f)	To check power (KW) drawn by the equipment

g)	The piping system shall be subjected to a leak test at 1.5 times the design pressure.

If the performance at field is found not to meet the requirement, the liquidated damages shall be applied.