## INDENTIFICATION
| Document Type for Renusagar Project | SERVICE IDENTIFICATION | COMPONENT IDENTIFICATION
| EN01= Engineering Documents and Drawings. | CPP= Complete plant (FGD & SAC)
| QA01= QA Documents. | HSD= FGTR | AN= Booster Fan
| QC01= Quality Control Document. | HTH= MCU(Flue gas cooling system) | AA= Valves
| IP01= Inspection Test Plan. | HNE= Stack/ Chimney system | AY= Expansion joints
| PS01= Work Method Statement/Procedures. | HTA= Flue gas ducting | BB= Tanks
| MA01= Manual. | UVC= Structure for FGD | AT= Filtering unit
| XF01= PFD Diagram. | UXA= Structure for External H2SO4 plant | AD= Spray nozzles for FGTR & MCU
| XG01= P& I Diagram. | PBQ= Process water system | AP= Pump
| TS01= Technical Specification. | RTQ= Waste water system | BQ= Hanger
| MS01= Master Project Schedule. | HSC= Fan System | BY= Slider bearing
| CS01= Cable Schedule. | GNK= Acid water system | BU= Insulation / Sheathing
| VS01= Valve Schedule | SAC= Sulphuric acid plant | YY= Glass flake lining
| PM01= Project management | UCA= Control Room Building FOR FGD | PA= Painting/PRIMER
| IT01= information technology/Software | HSQ= Sprinkler system | AE= Lifting device
| EE01= Engineering Issues | HSY= Control & instrumentation system | BR= Pipes
|  | HSH= Separator or Mist Eliminator | AQ= Damper
|  | UVX=Special structure (plant-specific- MCU) | YA= Air Conditioning/HVAC
| RHS of Service will be marked as 10 |  | KA= Lighting material
| LHS of Service will be marked as 20 |  | KP=Grounding Material
UC= CIVIL Materials
GK= PLC
GC= CONTROL CABLE
GE= POWER CABLES
GX= PMCC, MCC, ACDB and DCDB
MD= MOV
GF= Electrical/Control Cables and Glands
GD= CABLE TRAY
MA= MOTORS
GS= SWITCHGEAR
SAMPLE OF NUMBERING |  |  | GW= Electrical Panels and Junction Boxes
GH= LTMCC/SWITCHBOARD
GU= UPS

## Deliverable Number
DISCIPLINE CODE | 11 |  |  | 22 |  |  | 33 |  |  | 44 |  |  | 55 |  |  | 66 |  |  | 77 |  |  | 88 |  |  | 99
NAME OF DISCIPLINE | General |  |  | MECH |  |  | ELEC |  |  | C&I |  |  | CIVIL |  |  | QA/QC |  |  | HSE |  |  | SOFTWARE |  |  | SULPHURIC ACID PLANT
DOCUMENT TYPE | START NO | ALLOCATED | FINISH NO | START NO | ALLOCATED | FINISH NO | START NO | ALLOCATED | FINISH NO | START NO | ALLOCATED | FINISH NO | START NO | ALLOCATED | FINISH NO | START NO | ALLOCATED | FINISH NO | START NO | ALLOCATED | FINISH NO | START NO | ALLOCATED | FINISH NO | START NO | ALLOCATED | FINISH NO
EN01= Engineering Documents and Drawings. | 111001 | 999 | 112000 | 221001 | 999 | 222000 | 331001 | 999 | 332000 | 441001 | 999 | 442000 | 551001 | 999 | 552000 | 661001 | 999 | 662000 | 771001 | 999 | 772000 | 881001 | 999 | 882000 | 991001 | 999 | 992000
QA01= QA Documents. | 112001 | 999 | 113000 | 222001 | 999 | 223000 | 332001 | 999 | 333000 | 442001 | 999 | 443000 | 552001 | 999 | 553000 | 662001 | 999 | 663000 | 772001 | 999 | 773000 | 882001 | 999 | 883000 | 992001 | 999 | 993000
QC01= Quality Control Document. | 113001 | 999 | 114000 | 223001 | 999 | 224000 | 333001 | 999 | 334000 | 443001 | 999 | 444000 | 553001 | 999 | 554000 | 663001 | 999 | 664000 | 773001 | 999 | 774000 | 883001 | 999 | 884000 | 993001 | 999 | 994000
IP01= Inspection Test Plan. | 114001 | 999 | 115000 | 224001 | 999 | 225000 | 334001 | 999 | 335000 | 444001 | 999 | 445000 | 554001 | 999 | 555000 | 664001 | 999 | 665000 | 774001 | 999 | 775000 | 884001 | 999 | 885000 | 994001 | 999 | 995000
PS01= Work Method Statement/Procedures. | 115001 | 999 | 116000 | 225001 | 999 | 226000 | 335001 | 999 | 336000 | 445001 | 999 | 446000 | 555001 | 999 | 556000 | 665001 | 999 | 666000 | 775001 | 999 | 776000 | 885001 | 999 | 886000 | 995001 | 999 | 996000
MA01= Manual. | 116001 | 999 | 117000 | 226001 | 999 | 227000 | 336001 | 999 | 337000 | 446001 | 999 | 447000 | 556001 | 999 | 557000 | 666001 | 999 | 667000 | 776001 | 999 | 777000 | 886001 | 999 | 887000 | 996001 | 999 | 997000
XF01= PFD Diagram. | 117001 | 99 | 117100 | 227001 | 99 | 227100 | 337001 | 99 | 337100 | 447001 | 99 | 447100 | 557001 | 99 | 557100 | 667001 | 99 | 667100 | 777001 | 99 | 777100 | 887001 | 99 | 887100 | 997001 | 99 | 997100
XG01= P& I Diagram. | 117101 | 99 | 117200 | 227101 | 99 | 227200 | 337101 | 99 | 337200 | 447101 | 99 | 447200 | 557101 | 99 | 557200 | 667101 | 99 | 667200 | 777101 | 99 | 777200 | 887101 | 99 | 887200 | 997101 | 99 | 997200
TS01= Technical Specification. | 117201 | 999 | 118200 | 227201 | 999 | 228200 | 337201 | 999 | 338200 | 447201 | 999 | 448200 | 557201 | 999 | 558200 | 667201 | 999 | 668200 | 777201 | 999 | 778200 | 887201 | 999 | 888200 | 997201 | 999 | 998200
MS01= Master Project Schedule. | 111001
CS01= Cable Schedule. | [6 empty] | 338400 |  |  | 448400
VS01= Valve Schedule |  |  |  | 228300
PM01= Project management | 111002 | 999 | 112001
IT01= information technology/Software | 112002 | 999 | 113001

## Deliverable with Number
BE | DE |  | Drawing or Document No
AA | AA1 | Engineering Issues
|  | FGD & SAC Location of Bore Hole | S21001- EE01-05CPP- 113003
1 |  | FGD & SAC - PROCESS
1.1 | 1.1 | FGD - Process Flow Diagram with Mass Balance | S21001- XF01 - 05HSD- 227001- SHEET X OF XX
1.2 | 1.2 | SAC - Process Flow Diagram with Mass Balance | S21001- XF01 - 05SAC- 997001- SHEET X OF XX
1.3 | 1.3 | FGD & SAC - Media Specification
1.4 | 1.4 | FGD - Process and Instrumentation Diagrams (with KKS or other Hindalco numbering System) | S21001- XG01 - 05HSD- 227101- SHEET X OF XX
1.5 | 1.5 | SAC - Process and Instrumentation Diagrams (with KKS or other Hindalco numbering System) | S21001- XG01 - 05SAC- 997101- SHEET X OF XX
1.6 | 1.6 | FGD-Equipment List | S21001- EN01 - 05HSD- 221001
|  | SAC -Equipment List | S21001- EN01 - 05SAC- 991001
1.7 | 1.7 | FGD - Technical Specification with equipment sizing | S21001- TS01 - 05HSD- 227201
1.8 | 1.8 | SAC - Technical Specification with equipment sizing | S21001- TS01 - 05SAC- 997201
1.9 |  | FGD - Computerized Fluid-dynamic Simulation (CFD) | S21001- EN01 - 05HSD- 221002
1.10 |  | FGD - Performance Curve Inlet SOx vs. Outlet Sox | S21001- EN01 - 05HSD- 221003
1.11 |  | FGD - Specification of Performance Guaranteed Parameters | S21001- EN01 - 05HSD- 221004
1.12 |  | SAC - Specification of Performance Guaranteed Parameters | S21001- EN01 - 05SAC- 991002
2 |  | FGD & SAC - EQUIPMENT TECHNICAL SPECIFICATIONS
| 2.1 | FGD - Booster Fan - Technical Specification | S21001- TS01 - 05HSC- AN- 227202
| 2.2 | FGD - Flue Gas Ducts Expansion Joints - Technical Specification | S21001- TS01 - 05HTA- AY- 227203
| 2.3 | FGD - Flue Gas Ducts Dampers - Technical Specification | S21001- TS01 - 05HTA- AQ- 227204 SHEET X OF XX
| 2.4 | FGD - Hot Air Sealing Package for Dampers - Technical Specification (IF ANY) | S21001- TS01 - 05HTA- AQ- 227204 SHEET X OF XX
| 2.5 | FGD - Process Recycle Pumps - Technical Specification | S21001- TS01 - 05PBQ- AP- 227205
| 2.6 | FGD - Ash Filters - Technical Specification | S21001- TS01 - 05RTQ- AT- 227206
| 2.7 | FGD - Hopper Cleaning Pumps - Technical Specification | S21001- TS01 - 05PBQ- AP- 227207
| 2.8 | FGD - Wash Recycle Pumps - Technical Specification | S21001- TS01 - 05RTQ- AP- 227208
| 2.9 | FGD - Wash Recycle Ash Filters - Technical Specification | S21001- TS01 - 05RTQ- AT- 227209
| 2.10 | FGD - Process Water Pumps - Technical Specification | S21001- TS01 - 05PBQ- AP- 227210
| 2.11 | FGD - Acid Transfer Pumps - Technical Specification | S21001- TS01 - 05GNK- AP- 227211
| 2.12 | FGD - FGTR Washing Grid and Nozzles of SPC Modules - Technical Specification | S21001- TS01 - 05HSD- AD- 227212
| 2.13 | FGD - MCU Flue Gas Cooling Grid and Nozzles - Technical Specification | S21001- TS01 - 05HTH- AD- 227213
| 2.14 | SAC - Vapour-Liquid Separator - Technical Specification | under development
| 2.15 | SAC - Reboiler Heater Exchanger - Technical Specification | under development
| 2.16 | SAC - Acid Condenser - Technical Specification | under development
| 2.17 | SAC - Circulation Pumps - Technical Specification | under development
| 2.18 | SAC - Vacuum System - Technical Specification | under development
3 |  | FGD & SAC - MCU, FGTR, TANKS, VESSELS AND STEEL STRUCTURES DRAWINGS
3.1 | 3.1 | FGD - Structural Steel Materials - Technical Specification | under development
3.2 | 3.2 | SAC - Structural Steel Materials - Technical Specification | under development
| 3.3 | FGD - MCU Mist Cooling Unit - Mechanical Calculation according to Indian Standard (latest edition) | S21001- EN01 - 05HTH - 221005
3.4 | 3.4 | FGD - MCU Mist Cooling Unit - Outline Drawing (including hoppers, ) with design data, nozzles chart and loads on foundation | S21001- EN01 - 05HTH - 221006
|  | FGD - MCU Mist Cooling Unit - Outline Drawing supporting steel structure, , stairs and platforms | S21001- EN01 - 05UVX - 221007
| 3.5 | FGD - MCU Mist Cooling Unit - Construction Drawings (including hoppers ) | S21001- EN01 - 05HTH - 221008
|  | FGD - MCU Mist Cooling Unit - Construction Drawings (supporting steel structure, , stairs and platforms) | S21001- EN01 - 05UVX - 221009
| 3.6 | FGD - FGTR Flue Gas Treatment Reactor - Mechanical Calculation according to Indian Standard (latest edition) | S21001- EN01 - 05HSD - 221010
3.7 | 3.7 | FGD - FGTR Flue Gas Treatment Reactor - Outline Drawing (including hoppers,) with design data, nozzles chart and loads on foundation | S21001- EN01 - 05HSD - 221011
|  | FGD - FGTR Flue Gas Treatment Reactor - Outline Drawing (supporting steel structure, , stairs and platforms) | S21001- EN01 - 05UVC - 221012
3.8 | 3.8 | FGD - FGTR Flue Gas Treatment Reactor - Construction Drawings (including hoppers) | S21001- EN01 - 05HSD - 221013
|  | FGD - FGTR Flue Gas Treatment Reactor - Construction Drawings ( supporting steel structure, stairs and platforms) | S21001- EN01 - 05UVC - 221014
| 3.9 | FGD - FGTR - Slider Bearings Details | S21001- EN01 - 05HSD - 221015
|  | FGD - MCU - Slider Bearings Details | S21001- EN01 - 05HTH - 221016
| 3.10 | FGD - FGTR - Spring Details | S21001- EN01 - 05HSD - 221017
|  | FGD - MCU - Spring Details | S21001- EN01 - 05HTH - 221018
| 3.11 | FGD - Wet Stack - Mechanical Calculation according to Indian Standard (latest edition) | S21001- EN01 - 05HNE - 221019
3.12 | 3.12 | FGD - Wet Stack - Outline Drawing (including hoppers) with design data, nozzles chart and loads | S21001- EN01 - 05HNE - 221020
|  | FGD - Wet Stack - Outline Drawing (supporting steel structure, stairs and platforms) | S21001- EN01 - 05UVX - 221021
| 3.13 | FGD - Wet Stack - Construction Drawings (including hoppers) | S21001- EN01 - 05UVX - 221022
|  | FGD - Wet Stack - Construction Drawings (supporting steel structure, stairs and platforms) | S21001- EN01 - 05UVX - 221023
3.14 | 3.14 | FGD - Process Water Tank - Outline Drawing with design data, nozzles chart and loads | S21001- EN01 - 05PBQ - 221024
| 3.15 | FGD - Process Water Tank - Construction Drawings | S21001- EN01 - 05PBQ - 221025
3.16 | 3.16 | FGD - Waste Recycle Tank - Outline Drawing with design data, nozzles chart and loads | S21001- EN01 - 05RTY - 221026
| 3.17 | FGD - Waste Recycle Tank - Construction Drawings | S21001- EN01 - 05RTY - 221027
3.18 | 3.18 | SAC - Equipment Supporting Steel Structures (including stairs and platforms) - Outline Drawings | under development
| 3.19 | SAC - Equipment Supporting Steel Structures (including stairs and platforms) - Construction Drawings | under development
4 |  | FGD & SAC - GENERAL ARRANGEMENTS
4.1 | 4.1 | FGD - General Arrangement Drawing (Overall Plot Plan) | S21001- EN01 - 05HSD - 221028
4.2 | 4.2 | SAC- General Arrangement Drawing (Overall Plot Plan) | S21001- EN01 - 05SAC -
4.3 | 4.3 | FGD - General Arrangement Drawings (Plans and Sections) | S21001- EN01 - 05HSD - 221029
4.4 | 4.4 | SAC - General Arrangement Drawings (Plans and Sections) | S21001- EN01 - 05SAC -
5 |  | FGD & SAC - BUILDINGS
5.1 | 5.1 | FGD Electrical Buildings - Architectural Outline Drawings (Plans and Sections) | S21001- EN01 - 05UCA - 331001
| 5.2 | FGD Electrical Buildings - HVAC - Technical Specification/AIR CONDITIONER | S21001- TS01 - 05UCA -YA- 337201
| 5.3 | FGD Electrical Buildings - Lighting - Technical Specification | S21001- TS01 - 05UCA -KA- 337202
| 5.4 | FGD Electrical Buildings - Earthing Material and Lightning Arrestor - Technical Specification | S21001- TS01 - 05UCA -KP- 337203
5.5 | 5.5 | SAC Buildings - Architectural Outline Drawings (Plans and Sections) | under development
| 5.6 | SAC Buildings - HVAC - Technical Specification | S21001- TS01 - 05UCA -YA- 997202
| 5.7 | SAC Buildings - Lighting - Technical Specification | S21001- TS01 - 05UCA -KA- 997203
| 5.8 | SAC Buildings - Earthing Material and Lightning Arrestor - Technical Specification | S21001- TS01 - 05UCA -KP- 997204
6 |  | FGD & SAC - LIFTING EQUIPMENT SPECIFICATIONS
| 6.1 | FGD - Lifting device for SPC modules maintenance - Technical Specification | S21001- TS01 - 05HSD- AE- 227214
| 6.1 | SAC - Lifting device for SAC equipment maintenance - Technical Specification | S21001- TS01 - 05SAC- AE- 227215
7 |  | FGD - FLUE GAS DUCTS
7.1 | 7.1 | FGD - Flue Gas Ducts (including supporting structures, stairs and platforms) - Outline Drawings | S21001- EN01 - 05HTA - 221030
7.2 | 7.2 | FGD - Flue Gas Ducts Supporting Steel Structures (including supporting structures, stairs and platforms) - Construction Drawings | S21001- EN01 - 05UVC- 220131
8 |  | FGD & SAC - LININGS, PAINTINGS AND HEAT INSULATIONS
| 8.1 | FGD - Glass Flake Linings - Technical Specification | S21001- TS01 - 05HSD- YY- 227216
| 8.2 | FGD - Paintings - Technical Specification | S21001- TS01 - 05HSD- PA- 227217
| 8.3 | SAC - Paintings - Technical Specification | S21001- TS01 - 05SAC- PA-
| 8.4 | FGD - Heat Insulations - Technical Specification | S21001- TS01 - 05HSD- BU- 227218
| 8.5 | SAC - Heat Insulations - Technical Specification | S21001- TS01 - 05SAC- BU-
9 |  | FGD & SAC - CIVIL
9.1 | 9.1 | FGD - Civil Materials - Technical Specification | S21001- TS01 - 05HSD- UC- 557201
9.2 |  | SAC - Civil Materials - Technical Specification | S21001- TS01 - 05SAC- UC-
9.3 | 9.3 | FGD - Foundation Layout Drawings with equipment loads and embedded parts | S21001- EN01 - 05HSD - 551001
9.4 | 9.4 | SAC - Foundation Layout Drawings with equipment loads and embedded parts | S21001- EN01 - 05SAC -
9.5 |  | FGD - Seismic Calculation Report of the foundations | S21001- EN01 - 05HSD - 551002
9.6 |  | SAC - Seismic Calculation Report of the foundations | S21001- EN01 - 05SAC -
9.7 |  | FGD - Piling Outline Drawing (if piling is required)
9.8 |  | SAC - Piling Outline Drawing (if piling is required)
9.9 |  | FGD - Piling Specification (if piling is required)
9.10 |  | SAC - Piling Specification (if piling is required)
9.11 |  | FGD & SAC - Drainages drawings (funnels, trenches, sumps, etc.)
9.12 |  | FGD & SAC - Cable trenches - Outline Drawings
9.13 | 9.13 | FGD - Excavation and backfillings (with bill of quantitites) | S21001- EN01 - 05HSD - 551003
|  | SAC - Excavation and backfillings (with bill of quantitites) | S21001- EN01 - 05SAC -
9.14 | 9.14 | FGD - Equipment foundations - Formworks drawings (with bill of quantities)
9.15 | 9.15 | SAC - Equipment foundations - Formworks drawings (with bill of quantities)
9.16 | 9.16 | FGD - Equipment foundations - Steel bars and reinforcements drawings (with bill of quantities) | S21001- EN01 - 05HSD - 551004
9.17 |  | SAC - Equipment foundations - Formworks drawings (with bill of quantities) SAC - Equipment foundations - Steel bars and reinforcements drawings (with bill of quantities) | S21001- EN01 - 05SAC -
10 |  | FGD & SAC - PIPING
10.1 | 10.1 | FGD - Piping Materials Specification | S21001- TS01 - 05HSD- BR- 227219
10.2 | 10.2 | SAC - Piping Materials Specification | S21001- TS01 - 05SAC- BR-
| 10.3 | FGD - Piping Line List | S21001- EN01 - 05HSD- 220132
| 10.4 | SAC - Piping Line List | S21001- EN01 - 05SAC-
| 10.5 | FGD - Piping Layout (Plans and Sections) with pipe supports location identification | S21001- EN01 - 05HSD- 220133
| 10.6 | SAC - Piping Layout (Plans and Sections) with pipe supports location identification | under development
| 10.7 | FGD - Pipe Racks and Access Platforms for Maintenance - Drawings with bill of quantities | S21001- EN01 - 05HSD- 220134
| 10.8 | SAC - Pipe Racks and Access Platforms for Maintenance - Drawings with bill of quantitites | under development
| 10.9 | FGD - Pipe Supports - Drawings with bill of quantities | S21001- EN01 - 05HSD- 220135
| 10.10 | SAC - Pipe Supports - Drawings with bill of quantities | under development
| 10.11 | FGD - Piping Isometric Drawings with bill of quantities and support location identification | S21001- EN01 - 05HSD- 220136
| 10.12 | SAC - Piping Isometric Drawings with bill of quantities and support location identification | under development
10.13 | 10.13 | FGD - Piping Painting Specification (primer + final at site) | S21001- TS01 - 05HSD- PA- 227220
10.14 | 10.14 | SAC - Piping Painting Specification (primer + final at site) | under development
10.15 | 10.15 | FGD - Piping Heat Insulation Specification | S21001- TS01 - 05HSD- BU- 227221 SHEET X OF XX
10.16 | 10.16 | SAC - Piping Heat Insulation Specification | under development
10.17 | 10.17 | FGD - Expansion Joints Specification | S21001- TS01 - 05HSD- AY- 227222
10.18 | 10.18 | SAC - Expansion Joints Specification | under development
10.19 |  | SAC - Stress Analysis Calculation of piping steam lines | under development
11 |  | FGD & SAC - VALVES
11.1 |  | FGD - Valve List/ Schedule | S21001- VK01 - 05HSD- 228300
11.2 |  | SAC - Valve List/ Schedule | S21001- VK01 - 05SAC-
| 11.3 | FGD - On/Off Valves - Data Sheets - Technical Spec | S21001- TS01 - 05HSD- AA- 447201
| 11.4 | SAC - On/Off Valves - Data Sheets - Technical Spec | under development
| 11.5 | FGD - Control Valves - Data Sheets - Technical Spec | S21001- TS01 - 05HSD- AA- 447202
| 11.6 | SAC - Control Valves - Data Sheets - Technical Spec | under development
12 |  | FGD & SAC - INSTRUMENTATION AND CONTROL SYSTEM
| 12.1 | FGD - Operations & Controls Description | S21001- EN01 - 05HSD- 441001
| 12.2 | SAC - Operations & Controls Description | under development
12.3 | 12.3 | FGD - Instrument List | S21001- EN01 - 05HSD- 441002
12.4 | 12.4 | SAC - Instrument List | under development
| 12.5 | FGD - Measurement List | S21001- EN01 - 05HSD- 441003
| 12.6 | SAC - Measurement List | under development
12.7 | 12.7 | FGD - Input/Output List | S21001- EN01 - 05HSD- 441004
12.8 | 12.8 | SAC - Input/Output List | under development
| 12.9 | FGD - Instruments Data Sheets | S21001- EN01 - 05HSD- 441005
| 12.10 | SAC - Instruments Data Sheets | under development
12.11 | 12.11 | FGD - Technical Specification for PLC | S21001- TS01 - 05HSD- GK- 447203
12.12 | 12.12 | SAC - Technical Specification for PLC | S21001- TS01 - 05SAC- GK-
| 12.13 | FGD - Loop Diagrams of main process sections | S21001- EN01 - 05HSD- 441006
| 12.14 | SAC - Loop Diagrams of main process sections | under development
| 12.15 | FGD - Logic Diagrams | S21001- EN01 - 05HSD- 441007
| 12.16 | SAC - Logic Diagrams | under development
| 12.17 | FGD - Control Architecture Scheme | S21001- EN01 - 05HSD- 441008
| 12.18 | SAC - Control Architecture Scheme | under development
| 12.19 | FGD - Control Cables Sizing - Technical Specification | S21001- TS01 - 05HSD- GC- 447204
| 12.20 | SAC - Control Cables Sizing - Technical Specification | S21001- TS01 - 05SAC- GC-
| 12.21 | FGD - Hook-Up Diagrams | S21001- EN01 - 05HSD- 441009
| 12.22 | SAC - Hook-Up Diagrams | under development
| 12.23 | FGD - Control Room Layout Drawing | S21001- EN01 - 05UCA- 441010
| 12.24 | SAC - Control Room Layout Drawing | under development
| 12.25 | FGD - Instrument Location Plan Drawing | S21001- EN01 - 05HSD- 441011
| 12.26 | SAC - Instrument Location Plan Drawing | under development
| 12.27 | FGD - Junction Boxes Location Plan Drawing | S21001- EN01 - 05HSD- 441012
| 12.28 | SAC - Junction Boxes Location Plan Drawing | under development
|  | FGD - Control Cables List | S21001- CS01 - 05HSD - 448400
13 |  | FGD & SAC - ELECTRICAL SYSTEM
13.1 | 13.1 | FGD - Electrical Drive List | S21001- EN01 - 05HSD - 331002
13.2 | 13.2 | SAC - Electrical Drive List | under development
| 13.3 | FGD - Electrical Cables List | S21001- CS01 - 05HSD - 338400
| 13.4 | SAC - Electrical Cables List | under development
| 13.5 | FGD - Cable Trays / Conduits Layout with bill of quantities | S21001- EN01 - 05HSD - 331004
| 13.6 | SAC - Cable Trays / Conduits Layout with bill of quantities | under development
| 13.7 | FGD - Junction Boxes - Technical Specification | S21001- TS01 - 05HSD- GW- 337204
| 13.8 | SAC - Junction Boxes - Technical Specification | under development
13.9 | 13.9 | FGD - PMCC, MCC, ACDB and DCDB - Technical Specification | S21001- TS01 - 05HSD- GX- 337205
13.10 | 13.10 | SAC - PMCC, MCC, ACDB and DCDB - Technical Specification | under development
13.11 | 13.11 | FGD - MOV - Technical Specification | S21001- TS01 - 05HSD- MD- 337206
13.12 | 13.12 | SAC - MOV - Technical Specification | under development
13.13 | 13.13 | FGD - LT/HT motors - Technical Specification | S21001- TS01 - 05HSD- MA- 337207
13.14 | 13.14 | SAC- LT/HT cables - Technical Specification | under development
13.15 | 13.15 | FGD - Electrical Single Line Diagram | S21001- EN01 - 05HSD - 331005
13.16 | 13.16 | SAC- Electrical Single Line Diagram | under development
13.17 | 13.17 | FGD - Cable Sizing - Technical Specification | S21001- TS01 - 05HSD- GE- 337208
13.18 | 13.18 | SAC- Cable Sizing - Technical Specification | S21001- TS01 - 05SAC- GE-
| 13.19 | FGD - Individual Distribution Schemes/Control Schemes Drawing | S21001- EN01 - 05HSD - 331006
| 13.20 | SAC - Individual Distribution Schemes/Control Schemes Drawing | under development
| 13.21 | FGD - Illumination Scheme Drawing | S21001- EN01 - 05HSD - 331007
| 13.22 | SAC - Illumination Scheme Drawing | under development
| 13.23 | FGD - Plant lighting Layout Drawing | S21001- EN01 - 05HSD - 331008
| 13.24 | SAC - Plant lighting Layout Drawing | under development
13.25 | 13.25 | FGD - Grounding and Lightening System - Technical Specification
13.26 | 13.26 | SAC - Grounding and Lightening System - Technical Specification
| 13.27 | FGD - Grounding Scheme Drawing | S21001- EN01 - 05HSD - 331009
| 13.28 | SAC - Grounding Scheme Drawing | under development
| 13.29 | FGD - Lightening Protection Drawing | S21001- EN01 - 05HSD - 331010
| 13.30 | SAC - Lightening Protection Drawing | under development
| 13.31 | FGD - Plant Area Grounding and Lightening Protection Layout | S21001- EN01 - 05HSD - 331011
| 13.32 | SAC - Plant Area Grounding and Lightening Protection Layout | under development
| 13.33 | FGD - Electrical Equipment Layout | S21001- EN01 - 05HSD - 331012
| 13.34 | SAC - Electrical Equipment Layout | under development
| 13.35 | FGD - Electrical Room Layout (Plan and Sections) | S21001- EN01 - 05HSD - 331013
| 13.36 | SAC - Electrical Room Layout (Plan and Sections) | under development
| 13.37 | FGD – Electrical/Control Cables and Glands - Technical Specification | S21001- TS01- 05HSD- GF - 337209
| 13.38 | SAC – Electrical/Control Cables and Glands - Technical Specification | S21001- TS01- 05SAC- GF -
| 13.39 | FGD – Cable Trays - Technical Specification | S21001- TS01- 05HSD- GD - 337210
| 13.40 | SAC – Cable Trays - Technical Specification | S21001- TS01- 05SAC- GD -
| 13.41 | FGD – LT Motors - Technical Specification | S21001- TS01- 05HSD- MA - 337211
| 13.42 | SAC – LT Motors - Technical Specification | S21001- TS01- 05SAC- MA -
| 13.43 | FGD – HT Motors - Technical Specification | S21001- TS01- 05HSD- MA - 337212
| 13.44 | SAC – HT Motors - Technical Specification | S21001- TS01- 05SAC- MA -
| 13.45 | FGD – LT & HT Switchgears - Technical Specification | S21001- TS01- 05HSD- GS - 337213
| 13.46 | SAC – LT & HT Switchgears - Technical Specification | S21001- TS01- 05SAC- GS -
| 13.47 | FGD – Electrical Panels and Junction Boxes - Technical Specification | S21001- TS01- 05HSD- GW - 337214
| 13.48 | SAC – Electrical Panels and Junction Boxes - Technical Specification | S21001- TS01- 05SAC- GW -
| 13.49 | FGD – LTMCC / Switchboard - Technical Specification | S21001- TS01- 05HSD- GH - 337215
| 13.50 | SAC – LTMCC / Switchboard - Technical Specification | S21001- TS01- 05SAC- GH -
| 13.51 | FGD – UPS - Technical Specification | S21001- TS01- 05HSD- GU - 337216
| 13.52 | SAC – UPS - Technical Specification | S21001- TS01- 05SAC- GU -
| 13.53 | FGD – UPS - Line Diagram | S21001- EN01 - 05HSD - 331014
| 13.54 | SAC – UPS - Line Diagram | under development
| 13.55 | FGD & SAC - Auxiliary power calculation for continuous running of FGD plant including SAC at full load. | S21001- EN01 - 05HSD - 331015
Note on B13: suman das: Once Sizing in fixed, no updattion permits