## Cover
Owner: HINDALCO INDUSTRIES LIMITED Ahura Centre, 1st Floor, B Wing, Mahakali Caves Road, Andheri (East), Mumbai - 400 093, India
EPCM Contractor: W. L. GORE & ASSOCIATES (Pacific) Pte, Ltd. India Branch 703, A-Wing, 215 Atrium, Andheri Kurla Road, Mumbai 400059, India
Nominated Subcontractor - Engineering, Quality Control, Supervision: SMARTLuth Solution and Service Pvt. Ltd. Unit No: 503, 5th Floor, ECO Centre,. EM-4 Sector-V, Salt Lake City, Kolkata - 700091, India
Hindalco Renusagar U5 1 x 80 MW PF Captive Power Plant
Flue Gas Desulfurization Project (FGD) with GORETM SO2 Control System
FGD & SAC- Engineering Document List (EDL /MDL)
00 | 2022-01-06 | First Issue |  | S.Das | S.Chakraborty |  | M.Deb
Rev. | Date | Description of revision |  | Prepared | Checked |  | Approved
Hindalco Renusagar U5 1 x 80 MW PF Captive Power Plant |  |  |  | Drg. / Doc. No. : S21001-EN01-05CPP-221030
Flue Gas Desulfurization Project (FGD) with GORETM SO2 Control System |  |  |  | Gore Doc. No.: RPDU5.BA.002 |  | page 1 |  | of | 15
FGD & SAC- Engineering Document List (EDL/MDL) |  |  |  | GORE Job : RPDU5 |  | Rev. : | 00
File:
This document is a property of W.L. GORE & ASSOCIATES (Pacific) Pte, Ltd. and it may contain trade secrets or privileged, undisclosed or otherwise confidential information. If you have received this document in error, you are hereby notified that any review, copying or distribution of it is strictly prohibited.

## 6.1.2022
Engineering Document List / Master Document List
Project No: S21001 |  |  |  | APPROVAL CAT | 78
Project Name: FGD Treatment (SPC Technology) U5 - 1 x 80 MWe Renusagar Captive Power Plant, Hindalco –by W.L.Gore & Associates |  |  |  | INFORMATION CAT | 289
DOCUMENT NO: S21001-EN01-05CPP-221030_REV 0 DATED 6.1.2022
Pos | DESCRIPTION | SMARTLUTH DRAWING NO./DOCUMENT NO. | GORE Document Number | HINDALCO Document Number | Document type "FA" for approval or "FI" for information by HINDALCO
1 | FGD & SAC - PROCESS
1.1 | FGD - Process Flow Diagram with Mass Balance | S21001- XF01 - 05HSD- 227001 SHEET X OF XX | RPDU5.MP.001 | S21001- XF01 - 05HSD- 227001 SHEET X OF XX | FA
1.2 | SAC - Process Flow Diagram with Mass Balance | UNDER DEVELOPMENT | RPDU5.MP.301 | UNDER DEVELOPMENT | FA
1.3 | FGD & SAC - Media Specification | S21001-EN01-05CPP-111001 | RPDU5.MP.500 | S21001-EN01-05CPP-111001 | FI
1.4 | FGD - Process and Instrumentation Diagrams (with KKS or other Hindalco numbering System) | S21001- XG01 - 05HSD- 227101 SHEET X OF XX | RPDU5.MP.010 | S21001- XG01 - 05HSD- 227101 SHEET X OF XX | FA
1.5 | SAC - Process and Instrumentation Diagrams (with KKS or other Hindalco numbering System) | UNDER DEVELOPMENT | RPDU5.MP.310 | UNDER DEVELOPMENT | FA
1.6 | FGD & SAC -Equipment List | S21001-EN01-05CPP-111002 INCLUDES S21001- EN01 - 05HSD- 221001 S21001-EN01-05GNE-XXXXXX | RPDU5.MM.000 | S21001-EN01-05CPP-111002 INCLUDES S21001- EN01 - 05HSD- 221001 S21001-EN01-05GNE-XXXXXX | FI
1.7 | FGD - Technical Specification with equipment sizing | S21001- TS01 - 05HSD- 227201 | RPDU5.PG.001 | S21001- TS01 - 05HSD- 227201 | FA
1.8 | SAC - Technical Specification with equipment sizing | S21001-TS01- 05GNE- 997201 | RPDU5.PG.301 | S21001-TS01- 05GNE- 997201 | FA
1.9 | FGD - Computerized Fluid-dynamic Simulation (CFD) | S21001- EN01 - 05HSD- 221002 | RPDU5.MA.001 | S21001- EN01 - 05HSD- 221002 | FA
1.10 | FGD - Performance Curve Inlet SOx vs. Outlet SOx | S21001- EN01 - 05CPP- 221003 | RPDU5.PG.002 | S21001- EN01 - 05CPP- 221003 | FI
1.11 | FGD - Specification of Performance Guaranteed Parameters | S21001- EN01 - 05CPP- 221004 | RPDU5.PG.003 | S21001- EN01 - 05CPP- 221004 | FA
1.12 | SAC - Specification of Performance Guaranteed Parameters | UNDER DEVELOPMENT | RPDU5.PG.303 | UNDER DEVELOPMENT | FA
21.1 | Interface with customer equipment, facilities - Mechanical | S21001-EE01-05CPP-22001 to 221000 |  | S21001-EE01-05CPP-22001 to 221000 | FA
2 | FGD & SAC - EQUIPMENT TECHNICAL SPECIFICATIONS
2.1 | FGD - Booster Fan - Technical Specification | S21001- TS01 - 05HSC- 227202 | RPDU5.PG.030 | S21001- TS01 - 05HSC- 227202 | FI
2.2 | FGD - Flue Gas Duct Expansion Joint - Technical Specification | S21001- TS01 - 05HTA- 227203 | RPDU5.PG.031 | S21001- TS01 - 05HTA- 227203 | FI
2.3 | FGD - Flue Gas Duct Dampers - Technical Specification | S21001- TS01 - 05HTA- 227204 SHEET X OF XX | RPDU5.PG.032 | S21001- TS01 - 05HTA- 227204 SHEET X OF XX | FI
2.4 | FGD - Hot Air Sealing Package for Dampers - Technical Specification | IT IS NOT REQUIRED | RPDU5.PG.033 | IT IS NOT REQUIRED | FI
2.5 | FGD - Process Recycle Pumps - Technical Specification | S21001- TS01 - 05GNK- 227205 | RPDU5.PG.034 | S21001- TS01 - 05GNK- 227205 | FI
2.6 | FGD - Ash Filters - Technical Specification | S21001- TS01 - 05HSM- 227206 | RPDU5.PG.035 | S21001- TS01 - 05HSM- 227206 | FI
2.7 | FGD - Hopper Cleaning Pumps - Technical Specification | S21001- TS01 - 05GNK- 227207 | RPDU5.PG.036 | S21001- TS01 - 05GNK- 227207 | FI
2.8 | FGD - Wash Recycle Pumps - Technical Specification | S21001- TS01 - 05HSM- 227208 | RPDU5.PG.037 | S21001- TS01 - 05HSM- 227208 | FI
2.9 | FGD - Wash Recycle Ash Filters - Technical Specification | S21001- TS01 - 05HSM- 227209 | RPDU5.PG.038 | S21001- TS01 - 05HSM- 227209 | FI
2.10 | FGD - Process Water Pumps - Technical Specification | S21001- TS01 - 05GNK- 227210 | RPDU5.PG.039 | S21001- TS01 - 05GNK- 227210 | FI
2.11 | FGD - Acid Transfer Pumps - Technical Specification | S21001- TS01 - 05HSM- 227211 | RPDU5.PG.040 | S21001- TS01 - 05HSM- 227211 | FI
2.12 | FGD - FGTR Washing Grid and Nozzles of SPC Modules - Technical Specification | S21001- TS01 - 05HTD- 227213 S21001- TS01 - 05HTD- 227214 | RPDU5.PG.041 | S21001- TS01 - 05HTD- 227213 S21001- TS01 - 05HTD- 227214 | FI
2.13 | FGD - MCU Flue Gas Cooling Grid and Nozzles - Technical Specification | S21001-TS01- 05HTH- 227212 | RPDU5.PG.043 | S21001-TS01- 05HTH- 227212 | FI
2.14 | SAC - Vapour-Liquid Separator - Technical Specification | UNDER DEVELOPMENT | RPDU5.PG.330 | UNDER DEVELOPMENT | FI
2.15 | SAC - Reboiler Heater Exchanger - Technical Specification | UNDER DEVELOPMENT | RPDU5.PG.331 | UNDER DEVELOPMENT | FI
2.16 | SAC - Acid Condenser - Technical Specification | UNDER DEVELOPMENT | RPDU5.PG.332 | UNDER DEVELOPMENT | FI
2.17 | SAC - Circulation Pumps - Technical Specification | UNDER DEVELOPMENT | RPDU5.PG.333 | UNDER DEVELOPMENT | FI
2.18 | SAC - Vacuum System - Technical Specification | UNDER DEVELOPMENT | RPDU5.PG.334 | UNDER DEVELOPMENT | FI
3 | FGD & SAC - MCU, FGTR, TANKS, VESSELS AND STEEL STRUCTURES DRAWINGS
3.1 | FGD - Structural Steel Materials - Technical Specification | S21001-TS01-05HSD-227252 | RPDU5.PA.100 | S21001-TS01-05HSD-227252 | FI
3.2 | SAC - Structural Steel Materials - Technical Specification | S21001-TS01-05GNE-XXXXXX | RPDU5.PA.300 | S21001-TS01-05GNE-XXXXXX | FI
3.3 | FGD - MCU Mist Cooling Unit - Mechanical Calculation according to Indian Standard (latest edition) | S21001- EN01 - 05HTH - 221005 | RPDU5.MA.001 | S21001- EN01 - 05HTH - 221005 | FA
3.4 | FGD - MCU Mist Cooling Unit - Outline Drawing (including hoppers, supporting steel structure, stairs and platforms) with design data, nozzles chart and loads on foundation | S21001- EN01 - 05HTH - 221006 & S21001- EN01 - 05UVX - 221007 (For Structural steel, Galleries, Stairs & Platforms) | RPDU5.MV.001 | S21001- EN01 - 05HTH - 221006 & S21001- EN01 - 05UVX - 221007 (For Structural steel, Galleries, Stairs & Platforms) | FA
3.5 | FGD - MCU Mist Cooling Unit - Construction Drawings (including hoppers, supporting steel structure, stairs and platforms) | S21001- EN01 - 05HTH - 221008 & S21001- EN01 - 05UVX - 221009 (For Structural steel, Galleries, Stairs & Platforms) | RPDU5.MV.002 | S21001- EN01 - 05HTH - 221008 & S21001- EN01 - 05UVX - 221009 (For Structural steel, Galleries, Stairs & Platforms) | FI
3.6 | FGD - FGTR Flue Gas Treatment Reactor - Mechanical Calculation according to Indian Standard (latest edition) | S21001- EN01 - 05HSD - 221010 | RPDU5.MA.002 | S21001- EN01 - 05HSD - 221010 | FA
3.7 | FGD - FGTR Flue Gas Treatment Reactor - Outline Drawing (including hoppers, supporting steel structure, , stairs and platforms) with design data, nozzles chart and loads on foundation | S21001- EN01 - 05HSD - 221011 & S21001- EN01 - 05UVC - 221012(For Structural steel, Galleries, Stairs & Platforms) | RPDU5.MV.003 | S21001- EN01 - 05HSD - 221011 & S21001- EN01 - 05UVC - 221012(For Structural steel, Galleries, Stairs & Platforms) | FA
3.8 | FGD - FGTR Flue Gas Treatment Reactor - Construction Drawings (including hoppers, supporting steel structure, stairs and platforms) | S21001- EN01 - 05HSD - 221013 & S21001- EN01 - 05UVC - 221014 (For Structural steel, Galleries, Stairs & Platforms) | RPDU5.MV.004 | S21001- EN01 - 05HSD - 221013 & S21001- EN01 - 05UVC - 221014 (For Structural steel, Galleries, Stairs & Platforms) | FI
3.9 | FGD - MCU & FGTR - Slider Bearings Details | S21001- EN01 - 05HSD - 221015 for FGTR S21001- EN01 - 05HTH - 221016 for MCU | RPDU5.MV.501 | S21001- EN01 - 05HSD - 221015 for FGTR S21001- EN01 - 05HTH - 221016 for MCU | FI
3.10 | FGD - MCU & FGTR - Spring Details | S21001- EN01 - 05HSD - 221017 for FGTR S21001- EN01 - 05HTH - 221018 for MCU | RPDU5.MV.502 | S21001- EN01 - 05HSD - 221017 for FGTR S21001- EN01 - 05HTH - 221018 for MCU | FI
3.11 | FGD - Wet Stack - Mechanical Calculation according to Indian Standard (latest edition) | S21001- EN01 - 05HNE - 221019 | RPDU5.MA.005 | S21001- EN01 - 05HNE - 221019 | FA
3.12 | FGD - Wet Stack - Outline Drawing (including hoppers, supporting steel structure, , stairs and platforms) with design data, nozzles chart and loads | S21001- EN01 - 05HNE - 221020 & S21001- EN01 - 05UHN - 221021 (For Structural steel, Galleries, Stairs & Platforms) | RPDU5.MV.005 | S21001- EN01 - 05HNE - 221020 & S21001- EN01 - 05UHN - 221021 (For Structural steel, Galleries, Stairs & Platforms) | FA
3.13 | FGD - Wet Stack - Construction Drawings (including hoppers, supporting steel structure, , stairs and platforms) | S21001- EN01 - 05HNE - 221022 & S21001- EN01 - 05UHN - 221023 (For Structural steel, Galleries, Stairs & Platforms) | RPDU5.MV.006 | S21001- EN01 - 05HNE - 221022 & S21001- EN01 - 05UHN - 221023 (For Structural steel, Galleries, Stairs & Platforms) | FI
3.14 | FGD - Process Water Tank - Outline Drawing with design data, nozzles chart and loads | S21001- EN01 - 05GNK - 221024 | RPDU5.MV.010 | S21001- EN01 - 05GNK - 221024 | FA
3.15 | FGD - Process Water Tank - Construction Drawings | S21001- EN01 - 05GNK - 221025 | RPDU5.MV.011 | S21001- EN01 - 05GNK - 221025 | FI
3.16 | FGD - Waste Recycle Tank - Outline Drawing with design data, nozzles chart and loads | S21001- EN01 - 05HSM - 221026 | RPDU5.MV.012 | S21001- EN01 - 05HSM - 221026 | FA
3.17 | FGD - Waste Recycle Tank - Construction Drawings | S21001- EN01 - 05HSM - 221029 | RPDU5.MV.013 | S21001- EN01 - 05HSM - 221029 | FI
3.18 | SAC - Equipment Supporting Steel Structures (including stairs and platforms) - Outline Drawings | UNDER DEVELOPMENT | RPDU5.MV.301 | UNDER DEVELOPMENT | FA
3.19 | SAC - Equipment Supporting Steel Structures (including stairs and platforms) - Construction Drawings | UNDER DEVELOPMENT | RPDU5.MV.302 | UNDER DEVELOPMENT | FI
4 | FGD & SAC - GENERAL ARRANGEMENTS
4.1 | FGD - General Arrangement Drawing (Overall Plot Plan) | S21001- EN01 - 05HSD - 221027 | RPDU5.ML.000 | S21001- EN01 - 05HSD - 221027 | FA
4.2 | SAC- General Arrangement Drawing (Overall Plot Plan) | UNDER DEVELOPMENT | RPDU5.ML.300 | UNDER DEVELOPMENT | FA
4.3 | FGD - General Arrangement Drawings (Plans and Sections) | S21001- EN01 - 05HSD - 221028 | RPDU5.ML.001 | S21001- EN01 - 05HSD - 221028 | FA
4.4 | SAC - General Arrangement Drawings (Plans and Sections) | UNDER DEVELOPMENT | RPDU5.ML.301 | UNDER DEVELOPMENT | FA
5 | FGD & SAC - BUILDINGS
5.1 | FGD Electrical Buildings - Architectural Outline Drawings (Plans and Sections) | S21001- EN01 - 05UCA - 551006 | RPDU5.ML.501 | S21001- EN01 - 05UCA - 551006 | FI
5.2 | FGD Electrical Buildings - HVAC - Technical Specification | S21001- TS01 - 05UCA- 337201 | RPDU5.PG.501 | S21001- TS01 - 05UCA- 337201 | FI
5.3 | FGD Electrical Buildings - Lighting - Technical Specification | S21001- TS01 - 05UCA- 337202 | RPDU5.PG.502 | S21001- TS01 - 05UCA- 337202 | FI
5.4 | FGD Electrical Buildings - Earthing Material and Lightning Arrestor - Technical Specification | S21001- TS01 - 05UCA- 337203 | RPDU5.PG.503 | S21001- TS01 - 05UCA- 337203 | FI
5.5 | SAC Buildings - Architectural Outline Drawings (Plans and Sections) | UNDER DEVELOPMENT | RPDU5.ML.551 | UNDER DEVELOPMENT | FI
5.6 | SAC Buildings - HVAC - Technical Specification | UNDER DEVELOPMENT | RPDU5.PG.551 | UNDER DEVELOPMENT | FI
5.7 | SAC Buildings - Lighting - Technical Specification | UNDER DEVELOPMENT | RPDU5.PG.552 | UNDER DEVELOPMENT | FI
5.8 | SAC Buildings - Earthing Material and Lightning Arrestor - Technical Specification | UNDER DEVELOPMENT | RPDU5.PG.553 | UNDER DEVELOPMENT | FI
6 | FGD & SAC - LIFTING EQUIPMENT SPECIFICATIONS
6.1 | FGD - Lifting device for SPC modules maintenance - Technical Specification | S21001- TS01 - 05HSD- 227215 | RPDU5.PG.050 | S21001- TS01 - 05HSD- 227215 | FI
6.2 | SAC - Lifting device for SAC equipment maintenance - Technical Specification | UNDER DEVELOPMENT | RPDU5.PG.350 | UNDER DEVELOPMENT | FI
7 | FGD - FLUE GAS DUCTS
7.1 | FGD - Flue Gas Duct (including supporting structures, stairs and platforms) - Outline Drawings | S21001- EN01 - 05UVZ - 221037 | RPDU5.MU.001 | S21001- EN01 - 05UVZ - 221037 | FA
7.2 | FGD - Flue Gas Duct Supporting Steel Structures (including supporting structures, stairs and platforms) - Construction Drawings | S21001- EN01 - 05UVZ- 221031 | RPDU5.MU.002 | S21001- EN01 - 05UVZ- 221031 | FI
8 | FGD & SAC - LININGS, PAINTINGS AND HEAT INSULATIONS
8.1 | FGD - Glass Flake Linings - Technical Specification | S21001- TS01 - 05HSD- 227216 | RPDU5.PG.020 | S21001- TS01 - 05HSD- 227216 | FI
8.2 | FGD - Paintings - Technical Specification | S21001- TS01 - 05HSD- 227217 | RPDU5.PG.021 | S21001- TS01 - 05HSD- 227217 | FI
8.3 | SAC - Paintings - Technical Specification | UNDER DEVELOPMENT | RPDU5.PG.321 | UNDER DEVELOPMENT | FI
8.4 | FGD - Heat Insulations - Technical Specification | S21001- TS01 - 05HSD- 227218 | RPDU5.PG.022 | S21001- TS01 - 05HSD- 227218 | FI
8.5 | SAC - Heat Insulations - Technical Specification | UNDER DEVELOPMENT | RPDU5.PG.322 | UNDER DEVELOPMENT | FI
9 | FGD & SAC - CIVIL
9.1 | FGD - Civil Materials - Technical Specification | S21001- TS01 - 05HSD- 557201 | RPDU5.PA.550 | S21001- TS01 - 05HSD- 557201 | FI
9.2 | SAC - Civil Materials - Technical Specification | UNDER DEVELOPMENT / CIVIL MATERIAL MAY BE USED AS COMMON FOR FGD AND SAC, HENCE 9.1 SERVES BOTH | RPDU5.PA.551 | UNDER DEVELOPMENT / CIVIL MATERIAL MAY BE USED AS COMMON FOR FGD AND SAC, HENCE 9.1 SERVES BOTH | FI
9.3 | FGD - Foundation Layout Drawings with equipment loads and embedded part | S21001- EN01 - 05HSD - 551001 | RPDU5.MC.001 | S21001- EN01 - 05HSD - 551001 | FA
9.4 | SAC - Foundation Layout Drawings with equipment loads and embedded part | UNDER DEVELOPMENT | RPDU5.MC.301 | UNDER DEVELOPMENT | FA
9.5 | FGD - Seismic Calculation Report of the foundations | S21001- EN01 - 05CPP - 551002 | RPDU5.MA.001 | S21001- EN01 - 05CPP - 551002 | FA
9.6 | SAC - Seismic Calculation Report of the foundations | UNDER DEVELOPMENT | RPDU5.MA.301 | UNDER DEVELOPMENT | FA
9.7 | FGD - Piling Outline Drawing (if piling is required) | WILL DEVELOP IF REQUIRED | RPDU5.MC.002 | WILL DEVELOP IF REQUIRED | FA
9.8 | SAC - Piling Outline Drawing (if piling is required) | WILL DEVELOP IF REQUIRED | RPDU5.MC.302 | WILL DEVELOP IF REQUIRED | FA
9.9 | FGD - Piling Specification (if piling is required) | WILL DEVELOP IF REQUIRED | RPDU5.PG.507 | WILL DEVELOP IF REQUIRED | FA
9.10 | SAC - Piling Specification (if piling is required) | WILL DEVELOP IF REQUIRED | RPDU5.PG.508 | WILL DEVELOP IF REQUIRED | FA
9.11 | FGD & SAC - Drainages drawings (funnels, trenches, sumps, etc.) | S21001- EN01 - 05CPP - 551005 | RPDU5.MC.501 | S21001- EN01 - 05CPP - 551005 | FI
9.12 | FGD & SAC - Cable trenches - Outline Drawings | S21001-EN01-05CPP-XXXXX | RPDU5.MC.502 | S21001-EN01-05CPP-XXXXX | FI
9.13 | FGD & SAC - Excavation and backfillings (with bill of quantitites) | S21001- EN01 - 05HSD - 551003 | RPDU5.MC.503 | S21001- EN01 - 05HSD - 551003 | FI
9.14 | FGD - Equipment foundations - Formworks drawings (with bill of quantities) | WILL DEVELOP IF REQUIRED | RPDU5.MC.310 | WILL DEVELOP IF REQUIRED | FI
9.15 | SAC - Equipment foundations - Formworks drawings (with bill of quantities) | WILL DEVELOP IF REQUIRED | RPDU5.MC.510 | WILL DEVELOP IF REQUIRED | FI
9.16 | FGD - Equipment foundations - Steel bars and reinforcement drawings (with bill of quantities) | S21001- EN01 - 05HSD - 551004 | RPDU5.MC.350 | S21001- EN01 - 05HSD - 551004 | FI
9.17 | SAC - Equipment foundations - Formworks drawings (with bill of quantities) - Steel bars and reinforcement drawings (with bill of quantities) | WILL DEVELOP IF REQUIRED | RPDU5.MC.550 | WILL DEVELOP IF REQUIRED | FI
21.8 | Booster Fan Foundation - Design Drawings and Calculations | S21001-EN01-05HSC-551007 |  | S21001-EN01-05HSC-551007 | FA
21.9 | Geotechnical procedures | RPD-U5-FGD-C-SPC-01 | Hindalco Scope of Work | RPD-U5-FGD-C-SPC-01 | FA
21.10 | Geotechnical layout | RPD-U5-BHM-001 | Hindalco Scope of Work | RPD-U5-BHM-001 | FA
21.11 | Geotechnical report | Hindalco Scope of Work | Hindalco Scope of Work | Hindalco Scope of Work | FA
10 | FGD & SAC - PIPING
10.1 | FGD - Piping Materials Technical Specification | S21001- TS01- 05HSD- 227219 SHEET X OF XX | RPDU5.PG.010 | S21001- TS01- 05HSD- 227219 SHEET X OF XX | FI
10.2 | SAC - Piping Materials Specification | UNDER DEVELOPMENT | RPDU5.PG.310 | UNDER DEVELOPMENT | FI
10.3 | FGD - Piping Line List | S21001- EN01 - 05HSD- 221032 | RPDU5.MM.001 | S21001- EN01 - 05HSD- 221032 | FI
10.4 | SAC - Piping Line List | UNDER DEVELOPMENT | RPDU5.MM.301 | UNDER DEVELOPMENT | FI
10.5 | FGD - Piping Layout (Plans and Sections) with pipe support location identification | S21001- EN01 - 05HSD- 221033 | RPDU5.ML.010 | S21001- EN01 - 05HSD- 221033 | FI
10.6 | SAC - Piping Layout (Plans and Sections) with pipe support location identification | UNDER DEVELOPMENT | RPDU5.ML.310 | UNDER DEVELOPMENT | FI
10.7 | FGD - Pipe Racks and Access Platforms for Maintenance - Drawings with bill of quantities | S21001- EN01 - 05HSD- 221034 | RPDU5.MU.010 | S21001- EN01 - 05HSD- 221034 | FI
10.8 | SAC - Pipe Racks and Access Platforms for Maintenance - Drawings with bill of quantitites | UNDER DEVELOPMENT | RPDU5.MU.310 | UNDER DEVELOPMENT | FI
10.9 | FGD - Pipe Support - Drawings with bill of quantities | S21001- EN01 - 05HSD- 221035 | RPDU5.MU.050 | S21001- EN01 - 05HSD- 221035 | FI
10.10 | SAC - Pipe Support - Drawings with bill of quantities | UNDER DEVELOPMENT | RPDU5.MU.350 | UNDER DEVELOPMENT | FI
10.11 | FGD - Piping Isometric Drawings with bill of quantities and support location identification | S21001- EN01 - 05HSD- 221036 | RPDU5.MS.010 | S21001- EN01 - 05HSD- 221036 | FI
10.12 | SAC - Piping Isometric Drawings with bill of quantities and support location identification | UNDER DEVELOPMENT | RPDU5.MS.310 | UNDER DEVELOPMENT | FI
10.13 | FGD - Piping Painting Technical Specification (primer + final at site) | S21001- TS01 - 05HSD- 227220 | RPDU5.PG.011 | S21001- TS01 - 05HSD- 227220 | FI
10.14 | SAC - Piping Painting Specification (primer + final at site) | UNDER DEVELOPMENT | RPDU5.PG.311 | UNDER DEVELOPMENT | FI
10.15 | FGD - Piping Heat Insulation Technical Specification | S21001- TS01 - 05HSD- 227221 SHEET X OF XX | RPDU5.PG.012 | S21001- TS01 - 05HSD- 227221 SHEET X OF XX | FI
10.16 | SAC - Piping Heat Insulation Specification | UNDER DEVELOPMENT | RPDU5.PG.312 | UNDER DEVELOPMENT | FI
10.17 | FGD - Expansion Joint Technical Specification | S21001- TS01 - 05HSD- 227251 | RPDU5.PG.013 | S21001- TS01 - 05HSD- 227251 | FI
10.18 | SAC - Expansion Joint Technical Specification | UNDER DEVELOPMENT | RPDU5.PG.313 | UNDER DEVELOPMENT | FI
10.19 | SAC - Stress Analysis Calculation of piping steam lines | UNDER DEVELOPMENT | RPDU5.MA.302 | UNDER DEVELOPMENT | FI
11 | FGD & SAC - VALVES
11.1 | FGD - Valve List | S21001- VS01 - 05HSD- 228400 | RPDU5.MM.002 | S21001- VS01 - 05HSD- 228400 | FI
11.2 | SAC - Valve List | UNDER DEVELOPMENT | RPDU5.MM.302 | UNDER DEVELOPMENT | FI
11.3 | FGD - On/Off Valves - Data Sheet | S21001- TS01 - 05HSD- 447201 | RPDU5.PG.060 | S21001- TS01 - 05HSD- 447201 | FI
11.4 | SAC - On/Off Valves - Data Sheet | UNDER DEVELOPMENT | RPDU5.PG.360 | UNDER DEVELOPMENT | FI
11.5 | FGD - Control Valves - Data Sheet | S21001- TS01 - 05HSD- 447202 | RPDU5.PG.061 | S21001- TS01 - 05HSD- 447202 | FI
11.6 | SAC - Control Valves - Data Sheet | UNDER DEVELOPMENT | RPDU5.PG.361 | UNDER DEVELOPMENT | FI
12 | FGD & SAC - INSTRUMENTATION AND CONTROL SYSTEM
12.1 | FGD - Operations & Controls Description | S21001- EN01 - 05HSD- 441001 | RPDU5.PG.070 | S21001- EN01 - 05HSD- 441001 | FA
12.2 | SAC - Operations & Controls Description | UNDER DEVELOPMENT | RPDU5.PG.370 | UNDER DEVELOPMENT | FA
12.3 | FGD - Instrument List | S21001- EN01 - 05HSD- 441002 | RPDU5.EM.001 | S21001- EN01 - 05HSD- 441002 | FI
12.4 | SAC - Instrument List | UNDER DEVELOPMENT | RPDU5.EM.301 | UNDER DEVELOPMENT | FI
12.5 | FGD - Measurement List | S21001- EN01 - 05HSD- 441003 | RPDU5.EM.002 | S21001- EN01 - 05HSD- 441003 | FI
12.6 | SAC - Measurement List | UNDER DEVELOPMENT | RPDU5.EM.302 | UNDER DEVELOPMENT | FI
12.7 | FGD - Input/Output List | S21001- EN01 - 05HSD- 441004 | RPDU5.EM.003 | S21001- EN01 - 05HSD- 441004 | FA
12.8 | SAC - Input/Output List | UNDER DEVELOPMENT | RPDU5.EM.303 | UNDER DEVELOPMENT | FA
12.9 | FGD - Instrument Data Sheet | S21001- EN01 - 05HSD- 441005 | RPDU5.ES.001 | S21001- EN01 - 05HSD- 441005 | FA
12.10 | SAC - Instrument Data Sheet | UNDER DEVELOPMENT | RPDU5.ES.301 | UNDER DEVELOPMENT | FI
12.11 | FGD - Technical Specification for PLC | S21001- TS01 - 05HSD- 447203 | RPDU5.PE.001 | S21001- TS01 - 05HSD- 447203 | FI
12.12 | SAC - Technical Specification for PLC | UNDER DEVELOPMENT | RPDU5.PE.301 | UNDER DEVELOPMENT | FI
12.13 | FGD - Loop Diagrams of main process sections | S21001- EN01 - 05HSD- 441006 | RPDU5.EL.001 | S21001- EN01 - 05HSD- 441006 | FI
12.14 | SAC - Loop Diagrams of main process sections | UNDER DEVELOPMENT | RPDU5.EL.301 | UNDER DEVELOPMENT | FI
12.15 | FGD - Logic Diagrams | S21001- EN01 - 05HSD- 441007 | RPDU5.EL.010 | S21001- EN01 - 05HSD- 441007 | FI
12.16 | SAC - Logic Diagrams | UNDER DEVELOPMENT | RPDU5.EL.310 | UNDER DEVELOPMENT | FI
12.17 | FGD - Control Architecture Scheme | S21001- EN01 - 05HSD- 441008 | RPDU5.EL.050 | S21001- EN01 - 05HSD- 441008 | FA
12.18 | SAC - Control Architecture Scheme | UNDER DEVELOPMENT | RPDU5.EL.350 | UNDER DEVELOPMENT | FA
12.19 | FGD - Control Cables Sizing - Technical Specification | S21001- TS01 - 05HSD- 447204 | RPDU5.PE.050 | S21001- TS01 - 05HSD- 447204 | FI
12.20 | SAC - Control Cables Sizing - Technical Specification | UNDER DEVELOPMENT | RPDU5.PE.350 | UNDER DEVELOPMENT | FI
12.21 | FGD - Hook-Up Diagrams | S21001- EN01 - 05HSD- 441009 | RPDU5.EL.051 | S21001- EN01 - 05HSD- 441009 | FI
12.22 | SAC - Hook-Up Diagrams | UNDER DEVELOPMENT | RPDU5.EL.351 | UNDER DEVELOPMENT | FI
12.23 | FGD - Control Room Layout Drawing | S21001- EN01 - 05UCA- 441010 | RPDU5.EL.052 | S21001- EN01 - 05UCA- 441010 | FA
12.24 | SAC - Control Room Layout Drawing | UNDER DEVELOPMENT | RPDU5.EL.352 | UNDER DEVELOPMENT | FA
12.25 | FGD - Instrument Location Plan Drawing | S21001- EN01 - 05HSD- 441011 | RPDU5.EL.353 | S21001- EN01 - 05HSD- 441011 | FI
12.26 | SAC - Instrument Location Plan Drawing | UNDER DEVELOPMENT | RPDU5.EL.553 | UNDER DEVELOPMENT | FI
12.27 | FGD - Junction Boxes Location Plan Drawing | S21001- EN01 - 05HSD- 441012 | RPDU5.EL.054 | S21001- EN01 - 05HSD- 441012 | FI
12.28 | SAC - Junction Boxes Location Plan Drawing | UNDER DEVELOPMENT | RPDU5.EL.354 | UNDER DEVELOPMENT | FI
21.6 | Interface with customer equipment, facilities - Instrumentation and control | S21001-EE01-05CPP-44001 to 441000 |  | S21001-EE01-05CPP-44001 to 441000 | FA
21.12 | Control System Graphic/Mimic (Design document of GUI Pages) | S21001- EN01-05CPP-441013 |  | S21001- EN01-05CPP-441013 | FA
21.13 | FAT Procedure of Control System | S21001- EN01-05HSD-441014 |  | S21001- EN01-05HSD-441014 | FI
21.14 | PLC FAT Report | S21001- EN01-05HSD-441015 |  | S21001- EN01-05HSD-441015 | FI
21.15 | PLC Power Supply & Grounding Scheme | S21001- EN01-05HSD-441016 |  | S21001- EN01-05HSD-441016 | FI
21.23 | Drive Control and Control Interfacing philosophy | S21001-EN01-05HSD-441017 |  | S21001-EN01-05HSD-441017 | FI
13 | FGD & SAC - ELECTRICAL SYSTEM
13.1 | FGD - Electrical Load List | S21001- EN01 - 05HSD - 331001 | RPDU5.EM.000 | S21001- EN01 - 05HSD - 331001 | FI
13.2 | SAC - Electrical Load List | UNDER DEVELOPMENT | RPDU5.EM.300 | UNDER DEVELOPMENT | FI
13.3 | FGD - Electrical & Control Cables List | S21001- EN01 - 05HSD - 331002 & S21001- EN01 - 05HSD - 331003 FOR CONTROL CABLES | RPDU5.EM.004 | S21001- EN01 - 05HSD - 331002 & S21001- EN01 - 05HSD - 331003 FOR CONTROL CABLES | FI
13.4 | SAC - Electrical & Control Cables List | UNDER DEVELOPMENT | RPDU5.EM.304 | UNDER DEVELOPMENT | FI
13.5 | FGD - Cable Trays / Conduit Layout with bill of quantities | S21001- EN01 - 05HSD - 331004 | RPDU5.EV.001 | S21001- EN01 - 05HSD - 331004 | FI
13.6 | SAC - Cable Trays / Conduit Layout with bill of quantities | UNDER DEVELOPMENT | RPDU5.EV.301 | UNDER DEVELOPMENT | FI
13.7 | FGD - Junction Boxes - Technical Specification | S21001- TS01 - 05HSD- 337204 | RPDU5.ED.001 | S21001- TS01 - 05HSD- 337204 | FI
13.8 | SAC - Junction Boxes - Technical Specification | UNDER DEVELOPMENT | RPDU5.ED.301 | UNDER DEVELOPMENT | FI
13.9 | FGD - PMCC, MCC, ACDB , DCDB and Booster Fan VFD Panel - Technical Specification | S21001- TS01 - 05HSD- 337205 | RPDU5.ED.002 | S21001- TS01 - 05HSD- 337205 | FI
13.10 | SAC - PMCC, MCC, ACDB and DCDB - Technical Specification | UNDER DEVELOPMENT | RPDU5.ED.302 | UNDER DEVELOPMENT | FI
13.11 | FGD - MOV - Technical Specification | S21001- TS01 - 05HSD- 337206 | RPDU5.ED.003 | S21001- TS01 - 05HSD- 337206 | FI
13.12 | SAC - MOV - Technical Specification | UNDER DEVELOPMENT | RPDU5.ED.303 | UNDER DEVELOPMENT | FI
13.13 | FGD - LT/HT motors - Technical Specification | S21001- TS01 - 05HSD- 337207 | RPDU5.ED.004 | S21001- TS01 - 05HSD- 337207 | FI
13.14 | SAC- LT/HT cables - Technical Specification | UNDER DEVELOPMENT | RPDU5.ED.304 | UNDER DEVELOPMENT | FI
13.15 | FGD - Electrical Single Line Diagram including Emergency Power Supply Bus from Existing DG set | S21001- EN01 - 05HSD - 331005 | RPDU5.EG.001 | S21001- EN01 - 05HSD - 331005 | FA
13.16 | SAC- Electrical Single Line Diagram | UNDER DEVELOPMENT | RPDU5.EG.301 | UNDER DEVELOPMENT | FA
13.17 | FGD - Cable Sizing - Technical Specification | S21001- TS01 - 05HSD- 337208 | RPDU5.ED.005 | S21001- TS01 - 05HSD- 337208 | FI
13.18 | SAC- Cable Sizing - Technical Specification | UNDER DEVELOPMENT | RPDU5.ED.305 | UNDER DEVELOPMENT | FI
13.19 | FGD - Individual Distribution Schemes/Control Schemes Drawing | S21001- EN01 - 05HSD - 331006 | RPDU5.EG.002 | S21001- EN01 - 05HSD - 331006 | FI
13.20 | SAC - Individual Distribution Schemes/Control Schemes Drawing | UNDER DEVELOPMENT | RPDU5.EG.302 | UNDER DEVELOPMENT | FI
13.21 | FGD - Illumination Scheme Drawing | S21001- EN01 - 05HSD - 331007 | RPDU5.EG.003 | S21001- EN01 - 05HSD - 331007 | FI
13.22 | SAC - Illumination Scheme Drawing | UNDER DEVELOPMENT | RPDU5.EG.303 | UNDER DEVELOPMENT | FI
13.23 | FGD - Plant lighting Layout Drawing | S21001- EN01 - 05HSD - 331008 | RPDU5.EG.004 | S21001- EN01 - 05HSD - 331008 | FI
13.24 | SAC - Plant lighting Layout Drawing | UNDER DEVELOPMENT | RPDU5.EG.304 | UNDER DEVELOPMENT | FI
13.25 | FGD - Grounding and Lightening System - Technical Specification | S21001-TS01-05HSD-337232 | RPDU5.ED.006 | S21001-TS01-05HSD-337232 | FI
13.26 | SAC - Grounding and Lightening System - Technical Specification | UNDER DEVELOPMENT | RPDU5.ED.306 | UNDER DEVELOPMENT | FI
13.27 | FGD - Grounding Scheme Drawing | S21001- EN01 - 05HSD - 331009 | RPDU5.EG.006 | S21001- EN01 - 05HSD - 331009 | FA
13.28 | SAC - Grounding Scheme Drawing | UNDER DEVELOPMENT | RPDU5.EG.306 | UNDER DEVELOPMENT | FA
13.29 | FGD - Lightening Protection Drawing | S21001- EN01 - 05HSD - 331010 | RPDU5.EG.007 | S21001- EN01 - 05HSD - 331010 | FA
13.30 | SAC - Lightening Protection Drawing | UNDER DEVELOPMENT | RPDU5.EG.307 | UNDER DEVELOPMENT | FA
13.31 | FGD - Plant Area Grounding and Lightening Protection Layout | S21001- EN01 - 05HSD - 331011 | RPDU5.EG.008 | S21001- EN01 - 05HSD - 331011 | FA
13.32 | SAC - Plant Area Grounding and Lightening Protection Layout | UNDER DEVELOPMENT | RPDU5.EG.308 | UNDER DEVELOPMENT | FA
13.33 | FGD - Electrical Equipment Layout including Booster Fan VFD Panel | S21001- EN01 - 05HSD - 331012 | RPDU5.EG.009 | S21001- EN01 - 05HSD - 331012 | FA
13.34 | SAC - Electrical Equipment Layout | UNDER DEVELOPMENT | RPDU5.EG.309 | UNDER DEVELOPMENT | FA
13.35 | FGD - Electrical Room Layout (Plan and Sections) | S21001- EN01 - 05HSD - 331013 | RPDU5.EG.010 | S21001- EN01 - 05HSD - 331013 | FA
13.36 | SAC - Electrical Room Layout (Plan and Sections) | UNDER DEVELOPMENT | RPDU5.EG.310 | UNDER DEVELOPMENT | FA
13.37 | FGD – Electrical/Control Cables and Glands - Technical Specification | S21001- TS01- 05HSD - 337209 | RPDU5.ED.007 | S21001- TS01- 05HSD - 337209 | FI
13.38 | SAC – Electrical/Control Cables and Glands - Technical Specification | UNDER DEVELOPMENT | RPDU5.ED.307 | UNDER DEVELOPMENT | FI
13.39 | FGD – Cable Trays - Technical Specification | S21001- TS01- 05HSD - 337210 | RPDU5.ED.008 | S21001- TS01- 05HSD - 337210 | FI
13.40 | SAC – Cable Trays - Technical Specification | UNDER DEVELOPMENT | RPDU5.ED.308 | UNDER DEVELOPMENT | FI
13.41 | FGD – LT Motors - Technical Specification | S21001- TS01- 05HSD - 337211 | RPDU5.ED.009 | S21001- TS01- 05HSD - 337211 | FI
13.42 | SAC – LT Motors - Technical Specification | UNDER DEVELOPMENT | RPDU5.ED.309 | UNDER DEVELOPMENT | FI
13.43 | FGD – HT Motors - Technical Specification | S21001- TS01- 05HSD - 337212 | RPDU5.ED.010 | S21001- TS01- 05HSD - 337212 | FI
13.44 | SAC – HT Motors - Technical Specification | UNDER DEVELOPMENT | RPDU5.ED.310 | UNDER DEVELOPMENT | FI
13.45 | FGD – LT & HT Switchgears - Technical Specification | S21001- TS01- 05HSD - 337213 | RPDU5.ED.011 | S21001- TS01- 05HSD - 337213 | FI
13.46 | SAC – LT & HT Switchgears - Technical Specification | UNDER DEVELOPMENT | RPDU5.ED.311 | UNDER DEVELOPMENT | FI
13.47 | FGD – Electrical Panels and Junction Boxes - Technical Specification | S21001- TS01- 05HSD - 337214 | RPDU5.ED.012 | S21001- TS01- 05HSD - 337214 | FI
13.48 | SAC – Electrical Panels and Junction Boxes - Technical Specification | UNDER DEVELOPMENT | RPDU5.ED.312 | UNDER DEVELOPMENT | FI
13.49 | FGD – LTMCC / Switchboard - Technical Specification | S21001- TS01- 05HSD - 337215 | RPDU5.ED.013 | S21001- TS01- 05HSD - 337215 | FI
13.50 | SAC – LTMCC / Switchboard - Technical Specification | UNDER DEVELOPMENT | RPDU5.ED.313 | UNDER DEVELOPMENT | FI
13.51 | FGD – UPS - Technical Specification | S21001- TS01- 05HSD - 337216 | RPDU5.ED.014 | S21001- TS01- 05HSD - 337216 | FI
13.52 | SAC – UPS - Technical Specification | UNDER DEVELOPMENT | RPDU5.ED.314 | UNDER DEVELOPMENT | FI
13.53 | FGD – UPS - Line Diagram | S21001- EN01 - 05HSD - 331014 | RPDU5.EG.011 | S21001- EN01 - 05HSD - 331014 | FA
13.54 | SAC – UPS - Line Diagram | UNDER DEVELOPMENT | RPDU5.EG.311 | UNDER DEVELOPMENT | FA
13.55 | FGD & SAC - Auxiliary power calculation for continuous running of FGD plant including SAC at full load. | S21001- EN01 - 05CPP - 331015 | RPDU5.ED.500 | S21001- EN01 - 05CPP - 331015 | FA
21.7 | Interface with customer equipment, facilities - Electrical | S21001-EE01-05CPP-33001 to 331000 |  | S21001-EE01-05CPP-33001 to 331000 | FA
21.16 | Design calculation for power, control, instrument and any special cables | S21001-EN01-05HSD-331016 |  | S21001-EN01-05HSD-331016 | FI
21.17 | Design calculation for LT bus duct | S21001-EN01-05HSD-331017 |  | S21001-EN01-05HSD-331017 | FI
21.18 | Design calculation for lighting system | S21001-EN01-05HSD-331018 |  | S21001-EN01-05HSD-331018 | FI
21.19 | Design calculation for lightening protection system | S21001-EN01-05HSD-331019 |  | S21001-EN01-05HSD-331019 | FI
21.20 | Design calculation for earthing system | S21001-EN01-05HSD-331020 |  | S21001-EN01-05HSD-331020 | FI
21.21 | Schematic and wiring diagrams for medium voltage system | S21001-EN01-05HSD-331021 |  | S21001-EN01-05HSD-331021 | FI
21.22 | Schematic and wiring diagrams for low voltage system | S21001-EN01-05HSD-331022 |  | S21001-EN01-05HSD-331022 | FI
21.24 | List of electrical equipment and materials (Bill of materials) | S21001-EN01-05HSD-331023 |  | S21001-EN01-05HSD-331023 | FI
14 | FGD & SAC - FIRE FIGHTING SYSTEM
14.1 | FGD Fire Fighting - Fire Fighting & Detection System Technical Specification | S21001- TS01- 05SGA - 772001 | RPDU5.ED.800 | S21001- TS01- 05SGA - 772001 | FI
14.2 | SAC Fire Fighting - Fire Fighting & Detection System Technical Specification | UNDER DEVELOPMENT | RPDU5.ED.830 | UNDER DEVELOPMENT | FI
14.2 | FGD Fire Fighting - Hydrant and Water Spray System - Schematic Diagram | S21001- EN01- 05SGA - 771001 | RPDU5.EL.800 | S21001- EN01- 05SGA - 771001 | FA
14.3 | SAC Fire Fighting - Alarm System - Schematic Diagram | UNDER DEVELOPMENT | RPDU5.EL.830 | UNDER DEVELOPMENT | FA
14.4 | FGD Fire Fighting - Hydrant and Water Spray System - Layout Drawing | S21001- EN01- 05SGA - 771002 | RPDU5.ML.800 | S21001- EN01- 05SGA - 771002 | FA
14.4 | SAC Fire Fighting - Hydrant and Water Spray System - Layout Drawing | UNDER DEVELOPMENT | RPDU5.ML.830 | UNDER DEVELOPMENT | FA
14.5 | FGD Fire Fighting - Hydrant System - Hydraulic Calculation | S21001- EN01- 05SGA - 771003 | RPDU5.MA.800 | S21001- EN01- 05SGA - 771003 | FI
14.5 | SAC Fire Fighting - Hydrant System - Hydraulic Calculation | UNDER DEVELOPMENT | RPDU5.MA.830 | UNDER DEVELOPMENT | FI
14.6 | FGD Fire Fighting - Water Spray System - Hydraulic Calculation | S21001- EN01- 05SGA - 771004 | RPDU5.MA.801 | S21001- EN01- 05SGA - 771004 | FI
14.6 | SAC Fire Fighting - Water Spray System - Hydraulic Calculation | UNDER DEVELOPMENT | RPDU5.MA.831 | UNDER DEVELOPMENT | FI
14.7 | FGD Fire Fighting - Component Data Sheet | S21001- EN01- 05SGA - 771005 | RPDU5.PA.800 | S21001- EN01- 05SGA - 771005 | FA
14.7 | SAC Fire Fighting - Component Data Sheet | UNDER DEVELOPMENT | RPDU5.PA.830 | UNDER DEVELOPMENT | FA
14.8 | FGD Fire Fighting - Alarm System at MCC and Control Room - General Arrangement Drawing | S21001- EN01- 05SGA - 771006 | RPDU5.ML.801 | S21001- EN01- 05SGA - 771006 | FA
14.9 | SAC Fire Fighting - Alarm System at MCC and Control Room - General Arrangement Drawing | UNDER DEVELOPMENT | RPDU5.ML.831 | UNDER DEVELOPMENT | FA
14.10 | FGD Fire Fighting - Fire Detection Alarm System - Data Sheet | S21001- EN01- 05SGA - 771007 | RPDU5.PA.801 | S21001- EN01- 05SGA - 771007 | FA
14.11 | SAC Fire Fighting - Fire Detection Alarm System - Data Sheet | UNDER DEVELOPMENT | RPDU5.PA.831 | UNDER DEVELOPMENT | FA
14.12 | FGD Fire Fighting - Fire Detection Alarm System - Layout | S21001- EN01- 05SGA - 771008 | RPDU5.ML.802 | S21001- EN01- 05SGA - 771008 | FA
14.13 | SAC Fire Fighting - Fire Detection Alarm System - Layout | UNDER DEVELOPMENT | RPDU5.ML.832 | UNDER DEVELOPMENT | FA
14.14 | FGD Fire Fighting - Fire Detection Alarm System - Schematic Drawing | S21001- EN01- 05SGA - 771009 | RPDU5.ML.803 | S21001- EN01- 05SGA - 771009 | FI
14.15 | SAC Fire Fighting - Fire Detection Alarm System - Schematic Drawing | UNDER DEVELOPMENT | RPDU5.ML.833 | UNDER DEVELOPMENT | FI
14.16 | FGD Fire Fighting - Fire Detection Alarm Equipment - Technical Specification | S21001-TS01- 05SGA- 772002 SHEET X OF XX | RPDU5.PA.802 | S21001-TS01- 05SGA- 772002 SHEET X OF XX | FI
14.17 | SAC Fire Fighting - Fire Detection Alarm Equipment - Technical Specification | UNDER DEVELOPMENT | RPDU5.PA.832 | UNDER DEVELOPMENT | FI
14.18 | FGD Fire Fighting - Fire Extinguishers - Technical Specification | S21001- TS01- 05SGA- 772003 SHEET X OF XX | RPDU5.PA.803 | S21001- TS01- 05SGA- 772003 SHEET X OF XX | FI
14.19 | SAC Fire Fighting - Fire Extinguishers - Technical Specification | UNDER DEVELOPMENT | RPDU5.PA.833 | UNDER DEVELOPMENT | FI
14.20 | FGD Fire Fighting - ERW steel pipes and fittings - Technical Specification | S21001- TS01- 05SGA- 772004 SHEET X OF XX | RPDU5.PA.804 | S21001- TS01- 05SGA- 772004 SHEET X OF XX | FI
14.21 | SAC Fire Fighting - ERW steel pipes and fittings - Technical Specification | UNDER DEVELOPMENT | RPDU5.PA.834 | UNDER DEVELOPMENT | FI
14.22 | FGD Fire Fighting - Pumps - Technical Specification | S21001- TS01- 05SGA- 772005 SHEET X OF XX | RPDU5.PA.805 | S21001- TS01- 05SGA- 772005 SHEET X OF XX | FI
14.23 | SAC Fire Fighting - Pumps - Technical Specification | UNDER DEVELOPMENT | RPDU5.PA.835 | UNDER DEVELOPMENT | FI
14.24 | FGD Fire Fighting - Sprinklers - Technical Specification | S21001- TS01- 05SGA- 772006 SHEET X OF XX | RPDU5.PA.806 | S21001- TS01- 05SGA- 772006 SHEET X OF XX | FI
14.25 | SAC Fire Fighting - Sprinklers - Technical Specification | UNDER DEVELOPMENT | RPDU5.PA.836 | UNDER DEVELOPMENT | FI
15 | FGD & SAC - PURCHASING TECHNICAL SPECIFICATIONS
15.1 | FGD - Booster Fan along with VFD sysytem - PTS Purchasing Technical Specification | S21001- TS01 - 05HSC- 227222 | RPDU5.PA.001 | S21001- TS01 - 05HSC- 227222 | FI
15.2 | FGD - Flue Gas Duct Expansion Joints - PTS Purchasing Technical Specification (Duplicate) | S21001- TS01 - 05HTA- 227223 | RPDU5.PA.002 | S21001- TS01 - 05HTA- 227223 | FI
15.3 | FGD - Flue Gas Duct Dampers - PTS Purchasing Technical Specification | S21001- TS01 - 05HTA- 227223 | RPDU5.PA.003 | S21001- TS01 - 05HTA- 227223 | FI
15.4 | FGD - Pumps - PTS Purchasing Technical Specification | S21001- TS01 - 05PBL- 227224 (FOR BACKWASH & DEMISTER) S21001- TS01 - 05PBL- 227225 (FOR FRESH WATER & MAKE UP WATER) S21001- TS01 - 05GNK- 227226 (FOR HCP) S21001- TS01 - 05HSM- 227227 (FOR WRP) S21001- TS01 - 05GNK- 227228 (FOR PWP) S21001- TS01 - 05HSM- 227229 (FOR WWTP) S21001- TS01 - 05GNK- 227230 (FOR PRP) S21001- TS01 - 05HSM- 227231 (FOR ATP) S21001- TS01 - 05HSM- 227232 (FOR RWRP) S21001- TS01 - 05XXX- 227233 (FOR ALP) | RPDU5.PA.005 | S21001- TS01 - 05PBL- 227224 (FOR BACKWASH & DEMISTER) S21001- TS01 - 05PBL- 227225 (FOR FRESH WATER & MAKE UP WATER) S21001- TS01 - 05GNK- 227226 (FOR HCP) S21001- TS01 - 05HSM- 227227 (FOR WRP) S21001- TS01 - 05GNK- 227228 (FOR PWP) S21001- TS01 - 05HSM- 227229 (FOR WWTP) S21001- TS01 - 05GNK- 227230 (FOR PRP) S21001- TS01 - 05HSM- 227231 (FOR ATP) S21001- TS01 - 05HSM- 227232 (FOR RWRP) S21001- TS01 - 05XXX- 227233 (FOR ALP) | FI
15.5 | SAC - Pumps - PTS Purchasing Technical Specification | S21001- TS01 - 05GNE- 997201 | RPDU5.PA.305 | S21001- TS01 - 05GNE- 997201 | FI
15.6 | FGD - Ash Filters - PTS Purchasing Technical Specification | S21001- TS01 - 05HSM- 227234 (WRPFS) S21001- TS01 - 05HSM- 227235 (WWTPFS) | RPDU5.PA.006 | S21001- TS01 - 05HSM- 227234 (WRPFS) S21001- TS01 - 05HSM- 227235 (WWTPFS) | FI
15.7 | FGD - MCU Flue Gas Cooling Nozzles and FGTR Washing Nozzles of SPC Modules - PTS Purchasing Technical Specification | FGTR-S21001- TS01 - 05HTD- 227236 MCU-S21001-TS01- 05HTH- 227243 | RPDU5.PA.007 | FGTR-S21001- TS01 - 05HTD- 227236 MCU-S21001-TS01- 05HTH- 227243 | FI
15.8 | SCA - Vapour-Liquid Separator, Reboiler Heater Exchanger, Acid Condenser, Circulation Pumps and Vacuum System - PTS Purchasing Technical Specification | UNDER DEVELOPMENT | RPDU5.PA.301 | UNDER DEVELOPMENT | FI
15.9 | FGD - MCU Mist Cooling Unit, FGTR Flue Gas Treatment Unit and Wet Stack - PTS Purchasing Technical Specification | S21001- TS01 - 05HSF- 227238 | RPDU5.PA.008 | S21001- TS01 - 05HSF- 227238 | FI
15.10 | FGD - Steel Tanks - PTS Purchasing Technical Specification | S21001- TS01 - 05PBL- 227239 (FRESH WATER) S21001- TS01 - 05PBL- 227240 (PROCESS WATER) S21001- TS01 - 05HSM- 227241(WASTE WATER TANK) S21001- TS01 - 05HSM- 227242 (RECOVERED WATER RETURN TANK) S21001- TS01 - 05XXX- 227237 (CONCENTRATED ACID TANK) | RPDU5.PA.010 | S21001- TS01 - 05PBL- 227239 (FRESH WATER) S21001- TS01 - 05PBL- 227240 (PROCESS WATER) S21001- TS01 - 05HSM- 227241(WASTE WATER TANK) S21001- TS01 - 05HSM- 227242 (RECOVERED WATER RETURN TANK) S21001- TS01 - 05XXX- 227237 (CONCENTRATED ACID TANK) | FI
15.11 | SAC - Steel Tanks - PTS Purchasing Technical Specification | UNDER DEVELOPMENT | RPDU5.PA.310 | UNDER DEVELOPMENT | FI
15.12 | FGD - FRP Tanks - PTS Purchasing Technical Specification | S21001- TS01 - 05HSD- 227244 | RPDU5.PA.011 | S21001- TS01 - 05HSD- 227244 | FI
15.13 | SAC - FRP Tanks - PTS Purchasing Technical Specification | UNDER DEVELOPMENT | RPDU5.PA.311 | UNDER DEVELOPMENT | FI
15.14 | FGD Electrical Buildings - HVAC - PTS Purchasing Technical Specification | S21001- TS01 - 05UCA- 337223 | RPDU5.PA.012 | S21001- TS01 - 05UCA- 337223 | FI
15.15 | SAC Buildings - HVAC - PTS Purchasing Technical Specification | UNDER DEVELOPMENT | RPDU5.PA.312 | UNDER DEVELOPMENT | FI
15.16 | FGD Electrical Buildings - Lighting - PTS Purchasing Technical Specification | S21001- TS01 - 05UCA- 337224 | RPDU5.PA.013 | S21001- TS01 - 05UCA- 337224 | FI
15.17 | SAC Buildings - Lighting - PTS Purchasing Technical Specification | UNDER DEVELOPMENT | RPDU5.PA.313 | UNDER DEVELOPMENT | FI
15.18 | FGD Electrical Buildings - Earthing Material and Lightning Arrestor - PTS Purchasing Technical Specification | S21001- TS01 - 05UCA- 337225 | RPDU5.PA.014 | S21001- TS01 - 05UCA- 337225 | FI
15.19 | SAC Buildings - Earthing Material and Lightning Arrestor - PTS Purchasing Technical Specification | UNDER DEVELOPMENT | RPDU5.PA.314 | UNDER DEVELOPMENT | FI
15.20 | FGD - Lifting devices - PTS Purchasing Technical Specification | S21001- TS01 - 05HSD- 227245 | RPDU5.PA.015 | S21001- TS01 - 05HSD- 227245 | FI
15.21 | SAC - Lifting devices - PTS Purchasing Technical Specification | UNDER DEVELOPMENT | RPDU5.PA.315 | UNDER DEVELOPMENT | FI
15.22 | FGD - Flue Gas Duct (including supporting structures, stairs and platforms) - PTS Purchasing Technical Specification | S21001- TS01 - 05UVZ- 227246 | RPDU5.PA.009 | S21001- TS01 - 05UVZ- 227246 | FI
15.23 | FGD - Linings - PTS Purchasing Technical Specification | S21001-TS01-05HSD-22 | RPDU5.PA.015 | S21001-TS01-05HSD-22 | FI
15.24 | SAC - Linings - PTS Purchasing Technical Specification | UNDER DEVELOPMENT | RPDU5.PA.315 | UNDER DEVELOPMENT | FI
15.25 | FGD - Paintings - PTS Purchasing Technical Specification | S21001- TS01 - 05HSD- 227247 | RPDU5.PA.016 | S21001- TS01 - 05HSD- 227247 | FI
15.26 | SAC - Paintings - PTS Purchasing Technical Specification | UNDER DEVELOPMENT | RPDU5.PA.316 | UNDER DEVELOPMENT | FI
15.27 | FGD - Heat Insulations - PTS Purchasing Technical Specification | S21001- TS01- 05HSD- 227248 | RPDU5.PA.017 | S21001- TS01- 05HSD- 227248 | FI
15.28 | SAC - Heat Insulations - PTS Purchasing Technical Specification | UNDER DEVELOPMENT | RPDU5.PA.317 | UNDER DEVELOPMENT | FI
15.29 | FGD - Piping - PTS Purchasing Technical Specification | S21001- TS01- 05HSD- 227249 | RPDU5.PA.018 | S21001- TS01- 05HSD- 227249 | FI
15.30 | SAC - Piping - PTS Purchasing Technical Specification | UNDER DEVELOPMENT | RPDU5.PA.318 | UNDER DEVELOPMENT | FI
15.31 | FGD - Piping Support - PTS Purchasing Technical Specification | S21001- TS01- 05HSD- 227250 | RPDU5.PA.019 | S21001- TS01- 05HSD- 227250 | FI
15.32 | SAC - Piping Support - PTS Purchasing Technical Specification | UNDER DEVELOPMENT | RPDU5.PA.319 | UNDER DEVELOPMENT | FI
15.33 | FGD - Control System - PTS Purchasing Technical Specification | S21001- TS01- 05HSD- 337226 | RPDU5.PA.020 | S21001- TS01- 05HSD- 337226 | FI
15.34 | SAC - Control System - PTS Purchasing Technical Specification | UNDER DEVELOPMENT | RPDU5.PA.320 | UNDER DEVELOPMENT | FI
15.35 | FGD - Instrumentation - PTS Purchasing Technical Specification | S21001- TS01- 05HSD-337227 | RPDU5.PA.021 | S21001- TS01- 05HSD-337227 | FI
15.36 | SAC - Instrumentation - PTS Purchasing Technical Specification | UNDER DEVELOPMENT | RPDU5.PA.321 | UNDER DEVELOPMENT | FI
15.37 | FGD - Electrical & Control Cables - PTS Purchasing Technical Specification | S21001- TS01- 05HSD- 337228 (POWERCABLES) S21001- TS01- 05HSD- 447205 (CONTROL CABLES) | RPDU5.PA.022 | S21001- TS01- 05HSD- 337228 (POWERCABLES) S21001- TS01- 05HSD- 447205 (CONTROL CABLES) | FI
15.38 | SAC - Electrical & Control Cables - PTS Purchasing Technical Specification | UNDER DEVELOPMENT | RPDU5.PA.322 | UNDER DEVELOPMENT | FI
15.39 | FGD - Cable Trays and Conduit - PTS Purchasing Technical Specification | S21001- TS01- 05HSD- 337229 (TRAYS) S21001- TS01- 05HSD- 337230 (CONDUITS) | RPDU5.PA.023 | S21001- TS01- 05HSD- 337229 (TRAYS) S21001- TS01- 05HSD- 337230 (CONDUITS) | FI
15.40 | SAC - Cable Trays and Conduit - PTS Purchasing Technical Specification | UNDER DEVELOPMENT | RPDU5.PA.323 | UNDER DEVELOPMENT | FI
15.41 | FGD - Switchboard, Distribution and Utilities Boards - PTS Purchasing Technical Specification | S21001- TS01- 05HSD- 337231 | RPDU5.PA.024 | S21001- TS01- 05HSD- 337231 | FI
15.42 | SAC - Switchboard, Distribution and Utilities Boards - PTS Purchasing Technical Specification | UNDER DEVELOPMENT | RPDU5.PA.324 | UNDER DEVELOPMENT | FI
15.43 | FGD - Illumination/Lighting (Outside and inside) - PTS Purchasing Technical Specification | WILL DEVELOP IF REQUIRED | RPDU5.PA.025 | WILL DEVELOP IF REQUIRED | FI
15.44 | SAC - Illumination/Lighting (Outide and inside) - PTS Purchasing Technical Specification | WILL DEVELOP IF REQUIRED | RPDU5.PA.325 | WILL DEVELOP IF REQUIRED | FI
15.45 | FGD - Earthing Material and Lightning System - PTS Purchasing Technical Specification | WILL DEVELOP IF REQUIRED | RPDU5.PA.026 | WILL DEVELOP IF REQUIRED | FI
15.46 | SAC - Earthing Material and Lightning System - PTS Purchasing Technical Specification | WILL DEVELOP IF REQUIRED | RPDU5.PA.326 | WILL DEVELOP IF REQUIRED | FI
15.47 | FGD - Fire Fighting System - PTS Purchasing Technical Specification (if any) | S21001- TS01- 05SGA- 772007 | RPDU5.PA.027 | S21001- TS01- 05SGA- 772007 | FI
15.48 | SAC - Fire Fighting System - PTS Purchasing Technical Specification (if any) | WILL DEVELOP IF REQUIRED | RPDU5.PA.327 | WILL DEVELOP IF REQUIRED | FI
15.49 | FGD & SAC - Foundations Piling Works - PTS Purchasing Technical Specification (if piling is required) (No piling work) | WILL DEVELOP IF REQUIRED | RPDU5.PA.500 | WILL DEVELOP IF REQUIRED | FI
15.50 | FGD & SAC - Civil Works Procedure - PTS Purchasing Technical Specification | S21001- TS01- 05CPP- 555001 | RPDU5.PA.501 | S21001- TS01- 05CPP- 555001 | FI
15.51 | FGD & SAC - Mechanical Erection Works Procedure - PTS Purchasing Technical Specification | S21001- PS01- 05CPP- 225001 | RPDU5.PA.502 | S21001- PS01- 05CPP- 225001 | FI
15.52 | FGD & SAC - Electrical, Instrumentation and Control Installation Works Procedure- PTS Purchasing Technical Specification | S21001- PS01- 05CPP- 335001 | RPDU5.PA.503 | S21001- PS01- 05CPP- 335001 | FI
16 | FGD & SAC - QUALITY ASSURANCE
16.1 | FGD & SAC - Project Quality Control Manual (with Job Organization Chart) | S21001- QA01- 05CPP- 662001 | RPDU5.QB.501 | S21001- QA01- 05CPP- 662001 | FI
16.2 | FGD & SAC - Quality Control Plan | S21001- QA01- 05CPP- 662002 | RPDU5.QB.502 | S21001- QA01- 05CPP- 662002 | FI
16.3 | FGD & SAC - Overall Inspection and Test Plan | S21001- QA01- 05CPP- 662003 | RPDU5.QF.500 | S21001- QA01- 05CPP- 662003 | FA
16.4 | FGD & SAC - Final Quality Dossier | S21001- QA01- 05CPP- 662004 | RPDU5.QB.550 | S21001- QA01- 05CPP- 662004 | FI
16.5 | FGD & SAC - HAZOP study and ARM analysis (Availability, Reliability & Maintainability) | S21001- QA01- 05CPP- 662005 | RPDU5.QB.505 | S21001- QA01- 05CPP- 662005 | FI
17 | FGD & SAC - QUALITY CONTROL FOR FABRICATION
17.1 | FGD & SAC - ITP Inspection and Test Plans for Fabrication | S21001- IT01- 05CPP- 664001 | RPDU5.QB.503 | S21001- IT01- 05CPP- 664001 | FI
17.2 | FGD & SAC - Ball Valves - ITP Inspection and Test Plan for Fabrication | S21001- IT01- 05CPP- 664002 | RPDU5.QF.501 | S21001- IT01- 05CPP- 664002 | FI
17.3 | FGD & SAC - Butterfly Valves - ITP Inspection and Test Plan for Fabrication | S21001- IT01- 05CPP- 664003 | RPDU5.QF.502 | S21001- IT01- 05CPP- 664003 | FI
17.4 | FGD & SAC - Check Valves - ITP Inspection and Test Plan for Fabrication | S21001- IT01- 05CPP- 664004 | RPDU5.QF.503 | S21001- IT01- 05CPP- 664004 | FI
17.5 | FGD & SAC - Fiberglass Piping Prefabricated - ITP Inspection and Test Plan for Fabrication | S21001- IT01- 05CPP- 664005 | RPDU5.QF.504 | S21001- IT01- 05CPP- 664005 | FI
17.6 | FGD & SAC - Piping Expansion Joint - ITP Inspection and Test Plan for Fabrication | S21001- IT01- 05CPP- 664006 | RPDU5.QF.505 | S21001- IT01- 05CPP- 664006 | FI
17.7 | FGD & SAC - Carbon Steel Tanks - ITP Inspection and Test Plan for Fabrication | S21001- IT01- 05CPP- 664007 | RPDU5.QF.506 | S21001- IT01- 05CPP- 664007 | FI
17.8 | FGD & SAC - Pressure Vessels - ITP Inspection and Test Plan for Fabrication (No Pressure Vessels) | WILL DEVELOP IF REQUIRED | RPDU5.QF.507 | WILL DEVELOP IF REQUIRED | FI
17.9 | FGD & SAC - Fiberglass Tanks - ITP Inspection and Test Plan for Fabrication | S21001- IT01- 05CPP- 664008 | RPDU5.QF.508 | S21001- IT01- 05CPP- 664008 | FI
17.10 | FGD & SAC - Spray Nozzles - ITP Inspection and Test Plan for Fabrication | S21001- IT01- 05CPP- 664009 | RPDU5.QF.509 | S21001- IT01- 05CPP- 664009 | FI
17.11 | FGD & SAC - Booster Fan - ITP Inspection and Test Plan for Fabrication | S21001- IT01- 05CPP- 664010 | RPDU5.QF.510 | S21001- IT01- 05CPP- 664010 | FI
17.12 | FGD & SAC - Blowers - ITP Inspection and Test Plan for Fabrication | S21001- IT01- 05CPP- 664011 | RPDU5.QF.511 | S21001- IT01- 05CPP- 664011 | FI
17.13 | FGD & SAC - Fans - ITP Inspection and Test Plan for Fabrication | S21001- IT01- 05CPP- 664012 | RPDU5.QF.512 | S21001- IT01- 05CPP- 664012 | FI
17.14 | FGD & SAC - Centrifugal Pumps - ITP Inspection and Test Plan for Fabrication | S21001- IT01- 05CPP- 664013 | RPDU5.QF.513 | S21001- IT01- 05CPP- 664013 | FI
17.15 | SAC - Evaporators - ITP Inspection and Test Plan for Fabrication | S21001- IT01- 05CPP- 664014 | RPDU5.QF.514 | S21001- IT01- 05CPP- 664014 | FI
17.16 | SAC - Heat Exchangers - ITP Inspection and Test Plan for Fabrication | S21001- IT01- 05CPP- 664015 | RPDU5.QF.515 | S21001- IT01- 05CPP- 664015 | FI
17.17 | FGD & SAC - Carbon Steel Plates Painted - ITP Inspection and Test Plan for Fabrication | S21001- IT01- 05CPP- 664016 | RPDU5.QF.516 | S21001- IT01- 05CPP- 664016 | FI
17.18 | FGD & SAC - Alloy Steel Plates - ITP Inspection and Test Plan for Fabrication | S21001- IT01- 05CPP- 664017 | RPDU5.QF.517 | S21001- IT01- 05CPP- 664017 | FI
17.19 | FGD & SAC - Main Steel Structures - ITP Inspection and Test Plan for Fabrication | S21001- IT01- 05CPP- 664018 | RPDU5.QF.518 | S21001- IT01- 05CPP- 664018 | FI
17.20 | FGD & SAC - Flue Gas Duct - ITP Inspection and Test Plan for Fabrication | S21001- IT01- 05CPP- 664019 | RPDU5.QF.519 | S21001- IT01- 05CPP- 664019 | FI
17.21 | FGD & SAC - Flue Gas Dampers - ITP Inspection and Test Plan for Fabrication | S21001- IT01- 05CPP- 664020 | RPDU5.QF.520 | S21001- IT01- 05CPP- 664020 | FI
17.22 | FGD & SAC - Instrumentation - ITP Inspection and Test Plan for Fabrication | S21001- IT01- 05CPP- 664021 | RPDU5.QF.521 | S21001- IT01- 05CPP- 664021 | FI
17.23 | FGD & SAC - Analytical Instrument - ITP Inspection and Test Plan for Fabrication | S21001- IT01- 05CPP- 664022 | RPDU5.QF.522 | S21001- IT01- 05CPP- 664022 | FI
17.24 | FGD & SAC - Instrument Frames - ITP Inspection and Test Plan for Fabrication | S21001- IT01- 05CPP- 664023 | RPDU5.QF.523 | S21001- IT01- 05CPP- 664023 | FI
17.25 | FGD & SAC - Cables - ITP Inspection and Test Plan for Fabrication | S21001- IT01- 05CPP- 664024 | RPDU5.QF.524 | S21001- IT01- 05CPP- 664024 | FI
17.26 | FGD & SAC - PLC Local Control Panels - ITP Inspection and Test Plan for Fabrication | S21001- IT01- 05CPP- 664025 | RPDU5.QF.525 | S21001- IT01- 05CPP- 664025 | FI
17.27 | FGD -Ash Filters-ITP Inspection and Test Plan for Fabrication | S21001- IT01- 05CPP- 664045 |  | S21001- IT01- 05CPP- 664045 | FI
18 | FGD & SAC - QUALITY CONTROL FOR ERECTION AND CIVIL WORKS
18.1 | FGD & SAC - ITP Inspection and Test Plans for Civil & Erection Works | S21001- IT01- 05CPP- 664026 | RPDU5.QB.504 | S21001- IT01- 05CPP- 664026 | FI
18.2 | FGD & SAC - Booster Fan - ITP Inspection and Test Plan for Erection Works | S21001- IT01- 05CPP- 664027 | RPDU5.QM.501 | S21001- IT01- 05CPP- 664027 | FI
18.3 | FGD & SAC - Flue Gas Duct - ITP Inspection and Test Plan for Erection Works | S21001- IT01- 05CPP- 664028 | RPDU5.QM.502 | S21001- IT01- 05CPP- 664028 | FI
18.4 | FGD & SAC - Equipment Mechanical - ITP Inspection and Test Plan for Erection Works | S21001- IT01- 05CPP- 664029 | RPDU5.QM.503 | S21001- IT01- 05CPP- 664029 | FI
18.6 | FGD & SAC - Electrical Equipment - ITP Inspection and Test Plan for Erection Works | S21001- IT01- 05CPP- 664030 | RPDU5.QM.504 | S21001- IT01- 05CPP- 664030 | FI
18.7 | FGD & SAC - Instrumentation - ITP Inspection and Test Plan for Erection Works | S21001- IT01- 05CPP- 664031 | RPDU5.QM.505 | S21001- IT01- 05CPP- 664031 | FI
18.8 | FGD & SAC - Piping - ITP Inspection and Test Plan for Erection Works | S21001- IT01- 05CPP- 664032 | RPDU5.QM.506 | S21001- IT01- 05CPP- 664032 | FI
18.9 | FGD & SAC - Cables - ITP Inspection and Test Plan for Erection Works | S21001- IT01- 05CPP- 664033 | RPDU5.QM.507 | S21001- IT01- 05CPP- 664033 | FI
18.10 | FGD & SAC - Insulation - ITP Inspection and Test Plan for Erection Works | S21001- IT01- 05CPP- 664034 | RPDU5.QM.508 | S21001- IT01- 05CPP- 664034 | FI
18.11 | FGD & SAC - Mist Cooling Unit (MCU) - ITP Inspection and Test Plan for Erection Works | S21001- IT01- 05CPP- 664035 | RPDU5.QM.509 | S21001- IT01- 05CPP- 664035 | FI
18.11 | FGD & SAC - Flue Gas Treatment Reactor (FGTR) - ITP Inspection and Test Plan for Erection Works | S21001- IT01- 05CPP- 664036 | RPDU5.QM.510 | S21001- IT01- 05CPP- 664036 | FI
18.12 | FGD & SAC - Tanks - ITP Inspection and Test Plan for Erection Works | S21001- IT01- 05CPP- 664037 | RPDU5.QM.511 | S21001- IT01- 05CPP- 664037 | FI
18.13 | FGD & SAC - Site Painting - ITP Inspection and Test Plan for Erection Works | S21001- IT01- 05CPP- 664038 | RPDU5.QM.512 | S21001- IT01- 05CPP- 664038 | FI
18.14 | FGD & SAC - Glass Flake Lining - ITP Inspection and Test Plan for Erection Works | S21001- IT01- 05CPP- 664039 | RPDU5.QM.513 | S21001- IT01- 05CPP- 664039 | FI
18.15 | FGD & SAC - Concrete Works - ITP Inspection and Test Plan for Civil Works | S21001- IT01- 05CPP- 664040 | RPDU5.QM.514 | S21001- IT01- 05CPP- 664040 | FI
18.26 | FGD & SAC - System Deluge-Sprinkler - ITP Inspection and Test Plan for Civil Works | S21001- IT01- 05CPP- 664041 | RPDU5.QM.515 | S21001- IT01- 05CPP- 664041 | FI
18.28 | SAC - Earthing Lighting Protection System Installation - ITP Inspection and Test Plan for Civil Works | S21001- IT01- 05CPP- 664042 | RPDU5.QM.516 | S21001- IT01- 05CPP- 664042 | FI
18.28 | SAC - Roof and Cladding - ITP Inspection and Test Plan for Civil Works | S21001- IT01- 05CPP- 664043 | RPDU5.QM.517 | S21001- IT01- 05CPP- 664043 | FI
18.29 | FGD -Ash Filters-ITP Inspection and Test Plan for Erection | S21001- IT01- 05CPP- 664044 |  | S21001- IT01- 05CPP- 664044 | FI
19 | FGD & SAC - PROCEDURES AND MANUALS
19.1 | FGD - Flue Gas Duct - Erection Procedure | S21001-PS01- 05HTA- 225002 | RPDU5.PM.001 | S21001-PS01- 05HTA- 225002 | FI
19.2 | FGD - MCU Mist Cooling Unit - Erection Procedure | S21001-PS01- 05HTH- 225003 | RPDU5.PM.002 | S21001-PS01- 05HTH- 225003 | FI
19.3 | FGD - FGTR Flue Gas Treatment Reactor - Erection Procedure | S21001-PS01- 05HSD- 225004 | RPDU5.PM.003 | S21001-PS01- 05HSD- 225004 | FI
19.4 | FGD - Booster Fan including VFD system/panel - Erection Procedure | S21001-PS01- 05HSC- 225005 | RPDU5.PM.004 | S21001-PS01- 05HSC- 225005 | FI
19.5 | FGD & SAC - Tanks & Vessels - Erection Procedure | S21001-PS01-05CPP- 225001 | RPDU5.PM.005 | S21001-PS01-05CPP- 225001 | FI
19.6 | FGD & SAC - Piping - Erection Procedure | S21001-PS01- 05CPP- 225002 | RPDU5.PM.006 | S21001-PS01- 05CPP- 225002 | FI
19.7 | SAC - Erection Procedure | UNDER DEVELOPMENT | RPDU5.PM.007 | UNDER DEVELOPMENT | FI
19.8 | FGD - MCU Mist Cooling Unit - Commissioning Procedure | S21001-CC01-05HTH-228500 | RPDU5.PM.010 | S21001-CC01-05HTH-228500 | FI
19.9 | FGD - FGTR Flue Gas Treatment Reactor - Commissioning Procedure | S21001-CC01-05HSD-228501 | RPDU5.PM.011 | S21001-CC01-05HSD-228501 | FI
19.10 | FGD - Booster Fan - Commissioning Procedure | S21001-CC01-05HSC-228502 | RPDU5.PM.012 | S21001-CC01-05HSC-228502 | FI
19.11 | FGD & SAC - Pumps - Commissioning Procedure | S21001-CC01-05HSD-228503 S21001-CC01-05GNE-998503 | RPDU5.PM.013 | S21001-CC01-05HSD-228503 S21001-CC01-05GNE-998503 | FI
19.12 | SAC - Comissioning Procedure | UNDER DEVELOPMENT | RPDU5.PM.014 | UNDER DEVELOPMENT | FI
19.13 | FGD & SAC - Fire Fighting System - Commissioning Procedure | S21001- CC01- 05SGA- 778500 | RPDU5.PM.015 | S21001- CC01- 05SGA- 778500 | FI
19.14 | FGD - Performance Test Procedure | S21001-CC01-05HSD-228510 | RPDU5.PM.100 | S21001-CC01-05HSD-228510 | FA
19.15 | SAC - Performance Test Procedure | UNDER DEVELOPMENT | RPDU5.PM.300 | UNDER DEVELOPMENT | FA
19.16 | FGD - Operation & Maintenance Manual | S21001-MA01-05HSD-228511 | RPDU5.PM.110 | S21001-MA01-05HSD-228511 | FI
19.17 | SAC - Operation & Manintenance Manual | UNDER DEVELOPMENT | RPDU5.PM.310 | UNDER DEVELOPMENT | FI
20 | FGD & SAC - PROCEDURES AND MANUALS
20.1 | FGD & SAC- Master Project Schedule | S21001-MS01-05CPP-118400 | RPDU5.BA.001 | S21001-MS01-05CPP-118400 | FI
20.2 | FGD & SAC- Engineering Document List(EDL/MDL) | S21001-EN01-05CPP-221030 | RPDU5.BA.002 | S21001-EN01-05CPP-221030 | FI
| FGD & SAC KKS identification system | S21001- PM01-05CPP-121004
| FGD & SAC Drawing Standard Sheet and Document Cover Sheet | S21001- PM01-05CPP-121005
| SMARTLuth Organization Chart | S21001-PM01-05CPP- 121003
Note on C22: suman das: BOOSTER FAN RELATED WILL BE MARKED AS "HSC" "HNC" TO BE UPDATED AS "HSC"