## 6.1.2022
Engineering Document List / Master Document List
Project No: S21001 |  |  |  | APPROVAL CAT | 78
Project Name: FGD Treatment (SPC Technology) U5 - 1 x 80 MWe Renusagar Captive Power Plant, Hindalco –by W.L.Gore & Associates |  |  |  | INFORMATION CAT | 289
DOCUMENT NO: S21001-EN01-05CPP-221030_REV 0 DATED 6.1.2022
Pos | DESCRIPTION | SMARTLUTH DRAWING NO./DOCUMENT NO. | GORE Document Number | HINDALCO Document Number | Document type "FA" for approval or "FI" for information by HINDALCO
1 | FGD & SAC - PROCESS
1.1 | FGD - Process Flow Diagram with Mass Balance | S21001- XF01 - 05HSD- 227001 SHEET X OF XX | RPDU5.MP.001 | S21001- XF01 - 05HSD- 227001 SHEET X OF XX | FA
1.2 | SAC - Process Flow Diagram with Mass Balance | UNDER DEVELOPMENT | RPDU5.MP.301 | UNDER DEVELOPMENT | FA
1.3 | FGD & SAC - Media Specification | S21001-EN01-05CPP-111001 | RPDU5.MP.500 | S21001-EN01-05CPP-111001 | FI
1.4 | FGD - Process and Instrumentation Diagrams (with KKS or other Hindalco numbering System) | S21001- XG01 - 05HSD- 227101 SHEET X OF XX | RPDU5.MP.010 | S21001- XG01 - 05HSD- 227101 SHEET X OF XX | FA
1.5 | SAC - Process and Instrumentation Diagrams (with KKS or other Hindalco numbering System) | UNDER DEVELOPMENT | RPDU5.MP.310 | UNDER DEVELOPMENT | FA
1.6 | FGD & SAC -Equipment List | S21001-EN01-05CPP-111002 INCLUDES S21001- EN01 - 05HSD- 221001 S21001-EN01-05GNE-XXXXXX | RPDU5.MM.000 | S21001-EN01-05CPP-111002 INCLUDES S21001- EN01 - 05HSD- 221001 S21001-EN01-05GNE-XXXXXX | FI
1.7 | FGD - Technical Specification with equipment sizing | S21001- TS01 - 05HSD- 227201 | RPDU5.PG.001 | S21001- TS01 - 05HSD- 227201 | FA
1.8 | SAC - Technical Specification with equipment sizing | S21001-TS01- 05GNE- 997201 | RPDU5.PG.301 | S21001-TS01- 05GNE- 997201 | FA
1.9 | FGD - Computerized Fluid-dynamic Simulation (CFD) | S21001- EN01 - 05HSD- 221002 | RPDU5.MA.001 | S21001- EN01 - 05HSD- 221002 | FA
1.10 | FGD - Performance Curve Inlet SOx vs. Outlet SOx | S21001- EN01 - 05CPP- 221003 | RPDU5.PG.002 | S21001- EN01 - 05CPP- 221003 | FI
1.11 | FGD - Specification of Performance Guaranteed Parameters | S21001- EN01 - 05CPP- 221004 | RPDU5.PG.003 | S21001- EN01 - 05CPP- 221004 | FA
1.12 | SAC - Specification of Performance Guaranteed Parameters | UNDER DEVELOPMENT | RPDU5.PG.303 | UNDER DEVELOPMENT | FA
21.1 | Interface with customer equipment, facilities - Mechanical | S21001-EE01-05CPP-22001 to 221000 |  | S21001-EE01-05CPP-22001 to 221000 | FA
2 | FGD & SAC - EQUIPMENT TECHNICAL SPECIFICATIONS
2.1 | FGD - Booster Fan - Technical Specification | S21001- TS01 - 05HSC- 227202 | RPDU5.PG.030 | S21001- TS01 - 05HSC- 227202 | FI
2.2 | FGD - Flue Gas Duct Expansion Joint - Technical Specification | S21001- TS01 - 05HTA- 227203 | RPDU5.PG.031 | S21001- TS01 - 05HTA- 227203 | FI
2.3 | FGD - Flue Gas Duct Dampers - Technical Specification | S21001- TS01 - 05HTA- 227204 SHEET X OF XX | RPDU5.PG.032 | S21001- TS01 - 05HTA- 227204 SHEET X OF XX | FI
2.4 | FGD - Hot Air Sealing Package for Dampers - Technical Specification | IT IS NOT REQUIRED | RPDU5.PG.033 | IT IS NOT REQUIRED | FI
2.5 | FGD - Process Recycle Pumps - Technical Specification | S21001- TS01 - 05GNK- 227205 | RPDU5.PG.034 | S21001- TS01 - 05GNK- 227205 | FI
2.6 | FGD - Ash Filters - Technical Specification | S21001- TS01 - 05HSM- 227206 | RPDU5.PG.035 | S21001- TS01 - 05HSM- 227206 | FI
2.7 | FGD - Hopper Cleaning Pumps - Technical Specification | S21001- TS01 - 05GNK- 227207 | RPDU5.PG.036 | S21001- TS01 - 05GNK- 227207 | FI
2.8 | FGD - Wash Recycle Pumps - Technical Specification | S21001- TS01 - 05HSM- 227208 | RPDU5.PG.037 | S21001- TS01 - 05HSM- 227208 | FI
2.9 | FGD - Wash Recycle Ash Filters - Technical Specification | S21001- TS01 - 05HSM- 227209 | RPDU5.PG.038 | S21001- TS01 - 05HSM- 227209 | FI
2.10 | FGD - Process Water Pumps - Technical Specification | S21001- TS01 - 05GNK- 227210 | RPDU5.PG.039 | S21001- TS01 - 05GNK- 227210 | FI
2.11 | FGD - Acid Transfer Pumps - Technical Specification | S21001- TS01 - 05HSM- 227211 | RPDU5.PG.040 | S21001- TS01 - 05HSM- 227211 | FI
2.12 | FGD - FGTR Washing Grid and Nozzles of SPC Modules - Technical Specification | S21001- TS01 - 05HTD- 227213 S21001- TS01 - 05HTD- 227214 | RPDU5.PG.041 | S21001- TS01 - 05HTD- 227213 S21001- TS01 - 05HTD- 227214 | FI
2.13 | FGD - MCU Flue Gas Cooling Grid and Nozzles - Technical Specification | S21001-TS01- 05HTH- 227212 | RPDU5.PG.043 | S21001-TS01- 05HTH- 227212 | FI
2.14 | SAC - Vapour-Liquid Separator - Technical Specification | UNDER DEVELOPMENT | RPDU5.PG.330 | UNDER DEVELOPMENT | FI
2.15 | SAC - Reboiler Heater Exchanger - Technical Specification | UNDER DEVELOPMENT | RPDU5.PG.331 | UNDER DEVELOPMENT | FI
2.16 | SAC - Acid Condenser - Technical Specification | UNDER DEVELOPMENT | RPDU5.PG.332 | UNDER DEVELOPMENT | FI
2.17 | SAC - Circulation Pumps - Technical Specification | UNDER DEVELOPMENT | RPDU5.PG.333 | UNDER DEVELOPMENT | FI
2.18 | SAC - Vacuum System - Technical Specification | UNDER DEVELOPMENT | RPDU5.PG.334 | UNDER DEVELOPMENT | FI
3 | FGD & SAC - MCU, FGTR, TANKS, VESSELS AND STEEL STRUCTURES DRAWINGS
3.1 | FGD - Structural Steel Materials - Technical Specification | S21001-TS01-05HSD-227252 | RPDU5.PA.100 | S21001-TS01-05HSD-227252 | FI
3.2 | SAC - Structural Steel Materials - Technical Specification | S21001-TS01-05GNE-XXXXXX | RPDU5.PA.300 | S21001-TS01-05GNE-XXXXXX | FI
3.3 | FGD - MCU Mist Cooling Unit - Mechanical Calculation according to Indian Standard (latest edition) | S21001- EN01 - 05HTH - 221005 | RPDU5.MA.001 | S21001- EN01 - 05HTH - 221005 | FA
3.4 | FGD - MCU Mist Cooling Unit - Outline Drawing (including hoppers, supporting steel structure, stairs and platforms) with design data, nozzles chart and loads on foundation | S21001- EN01 - 05HTH - 221006 & S21001- EN01 - 05UVX - 221007 (For Structural steel, Galleries, Stairs & Platforms) | RPDU5.MV.001 | S21001- EN01 - 05HTH - 221006 & S21001- EN01 - 05UVX - 221007 (For Structural steel, Galleries, Stairs & Platforms) | FA
3.5 | FGD - MCU Mist Cooling Unit - Construction Drawings (including hoppers, supporting steel structure, stairs and platforms) | S21001- EN01 - 05HTH - 221008 & S21001- EN01 - 05UVX - 221009 (For Structural steel, Galleries, Stairs & Platforms) | RPDU5.MV.002 | S21001- EN01 - 05HTH - 221008 & S21001- EN01 - 05UVX - 221009 (For Structural steel, Galleries, Stairs & Platforms) | FI
3.6 | FGD - FGTR Flue Gas Treatment Reactor - Mechanical Calculation according to Indian Standard (latest edition) | S21001- EN01 - 05HSD - 221010 | RPDU5.MA.002 | S21001- EN01 - 05HSD - 221010 | FA
3.7 | FGD - FGTR Flue Gas Treatment Reactor - Outline Drawing (including hoppers, supporting steel structure, , stairs and platforms) with design data, nozzles chart and loads on foundation | S21001- EN01 - 05HSD - 221011 & S21001- EN01 - 05UVC - 221012(For Structural steel, Galleries, Stairs & Platforms) | RPDU5.MV.003 | S21001- EN01 - 05HSD - 221011 & S21001- EN01 - 05UVC - 221012(For Structural steel, Galleries, Stairs & Platforms) | FA
3.8 | FGD - FGTR Flue Gas Treatment Reactor - Construction Drawings (including hoppers, supporting steel structure, stairs and platforms) | S21001- EN01 - 05HSD - 221013 & S21001- EN01 - 05UVC - 221014 (For Structural steel, Galleries, Stairs & Platforms) | RPDU5.MV.004 | S21001- EN01 - 05HSD - 221013 & S21001- EN01 - 05UVC - 221014 (For Structural steel, Galleries, Stairs & Platforms) | FI
3.9 | FGD - MCU & FGTR - Slider Bearings Details | S21001- EN01 - 05HSD - 221015 for FGTR S21001- EN01 - 05HTH - 221016 for MCU | RPDU5.MV.501 | S21001- EN01 - 05HSD - 221015 for FGTR S21001- EN01 - 05HTH - 221016 for MCU | FI
3.10 | FGD - MCU & FGTR - Spring Details | S21001- EN01 - 05HSD - 221017 for FGTR S21001- EN01 - 05HTH - 221018 for MCU | RPDU5.MV.502 | S21001- EN01 - 05HSD - 221017 for FGTR S21001- EN01 - 05HTH - 221018 for MCU | FI
3.11 | FGD - Wet Stack - Mechanical Calculation according to Indian Standard (latest edition) | S21001- EN01 - 05HNE - 221019 | RPDU5.MA.005 | S21001- EN01 - 05HNE - 221019 | FA
3.12 | FGD - Wet Stack - Outline Drawing (including hoppers, supporting steel structure, , stairs and platforms) with design data, nozzles chart and loads | S21001- EN01 - 05HNE - 221020 & S21001- EN01 - 05UHN - 221021 (For Structural steel, Galleries, Stairs & Platforms) | RPDU5.MV.005 | S21001- EN01 - 05HNE - 221020 & S21001- EN01 - 05UHN - 221021 (For Structural steel, Galleries, Stairs & Platforms) | FA
3.13 | FGD - Wet Stack - Construction Drawings (including hoppers, supporting steel structure, , stairs and platforms) | S21001- EN01 - 05HNE - 221022 & S21001- EN01 - 05UHN - 221023 (For Structural steel, Galleries, Stairs & Platforms) | RPDU5.MV.006 | S21001- EN01 - 05HNE - 221022 & S21001- EN01 - 05UHN - 221023 (For Structural steel, Galleries, Stairs & Platforms) | FI
3.14 | FGD - Process Water Tank - Outline Drawing with design data, nozzles chart and loads | S21001- EN01 - 05GNK - 221024 | RPDU5.MV.010 | S21001- EN01 - 05GNK - 221024 | FA
3.15 | FGD - Process Water Tank - Construction Drawings | S21001- EN01 - 05GNK - 221025 | RPDU5.MV.011 | S21001- EN01 - 05GNK - 221025 | FI
3.16 | FGD - Waste Recycle Tank - Outline Drawing with design data, nozzles chart and loads | S21001- EN01 - 05HSM - 221026 | RPDU5.MV.012 | S21001- EN01 - 05HSM - 221026 | FA
3.17 | FGD - Waste Recycle Tank - Construction Drawings | S21001- EN01 - 05HSM - 221029 | RPDU5.MV.013 | S21001- EN01 - 05HSM - 221029 | FI
3.18 | SAC - Equipment Supporting Steel Structures (including stairs and platforms) - Outline Drawings | UNDER DEVELOPMENT | RPDU5.MV.301 | UNDER DEVELOPMENT | FA
3.19 | SAC - Equipment Supporting Steel Structures (including stairs and platforms) - Construction Drawings | UNDER DEVELOPMENT | RPDU5.MV.302 | UNDER DEVELOPMENT | FI
4 | FGD & SAC - GENERAL ARRANGEMENTS
4.1 | FGD - General Arrangement Drawing (Overall Plot Plan) | S21001- EN01 - 05HSD - 221027 | RPDU5.ML.000 | S21001- EN01 - 05HSD - 221027 | FA
4.2 | SAC- General Arrangement Drawing (Overall Plot Plan) | UNDER DEVELOPMENT | RPDU5.ML.300 | UNDER DEVELOPMENT | FA
4.3 | FGD - General Arrangement Drawings (Plans and Sections) | S21001- EN01 - 05HSD - 221028 | RPDU5.ML.001 | S21001- EN01 - 05HSD - 221028 | FA
4.4 | SAC - General Arrangement Drawings (Plans and Sections) | UNDER DEVELOPMENT | RPDU5.ML.301 | UNDER DEVELOPMENT | FA
5 | FGD & SAC - BUILDINGS
5.1 | FGD Electrical Buildings - Architectural Outline Drawings (Plans and Sections) | S21001- EN01 - 05UCA - 551006 | RPDU5.ML.501 | S21001- EN01 - 05UCA - 551006 | FI
5.2 | FGD Electrical Buildings - HVAC - Technical Specification | S21001- TS01 - 05UCA- 337201 | RPDU5.PG.501 | S21001- TS01 - 05UCA- 337201 | FI
5.3 | FGD Electrical Buildings - Lighting - Technical Specification | S21001- TS01 - 05UCA- 337202 | RPDU5.PG.502 | S21001- TS01 - 05UCA- 337202 | FI
5.4 | FGD Electrical Buildings - Earthing Material and Lightning Arrestor - Technical Specification | S21001- TS01 - 05UCA- 337203 | RPDU5.PG.503 | S21001- TS01 - 05UCA- 337203 | FI
5.5 | SAC Buildings - Architectural Outline Drawings (Plans and Sections) | UNDER DEVELOPMENT | RPDU5.ML.551 | UNDER DEVELOPMENT | FI
5.6 | SAC Buildings - HVAC - Technical Specification | UNDER DEVELOPMENT | RPDU5.PG.551 | UNDER DEVELOPMENT | FI
5.7 | SAC Buildings - Lighting - Technical Specification | UNDER DEVELOPMENT | RPDU5.PG.552 | UNDER DEVELOPMENT | FI
5.8 | SAC Buildings - Earthing Material and Lightning Arrestor - Technical Specification | UNDER DEVELOPMENT | RPDU5.PG.553 | UNDER DEVELOPMENT | FI
6 | FGD & SAC - LIFTING EQUIPMENT SPECIFICATIONS
6.1 | FGD - Lifting device for SPC modules maintenance - Technical Specification | S21001- TS01 - 05HSD- 227215 | RPDU5.PG.050 | S21001- TS01 - 05HSD- 227215 | FI
6.2 | SAC - Lifting device for SAC equipment maintenance - Technical Specification | UNDER DEVELOPMENT | RPDU5.PG.350 | UNDER DEVELOPMENT | FI
7 | FGD - FLUE GAS DUCTS
7.1 | FGD - Flue Gas Duct (including supporting structures, stairs and platforms) - Outline Drawings | S21001- EN01 - 05UVZ - 221037 | RPDU5.MU.001 | S21001- EN01 - 05UVZ - 221037 | FA
7.2 | FGD - Flue Gas Duct Supporting Steel Structures (including supporting structures, stairs and platforms) - Construction Drawings | S21001- EN01 - 05UVZ- 221031 | RPDU5.MU.002 | S21001- EN01 - 05UVZ- 221031 | FI
8 | FGD & SAC - LININGS, PAINTINGS AND HEAT INSULATIONS
8.1 | FGD - Glass Flake Linings - Technical Specification | S21001- TS01 - 05HSD- 227216 | RPDU5.PG.020 | S21001- TS01 - 05HSD- 227216 | FI
8.2 | FGD - Paintings - Technical Specification | S21001- TS01 - 05HSD- 227217 | RPDU5.PG.021 | S21001- TS01 - 05HSD- 227217 | FI
8.3 | SAC - Paintings - Technical Specification | UNDER DEVELOPMENT | RPDU5.PG.321 | UNDER DEVELOPMENT | FI
8.4 | FGD - Heat Insulations - Technical Specification | S21001- TS01 - 05HSD- 227218 | RPDU5.PG.022 | S21001- TS01 - 05HSD- 227218 | FI
8.5 | SAC - Heat Insulations - Technical Specification | UNDER DEVELOPMENT | RPDU5.PG.322 | UNDER DEVELOPMENT | FI
9 | FGD & SAC - CIVIL
9.1 | FGD - Civil Materials - Technical Specification | S21001- TS01 - 05HSD- 557201 | RPDU5.PA.550 | S21001- TS01 - 05HSD- 557201 | FI
9.2 | SAC - Civil Materials - Technical Specification | UNDER DEVELOPMENT / CIVIL MATERIAL MAY BE USED AS COMMON FOR FGD AND SAC, HENCE 9.1 SERVES BOTH | RPDU5.PA.551 | UNDER DEVELOPMENT / CIVIL MATERIAL MAY BE USED AS COMMON FOR FGD AND SAC, HENCE 9.1 SERVES BOTH | FI
9.3 | FGD - Foundation Layout Drawings with equipment loads and embedded part | S21001- EN01 - 05HSD - 551001 | RPDU5.MC.001 | S21001- EN01 - 05HSD - 551001 | FA
9.4 | SAC - Foundation Layout Drawings with equipment loads and embedded part | UNDER DEVELOPMENT | RPDU5.MC.301 | UNDER DEVELOPMENT | FA
9.5 | FGD - Seismic Calculation Report of the foundations | S21001- EN01 - 05CPP - 551002 | RPDU5.MA.001 | S21001- EN01 - 05CPP - 551002 | FA
9.6 | SAC - Seismic Calculation Report of the foundations | UNDER DEVELOPMENT | RPDU5.MA.301 | UNDER DEVELOPMENT | FA
9.7 | FGD - Piling Outline Drawing (if piling is required) | WILL DEVELOP IF REQUIRED | RPDU5.MC.002 | WILL DEVELOP IF REQUIRED | FA
9.8 | SAC - Piling Outline Drawing (if piling is required) | WILL DEVELOP IF REQUIRED | RPDU5.MC.302 | WILL DEVELOP IF REQUIRED | FA
9.9 | FGD - Piling Specification (if piling is required) | WILL DEVELOP IF REQUIRED | RPDU5.PG.507 | WILL DEVELOP IF REQUIRED | FA
9.10 | SAC - Piling Specification (if piling is required) | WILL DEVELOP IF REQUIRED | RPDU5.PG.508 | WILL DEVELOP IF REQUIRED | FA
9.11 | FGD & SAC - Drainages drawings (funnels, trenches, sumps, etc.) | S21001- EN01 - 05CPP - 551005 | RPDU5.MC.501 | S21001- EN01 - 05CPP - 551005 | FI
9.12 | FGD & SAC - Cable trenches - Outline Drawings | S21001-EN01-05CPP-XXXXX | RPDU5.MC.502 | S21001-EN01-05CPP-XXXXX | FI
9.13 | FGD & SAC - Excavation and backfillings (with bill of quantitites) | S21001- EN01 - 05HSD - 551003 | RPDU5.MC.503 | S21001- EN01 - 05HSD - 551003 | FI
9.14 | FGD - Equipment foundations - Formworks drawings (with bill of quantities) | WILL DEVELOP IF REQUIRED | RPDU5.MC.310 | WILL DEVELOP IF REQUIRED | FI
9.15 | SAC - Equipment foundations - Formworks drawings (with bill of quantities) | WILL DEVELOP IF REQUIRED | RPDU5.MC.510 | WILL DEVELOP IF REQUIRED | FI
9.16 | FGD - Equipment foundations - Steel bars and reinforcement drawings (with bill of quantities) | S21001- EN01 - 05HSD - 551004 | RPDU5.MC.350 | S21001- EN01 - 05HSD - 551004 | FI
9.17 | SAC - Equipment foundations - Formworks drawings (with bill of quantities) - Steel bars and reinforcement drawings (with bill of quantities) | WILL DEVELOP IF REQUIRED | RPDU5.MC.550 | WILL DEVELOP IF REQUIRED | FI
21.8 | Booster Fan Foundation - Design Drawings and Calculations | S21001-EN01-05HSC-551007 |  | S21001-EN01-05HSC-551007 | FA
21.9 | Geotechnical procedures | RPD-U5-FGD-C-SPC-01 | Hindalco Scope of Work | RPD-U5-FGD-C-SPC-01 | FA
21.10 | Geotechnical layout | RPD-U5-BHM-001 | Hindalco Scope of Work | RPD-U5-BHM-001 | FA
21.11 | Geotechnical report | Hindalco Scope of Work | Hindalco Scope of Work | Hindalco Scope of Work | FA
10 | FGD & SAC - PIPING
10.1 | FGD - Piping Materials Technical Specification | S21001- TS01- 05HSD- 227219 SHEET X OF XX | RPDU5.PG.010 | S21001- TS01- 05HSD- 227219 SHEET X OF XX | FI
10.2 | SAC - Piping Materials Specification | UNDER DEVELOPMENT | RPDU5.PG.310 | UNDER DEVELOPMENT | FI
10.3 | FGD - Piping Line List | S21001- EN01 - 05HSD- 221032 | RPDU5.MM.001 | S21001- EN01 - 05HSD- 221032 | FI
10.4 | SAC - Piping Line List | UNDER DEVELOPMENT | RPDU5.MM.301 | UNDER DEVELOPMENT | FI
10.5 | FGD - Piping Layout (Plans and Sections) with pipe support location identification | S21001- EN01 - 05HSD- 221033 | RPDU5.ML.010 | S21001- EN01 - 05HSD- 221033 | FI
10.6 | SAC - Piping Layout (Plans and Sections) with pipe support location identification | UNDER DEVELOPMENT | RPDU5.ML.310 | UNDER DEVELOPMENT | FI
10.7 | FGD - Pipe Racks and Access Platforms for Maintenance - Drawings with bill of quantities | S21001- EN01 - 05HSD- 221034 | RPDU5.MU.010 | S21001- EN01 - 05HSD- 221034 | FI
10.8 | SAC - Pipe Racks and Access Platforms for Maintenance - Drawings with bill of quantitites | UNDER DEVELOPMENT | RPDU5.MU.310 | UNDER DEVELOPMENT | FI
10.9 | FGD - Pipe Support - Drawings with bill of quantities | S21001- EN01 - 05HSD- 221035 | RPDU5.MU.050 | S21001- EN01 - 05HSD- 221035 | FI
10.10 | SAC - Pipe Support - Drawings with bill of quantities | UNDER DEVELOPMENT | RPDU5.MU.350 | UNDER DEVELOPMENT | FI
10.11 | FGD - Piping Isometric Drawings with bill of quantities and support location identification | S21001- EN01 - 05HSD- 221036 | RPDU5.MS.010 | S21001- EN01 - 05HSD- 221036 | FI
10.12 | SAC - Piping Isometric Drawings with bill of quantities and support location identification | UNDER DEVELOPMENT | RPDU5.MS.310 | UNDER DEVELOPMENT | FI
10.13 | FGD - Piping Painting Technical Specification (primer + final at site) | S21001- TS01 - 05HSD- 227220 | RPDU5.PG.011 | S21001- TS01 - 05HSD- 227220 | FI
10.14 | SAC - Piping Painting Specification (primer + final at site) | UNDER DEVELOPMENT | RPDU5.PG.311 | UNDER DEVELOPMENT | FI
10.15 | FGD - Piping Heat Insulation Technical Specification | S21001- TS01 - 05HSD- 227221 SHEET X OF XX | RPDU5.PG.012 | S21001- TS01 - 05HSD- 227221 SHEET X OF XX | FI
10.16 | SAC - Piping Heat Insulation Specification | UNDER DEVELOPMENT | RPDU5.PG.312 | UNDER DEVELOPMENT | FI
10.17 | FGD - Expansion Joint Technical Specification | S21001- TS01 - 05HSD- 227251 | RPDU5.PG.013 | S21001- TS01 - 05HSD- 227251 | FI
10.18 | SAC - Expansion Joint Technical Specification | UNDER DEVELOPMENT | RPDU5.PG.313 | UNDER DEVELOPMENT | FI
10.19 | SAC - Stress Analysis Calculation of piping steam lines | UNDER DEVELOPMENT | RPDU5.MA.302 | UNDER DEVELOPMENT | FI
11 | FGD & SAC - VALVES
11.1 | FGD - Valve List | S21001- VS01 - 05HSD- 228400 | RPDU5.MM.002 | S21001- VS01 - 05HSD- 228400 | FI
11.2 | SAC - Valve List | UNDER DEVELOPMENT | RPDU5.MM.302 | UNDER DEVELOPMENT | FI
11.3 | FGD - On/Off Valves - Data Sheet | S21001- TS01 - 05HSD- 447201 | RPDU5.PG.060 | S21001- TS01 - 05HSD- 447201 | FI
11.4 | SAC - On/Off Valves - Data Sheet | UNDER DEVELOPMENT | RPDU5.PG.360 | UNDER DEVELOPMENT | FI
11.5 | FGD - Control Valves - Data Sheet | S21001- TS01 - 05HSD- 447202 | RPDU5.PG.061 | S21001- TS01 - 05HSD- 447202 | FI
11.6 | SAC - Control Valves - Data Sheet | UNDER DEVELOPMENT | RPDU5.PG.361 | UNDER DEVELOPMENT | FI
12 | FGD & SAC - INSTRUMENTATION AND CONTROL SYSTEM
12.1 | FGD - Operations & Controls Description | S21001- EN01 - 05HSD- 441001 | RPDU5.PG.070 | S21001- EN01 - 05HSD- 441001 | FA
12.2 | SAC - Operations & Controls Description | UNDER DEVELOPMENT | RPDU5.PG.370 | UNDER DEVELOPMENT | FA
12.3 | FGD - Instrument List | S21001- EN01 - 05HSD- 441002 | RPDU5.EM.001 | S21001- EN01 - 05HSD- 441002 | FI
12.4 | SAC - Instrument List | UNDER DEVELOPMENT | RPDU5.EM.301 | UNDER DEVELOPMENT | FI
12.5 | FGD - Measurement List | S21001- EN01 - 05HSD- 441003 | RPDU5.EM.002 | S21001- EN01 - 05HSD- 441003 | FI
12.6 | SAC - Measurement List | UNDER DEVELOPMENT | RPDU5.EM.302 | UNDER DEVELOPMENT | FI
12.7 | FGD - Input/Output List | S21001- EN01 - 05HSD- 441004 | RPDU5.EM.003 | S21001- EN01 - 05HSD- 441004 | FA
12.8 | SAC - Input/Output List | UNDER DEVELOPMENT | RPDU5.EM.303 | UNDER DEVELOPMENT | FA
12.9 | FGD - Instrument Data Sheet | S21001- EN01 - 05HSD- 441005 | RPDU5.ES.001 | S21001- EN01 - 05HSD- 441005 | FA
12.10 | SAC - Instrument Data Sheet | UNDER DEVELOPMENT | RPDU5.ES.301 | UNDER DEVELOPMENT | FI
12.11 | FGD - Technical Specification for PLC | S21001- TS01 - 05HSD- 447203 | RPDU5.PE.001 | S21001- TS01 - 05HSD- 447203 | FI
12.12 | SAC - Technical Specification for PLC | UNDER DEVELOPMENT | RPDU5.PE.301 | UNDER DEVELOPMENT | FI
12.13 | FGD - Loop Diagrams of main process sections | S21001- EN01 - 05HSD- 441006 | RPDU5.EL.001 | S21001- EN01 - 05HSD- 441006 | FI
12.14 | SAC - Loop Diagrams of main process sections | UNDER DEVELOPMENT | RPDU5.EL.301 | UNDER DEVELOPMENT | FI
12.15 | FGD - Logic Diagrams | S21001- EN01 - 05HSD- 441007 | RPDU5.EL.010 | S21001- EN01 - 05HSD- 441007 | FI
12.16 | SAC - Logic Diagrams | UNDER DEVELOPMENT | RPDU5.EL.310 | UNDER DEVELOPMENT | FI
12.17 | FGD - Control Architecture Scheme | S21001- EN01 - 05HSD- 441008 | RPDU5.EL.050 | S21001- EN01 - 05HSD- 441008 | FA
12.18 | SAC - Control Architecture Scheme | UNDER DEVELOPMENT | RPDU5.EL.350 | UNDER DEVELOPMENT | FA
12.19 | FGD - Control Cables Sizing - Technical Specification | S21001- TS01 - 05HSD- 447204 | RPDU5.PE.050 | S21001- TS01 - 05HSD- 447204 | FI
12.20 | SAC - Control Cables Sizing - Technical Specification | UNDER DEVELOPMENT | RPDU5.PE.350 | UNDER DEVELOPMENT | FI
12.21 | FGD - Hook-Up Diagrams | S21001- EN01 - 05HSD- 441009 | RPDU5.EL.051 | S21001- EN01 - 05HSD- 441009 | FI
12.22 | SAC - Hook-Up Diagrams | UNDER DEVELOPMENT | RPDU5.EL.351 | UNDER DEVELOPMENT | FI
12.23 | FGD - Control Room Layout Drawing | S21001- EN01 - 05UCA- 441010 | RPDU5.EL.052 | S21001- EN01 - 05UCA- 441010 | FA
12.24 | SAC - Control Room Layout Drawing | UNDER DEVELOPMENT | RPDU5.EL.352 | UNDER DEVELOPMENT | FA
12.25 | FGD - Instrument Location Plan Drawing | S21001- EN01 - 05HSD- 441011 | RPDU5.EL.353 | S21001- EN01 - 05HSD- 441011 | FI
12.26 | SAC - Instrument Location Plan Drawing | UNDER DEVELOPMENT | RPDU5.EL.553 | UNDER DEVELOPMENT | FI
12.27 | FGD - Junction Boxes Location Plan Drawing | S21001- EN01 - 05HSD- 441012 | RPDU5.EL.054 | S21001- EN01 - 05HSD- 441012 | FI
12.28 | SAC - Junction Boxes Location Plan Drawing | UNDER DEVELOPMENT | RPDU5.EL.354 | UNDER DEVELOPMENT | FI
21.6 | Interface with customer equipment, facilities - Instrumentation and control | S21001-EE01-05CPP-44001 to 441000 |  | S21001-EE01-05CPP-44001 to 441000 | FA
21.12 | Control System Graphic/Mimic (Design document of GUI Pages) | S21001- EN01-05CPP-441013 |  | S21001- EN01-05CPP-441013 | FA
21.13 | FAT Procedure of Control System | S21001- EN01-05HSD-441014 |  | S21001- EN01-05HSD-441014 | FI
21.14 | PLC FAT Report | S21001- EN01-05HSD-441015 |  | S21001- EN01-05HSD-441015 | FI
21.15 | PLC Power Supply & Grounding Scheme | S21001- EN01-05HSD-441016 |  | S21001- EN01-05HSD-441016 | FI
21.23 | Drive Control and Control Interfacing philosophy | S21001-EN01-05HSD-441017 |  | S21001-EN01-05HSD-441017 | FI
13 | FGD & SAC - ELECTRICAL SYSTEM
13.1 | FGD - Electrical Load List | S21001- EN01 - 05HSD - 331001 | RPDU5.EM.000 | S21001- EN01 - 05HSD - 331001 | FI
13.2 | SAC - Electrical Load List | UNDER DEVELOPMENT | RPDU5.EM.300 | UNDER DEVELOPMENT | FI
13.3 | FGD - Electrical & Control Cables List | S21001- EN01 - 05HSD - 331002 & S21001- EN01 - 05HSD - 331003 FOR CONTROL CABLES | RPDU5.EM.004 | S21001- EN01 - 05HSD - 331002 & S21001- EN01 - 05HSD - 331003 FOR CONTROL CABLES | FI
13.4 | SAC - Electrical & Control Cables List | UNDER DEVELOPMENT | RPDU5.EM.304 | UNDER DEVELOPMENT | FI
13.5 | FGD - Cable Trays / Conduit Layout with bill of quantities | S21001- EN01 - 05HSD - 331004 | RPDU5.EV.001 | S21001- EN01 - 05HSD - 331004 | FI
13.6 | SAC - Cable Trays / Conduit Layout with bill of quantities | UNDER DEVELOPMENT | RPDU5.EV.301 | UNDER DEVELOPMENT | FI
13.7 | FGD - Junction Boxes - Technical Specification | S21001- TS01 - 05HSD- 337204 | RPDU5.ED.001 | S21001- TS01 - 05HSD- 337204 | FI
13.8 | SAC - Junction Boxes - Technical Specification | UNDER DEVELOPMENT | RPDU5.ED.301 | UNDER DEVELOPMENT | FI
13.9 | FGD - PMCC, MCC, ACDB , DCDB and Booster Fan VFD Panel - Technical Specification | S21001- TS01 - 05HSD- 337205 | RPDU5.ED.002 | S21001- TS01 - 05HSD- 337205 | FI
13.10 | SAC - PMCC, MCC, ACDB and DCDB - Technical Specification | UNDER DEVELOPMENT | RPDU5.ED.302 | UNDER DEVELOPMENT | FI
13.11 | FGD - MOV - Technical Specification | S21001- TS01 - 05HSD- 337206 | RPDU5.ED.003 | S21001- TS01 - 05HSD- 337206 | FI
13.12 | SAC - MOV - Technical Specification | UNDER DEVELOPMENT | RPDU5.ED.303 | UNDER DEVELOPMENT | FI
13.13 | FGD - LT/HT motors - Technical Specification | S21001- TS01 - 05HSD- 337207 | RPDU5.ED.004 | S21001- TS01 - 05HSD- 337207 | FI
13.14 | SAC- LT/HT cables - Technical Specification | UNDER DEVELOPMENT | RPDU5.ED.304 | UNDER DEVELOPMENT | FI
13.15 | FGD - Electrical Single Line Diagram including Emergency Power Supply Bus from Existing DG set | S21001- EN01 - 05HSD - 331005 | RPDU5.EG.001 | S21001- EN01 - 05HSD - 331005 | FA
13.16 | SAC- Electrical Single Line Diagram | UNDER DEVELOPMENT | RPDU5.EG.301 | UNDER DEVELOPMENT | FA
13.17 | FGD - Cable Sizing - Technical Specification | S21001- TS01 - 05HSD- 337208 | RPDU5.ED.005 | S21001- TS01 - 05HSD- 337208 | FI
13.18 | SAC- Cable Sizing - Technical Specification | UNDER DEVELOPMENT | RPDU5.ED.305 | UNDER DEVELOPMENT | FI
13.19 | FGD - Individual Distribution Schemes/Control Schemes Drawing | S21001- EN01 - 05HSD - 331006 | RPDU5.EG.002 | S21001- EN01 - 05HSD - 331006 | FI
13.20 | SAC - Individual Distribution Schemes/Control Schemes Drawing | UNDER DEVELOPMENT | RPDU5.EG.302 | UNDER DEVELOPMENT | FI
13.21 | FGD - Illumination Scheme Drawing | S21001- EN01 - 05HSD - 331007 | RPDU5.EG.003 | S21001- EN01 - 05HSD - 331007 | FI
13.22 | SAC - Illumination Scheme Drawing | UNDER DEVELOPMENT | RPDU5.EG.303 | UNDER DEVELOPMENT | FI
13.23 | FGD - Plant lighting Layout Drawing | S21001- EN01 - 05HSD - 331008 | RPDU5.EG.004 | S21001- EN01 - 05HSD - 331008 | FI
13.24 | SAC - Plant lighting Layout Drawing | UNDER DEVELOPMENT | RPDU5.EG.304 | UNDER DEVELOPMENT | FI
13.25 | FGD - Grounding and Lightening System - Technical Specification | S21001-TS01-05HSD-337232 | RPDU5.ED.006 | S21001-TS01-05HSD-337232 | FI
13.26 | SAC - Grounding and Lightening System - Technical Specification | UNDER DEVELOPMENT | RPDU5.ED.306 | UNDER DEVELOPMENT | FI
13.27 | FGD - Grounding Scheme Drawing | S21001- EN01 - 05HSD - 331009 | RPDU5.EG.006 | S21001- EN01 - 05HSD - 331009 | FA
13.28 | SAC - Grounding Scheme Drawing | UNDER DEVELOPMENT | RPDU5.EG.306 | UNDER DEVELOPMENT | FA
13.29 | FGD - Lightening Protection Drawing | S21001- EN01 - 05HSD - 331010 | RPDU5.EG.007 | S21001- EN01 - 05HSD - 331010 | FA
13.30 | SAC - Lightening Protection Drawing | UNDER DEVELOPMENT | RPDU5.EG.307 | UNDER DEVELOPMENT | FA
13.31 | FGD - Plant Area Grounding and Lightening Protection Layout | S21001- EN01 - 05HSD - 331011 | RPDU5.EG.008 | S21001- EN01 - 05HSD - 331011 | FA
13.32 | SAC - Plant Area Grounding and Lightening Protection Layout | UNDER DEVELOPMENT | RPDU5.EG.308 | UNDER DEVELOPMENT | FA
13.33 | FGD - Electrical Equipment Layout including Booster Fan VFD Panel | S21001- EN01 - 05HSD - 331012 | RPDU5.EG.009 | S21001- EN01 - 05HSD - 331012 | FA
13.34 | SAC - Electrical Equipment Layout | UNDER DEVELOPMENT | RPDU5.EG.309 | UNDER DEVELOPMENT | FA
13.35 | FGD - Electrical Room Layout (Plan and Sections) | S21001- EN01 - 05HSD - 331013 | RPDU5.EG.010 | S21001- EN01 - 05HSD - 331013 | FA
13.36 | SAC - Electrical Room Layout (Plan and Sections) | UNDER DEVELOPMENT | RPDU5.EG.310 | UNDER DEVELOPMENT | FA
13.37 | FGD – Electrical/Control Cables and Glands - Technical Specification | S21001- TS01- 05HSD - 337209 | RPDU5.ED.007 | S21001- TS01- 05HSD - 337209 | FI
13.38 | SAC – Electrical/Control Cables and Glands - Technical Specification | UNDER DEVELOPMENT | RPDU5.ED.307 | UNDER DEVELOPMENT | FI
13.39 | FGD – Cable Trays - Technical Specification | S21001- TS01- 05HSD - 337210 | RPDU5.ED.008 | S21001- TS01- 05HSD - 337210 | FI
13.40 | SAC – Cable Trays - Technical Specification | UNDER DEVELOPMENT | RPDU5.ED.308 | UNDER DEVELOPMENT | FI
13.41 | FGD – LT Motors - Technical Specification | S21001- TS01- 05HSD - 337211 | RPDU5.ED.009 | S21001- TS01- 05HSD - 337211 | FI
13.42 | SAC – LT Motors - Technical Specification | UNDER DEVELOPMENT | RPDU5.ED.309 | UNDER DEVELOPMENT | FI
13.43 | FGD – HT Motors - Technical Specification | S21001- TS01- 05HSD - 337212 | RPDU5.ED.010 | S21001- TS01- 05HSD - 337212 | FI
13.44 | SAC – HT Motors - Technical Specification | UNDER DEVELOPMENT | RPDU5.ED.310 | UNDER DEVELOPMENT | FI
13.45 | FGD – LT & HT Switchgears - Technical Specification | S21001- TS01- 05HSD - 337213 | RPDU5.ED.011 | S21001- TS01- 05HSD - 337213 | FI
13.46 | SAC – LT & HT Switchgears - Technical Specification | UNDER DEVELOPMENT | RPDU5.ED.311 | UNDER DEVELOPMENT | FI
13.47 | FGD – Electrical Panels and Junction Boxes - Technical Specification | S21001- TS01- 05HSD - 337214 | RPDU5.ED.012 | S21001- TS01- 05HSD - 337214 | FI
13.48 | SAC – Electrical Panels and Junction Boxes - Technical Specification | UNDER DEVELOPMENT | RPDU5.ED.312 | UNDER DEVELOPMENT | FI
13.49 | FGD – LTMCC / Switchboard - Technical Specification | S21001- TS01- 05HSD - 337215 | RPDU5.ED.013 | S21001- TS01- 05HSD - 337215 | FI
13.50 | SAC – LTMCC / Switchboard - Technical Specification | UNDER DEVELOPMENT | RPDU5.ED.313 | UNDER DEVELOPMENT | FI
13.51 | FGD – UPS - Technical Specification | S21001- TS01- 05HSD - 337216 | RPDU5.ED.014 | S21001- TS01- 05HSD - 337216 | FI
13.52 | SAC – UPS - Technical Specification | UNDER DEVELOPMENT | RPDU5.ED.314 | UNDER DEVELOPMENT | FI
13.53 | FGD – UPS - Line Diagram | S21001- EN01 - 05HSD - 331014 | RPDU5.EG.011 | S21001- EN01 - 05HSD - 331014 | FA
13.54 | SAC – UPS - Line Diagram | UNDER DEVELOPMENT | RPDU5.EG.311 | UNDER DEVELOPMENT | FA
13.55 | FGD & SAC - Auxiliary power calculation for continuous running of FGD plant including SAC at full load. | S21001- EN01 - 05CPP - 331015 | RPDU5.ED.500 | S21001- EN01 - 05CPP - 331015 | FA
21.7 | Interface with customer equipment, facilities - Electrical | S21001-EE01-05CPP-33001 to 331000 |  | S21001-EE01-05CPP-33001 to 331000 | FA
21.16 | Design calculation for power, control, instrument and any special cables | S21001-EN01-05HSD-331016 |  | S21001-EN01-05HSD-331016 | FI
21.17 | Design calculation for LT bus duct | S21001-EN01-05HSD-331017 |  | S21001-EN01-05HSD-331017 | FI
21.18 | Design calculation for lighting system | S21001-EN01-05HSD-331018 |  | S21001-EN01-05HSD-331018 | FI
21.19 | Design calculation for lightening protection system | S21001-EN01-05HSD-331019 |  | S21001-EN01-05HSD-331019 | FI
21.20 | Design calculation for earthing system | S21001-EN01-05HSD-331020 |  | S21001-EN01-05HSD-331020 | FI
21.21 | Schematic and wiring diagrams for medium voltage system | S21001-EN01-05HSD-331021 |  | S21001-EN01-05HSD-331021 | FI
21.22 | Schematic and wiring diagrams for low voltage system | S21001-EN01-05HSD-331022 |  | S21001-EN01-05HSD-331022 | FI
21.24 | List of electrical equipment and materials (Bill of materials) | S21001-EN01-05HSD-331023 |  | S21001-EN01-05HSD-331023 | FI
14 | FGD & SAC - FIRE FIGHTING SYSTEM
14.1 | FGD Fire Fighting - Fire Fighting & Detection System Technical Specification | S21001- TS01- 05SGA - 772001 | RPDU5.ED.800 | S21001- TS01- 05SGA - 772001 | FI
14.2 | SAC Fire Fighting - Fire Fighting & Detection System Technical Specification | UNDER DEVELOPMENT | RPDU5.ED.830 | UNDER DEVELOPMENT | FI
14.2 | FGD Fire Fighting - Hydrant and Water Spray System - Schematic Diagram | S21001- EN01- 05SGA - 771001 | RPDU5.EL.800 | S21001- EN01- 05SGA - 771001 | FA
14.3 | SAC Fire Fighting - Alarm System - Schematic Diagram | UNDER DEVELOPMENT | RPDU5.EL.830 | UNDER DEVELOPMENT | FA
14.4 | FGD Fire Fighting - Hydrant and Water Spray System - Layout Drawing | S21001- EN01- 05SGA - 771002 | RPDU5.ML.800 | S21001- EN01- 05SGA - 771002 | FA
14.4 | SAC Fire Fighting - Hydrant and Water Spray System - Layout Drawing | UNDER DEVELOPMENT | RPDU5.ML.830 | UNDER DEVELOPMENT | FA
14.5 | FGD Fire Fighting - Hydrant System - Hydraulic Calculation | S21001- EN01- 05SGA - 771003 | RPDU5.MA.800 | S21001- EN01- 05SGA - 771003 | FI
14.5 | SAC Fire Fighting - Hydrant System - Hydraulic Calculation | UNDER DEVELOPMENT | RPDU5.MA.830 | UNDER DEVELOPMENT | FI
14.6 | FGD Fire Fighting - Water Spray System - Hydraulic Calculation | S21001- EN01- 05SGA - 771004 | RPDU5.MA.801 | S21001- EN01- 05SGA - 771004 | FI
14.6 | SAC Fire Fighting - Water Spray System - Hydraulic Calculation | UNDER DEVELOPMENT | RPDU5.MA.831 | UNDER DEVELOPMENT | FI
14.7 | FGD Fire Fighting - Component Data Sheet | S21001- EN01- 05SGA - 771005 | RPDU5.PA.800 | S21001- EN01- 05SGA - 771005 | FA
14.7 | SAC Fire Fighting - Component Data Sheet | UNDER DEVELOPMENT | RPDU5.PA.830 | UNDER DEVELOPMENT | FA
14.8 | FGD Fire Fighting - Alarm System at MCC and Control Room - General Arrangement Drawing | S21001- EN01- 05SGA - 771006 | RPDU5.ML.801 | S21001- EN01- 05SGA - 771006 | FA
14.9 | SAC Fire Fighting - Alarm System at MCC and Control Room - General Arrangement Drawing | UNDER DEVELOPMENT | RPDU5.ML.831 | UNDER DEVELOPMENT | FA
14.10 | FGD Fire Fighting - Fire Detection Alarm System - Data Sheet | S21001- EN01- 05SGA - 771007 | RPDU5.PA.801 | S21001- EN01- 05SGA - 771007 | FA
14.11 | SAC Fire Fighting - Fire Detection Alarm System - Data Sheet | UNDER DEVELOPMENT | RPDU5.PA.831 | UNDER DEVELOPMENT | FA
14.12 | FGD Fire Fighting - Fire Detection Alarm System - Layout | S21001- EN01- 05SGA - 771008 | RPDU5.ML.802 | S21001- EN01- 05SGA - 771008 | FA
14.13 | SAC Fire Fighting - Fire Detection Alarm System - Layout | UNDER DEVELOPMENT | RPDU5.ML.832 | UNDER DEVELOPMENT | FA
14.14 | FGD Fire Fighting - Fire Detection Alarm System - Schematic Drawing | S21001- EN01- 05SGA - 771009 | RPDU5.ML.803 | S21001- EN01- 05SGA - 771009 | FI
14.15 | SAC Fire Fighting - Fire Detection Alarm System - Schematic Drawing | UNDER DEVELOPMENT | RPDU5.ML.833 | UNDER DEVELOPMENT | FI
14.16 | FGD Fire Fighting - Fire Detection Alarm Equipment - Technical Specification | S21001-TS01- 05SGA- 772002 SHEET X OF XX | RPDU5.PA.802 | S21001-TS01- 05SGA- 772002 SHEET X OF XX | FI
14.17 | SAC Fire Fighting - Fire Detection Alarm Equipment - Technical Specification | UNDER DEVELOPMENT | RPDU5.PA.832 | UNDER DEVELOPMENT | FI
14.18 | FGD Fire Fighting - Fire Extinguishers - Technical Specification | S21001- TS01- 05SGA- 772003 SHEET X OF XX | RPDU5.PA.803 | S21001- TS01- 05SGA- 772003 SHEET X OF XX | FI
14.19 | SAC Fire Fighting - Fire Extinguishers - Technical Specification | UNDER DEVELOPMENT | RPDU5.PA.833 | UNDER DEVELOPMENT | FI
14.20 | FGD Fire Fighting - ERW steel pipes and fittings - Technical Specification | S21001- TS01- 05SGA- 772004 SHEET X OF XX | RPDU5.PA.804 | S21001- TS01- 05SGA- 772004 SHEET X OF XX | FI
14.21 | SAC Fire Fighting - ERW steel pipes and fittings - Technical Specification | UNDER DEVELOPMENT | RPDU5.PA.834 | UNDER DEVELOPMENT | FI
14.22 | FGD Fire Fighting - Pumps - Technical Specification | S21001- TS01- 05SGA- 772005 SHEET X OF XX | RPDU5.PA.805 | S21001- TS01- 05SGA- 772005 SHEET X OF XX | FI
14.23 | SAC Fire Fighting - Pumps - Technical Specification | UNDER DEVELOPMENT | RPDU5.PA.835 | UNDER DEVELOPMENT | FI
14.24 | FGD Fire Fighting - Sprinklers - Technical Specification | S21001- TS01- 05SGA- 772006 SHEET X OF XX | RPDU5.PA.806 | S21001- TS01- 05SGA- 772006 SHEET X OF XX | FI
14.25 | SAC Fire Fighting - Sprinklers - Technical Specification | UNDER DEVELOPMENT | RPDU5.PA.836 | UNDER DEVELOPMENT | FI
15 | FGD & SAC - PURCHASING TECHNICAL SPECIFICATIONS
15.1 | FGD - Booster Fan along with VFD sysytem - PTS Purchasing Technical Specification | S21001- TS01 - 05HSC- 227222 | RPDU5.PA.001 | S21001- TS01 - 05HSC- 227222 | FI
15.2 | FGD - Flue Gas Duct Expansion Joints - PTS Purchasing Technical Specification (Duplicate) | S21001- TS01 - 05HTA- 227223 | RPDU5.PA.002 | S21001- TS01 - 05HTA- 227223 | FI
15.3 | FGD - Flue Gas Duct Dampers - PTS Purchasing Technical Specification | S21001- TS01 - 05HTA- 227223 | RPDU5.PA.003 | S21001- TS01 - 05HTA- 227223 | FI
15.4 | FGD - Pumps - PTS Purchasing Technical Specification | S21001- TS01 - 05PBL- 227224 (FOR BACKWASH & DEMISTER) S21001- TS01 - 05PBL- 227225 (FOR FRESH WATER & MAKE UP WATER) S21001- TS01 - 05GNK- 227226 (FOR HCP) S21001- TS01 - 05HSM- 227227 (FOR WRP) S21001- TS01 - 05GNK- 227228 (FOR PWP) S21001- TS01 - 05HSM- 227229 (FOR WWTP) S21001- TS01 - 05GNK- 227230 (FOR PRP) S21001- TS01 - 05HSM- 227231 (FOR ATP) S21001- TS01 - 05HSM- 227232 (FOR RWRP) S21001- TS01 - 05XXX- 227233 (FOR ALP) | RPDU5.PA.005 | S21001- TS01 - 05PBL- 227224 (FOR BACKWASH & DEMISTER) S21001- TS01 - 05PBL- 227225 (FOR FRESH WATER & MAKE UP WATER) S21001- TS01 - 05GNK- 227226 (FOR HCP) S21001- TS01 - 05HSM- 227227 (FOR WRP) S21001- TS01 - 05GNK- 227228 (FOR PWP) S21001- TS01 - 05HSM- 227229 (FOR WWTP) S21001- TS01 - 05GNK- 227230 (FOR PRP) S21001- TS01 - 05HSM- 227231 (FOR ATP) S21001- TS01 - 05HSM- 227232 (FOR RWRP) S21001- TS01 - 05XXX- 227233 (FOR ALP) | FI
15.5 | SAC - Pumps - PTS Purchasing Technical Specification | S21001- TS01 - 05GNE- 997201 | RPDU5.PA.305 | S21001- TS01 - 05GNE- 997201 | FI
15.6 | FGD - Ash Filters - PTS Purchasing Technical Specification | S21001- TS01 - 05HSM- 227234 (WRPFS) S21001- TS01 - 05HSM- 227235 (WWTPFS) | RPDU5.PA.006 | S21001- TS01 - 05HSM- 227234 (WRPFS) S21001- TS01 - 05HSM- 227235 (WWTPFS) | FI
15.7 | FGD - MCU Flue Gas Cooling Nozzles and FGTR Washing Nozzles of SPC Modules - PTS Purchasing Technical Specification | FGTR-S21001- TS01 - 05HTD- 227236 MCU-S21001-TS01- 05HTH- 227243 | RPDU5.PA.007 | FGTR-S21001- TS01 - 05HTD- 227236 MCU-S21001-TS01- 05HTH- 227243 | FI
15.8 | SCA - Vapour-Liquid Separator, Reboiler Heater Exchanger, Acid Condenser, Circulation Pumps and Vacuum System - PTS Purchasing Technical Specification | UNDER DEVELOPMENT | RPDU5.PA.301 | UNDER DEVELOPMENT | FI
15.9 | FGD - MCU Mist Cooling Unit, FGTR Flue Gas Treatment Unit and Wet Stack - PTS Purchasing Technical Specification | S21001- TS01 - 05HSF- 227238 | RPDU5.PA.008 | S21001- TS01 - 05HSF- 227238 | FI
15.10 | FGD - Steel Tanks - PTS Purchasing Technical Specification | S21001- TS01 - 05PBL- 227239 (FRESH WATER) S21001- TS01 - 05PBL- 227240 (PROCESS WATER) S21001- TS01 - 05HSM- 227241(WASTE WATER TANK) S21001- TS01 - 05HSM- 227242 (RECOVERED WATER RETURN TANK) S21001- TS01 - 05XXX- 227237 (CONCENTRATED ACID TANK) | RPDU5.PA.010 | S21001- TS01 - 05PBL- 227239 (FRESH WATER) S21001- TS01 - 05PBL- 227240 (PROCESS WATER) S21001- TS01 - 05HSM- 227241(WASTE WATER TANK) S21001- TS01 - 05HSM- 227242 (RECOVERED WATER RETURN TANK) S21001- TS01 - 05XXX- 227237 (CONCENTRATED ACID TANK) | FI
15.11 | SAC - Steel Tanks - PTS Purchasing Technical Specification | UNDER DEVELOPMENT | RPDU5.PA.310 | UNDER DEVELOPMENT | FI
15.12 | FGD - FRP Tanks - PTS Purchasing Technical Specification | S21001- TS01 - 05HSD- 227244 | RPDU5.PA.011 | S21001- TS01 - 05HSD- 227244 | FI
15.13 | SAC - FRP Tanks - PTS Purchasing Technical Specification | UNDER DEVELOPMENT | RPDU5.PA.311 | UNDER DEVELOPMENT | FI
15.14 | FGD Electrical Buildings - HVAC - PTS Purchasing Technical Specification | S21001- TS01 - 05UCA- 337223 | RPDU5.PA.012 | S21001- TS01 - 05UCA- 337223 | FI
15.15 | SAC Buildings - HVAC - PTS Purchasing Technical Specification | UNDER DEVELOPMENT | RPDU5.PA.312 | UNDER DEVELOPMENT | FI
15.16 | FGD Electrical Buildings - Lighting - PTS Purchasing Technical Specification | S21001- TS01 - 05UCA- 337224 | RPDU5.PA.013 | S21001- TS01 - 05UCA- 337224 | FI
15.17 | SAC Buildings - Lighting - PTS Purchasing Technical Specification | UNDER DEVELOPMENT | RPDU5.PA.313 | UNDER DEVELOPMENT | FI
15.18 | FGD Electrical Buildings - Earthing Material and Lightning Arrestor - PTS Purchasing Technical Specification | S21001- TS01 - 05UCA- 337225 | RPDU5.PA.014 | S21001- TS01 - 05UCA- 337225 | FI
15.19 | SAC Buildings - Earthing Material and Lightning Arrestor - PTS Purchasing Technical Specification | UNDER DEVELOPMENT | RPDU5.PA.314 | UNDER DEVELOPMENT | FI
15.20 | FGD - Lifting devices - PTS Purchasing Technical Specification | S21001- TS01 - 05HSD- 227245 | RPDU5.PA.015 | S21001- TS01 - 05HSD- 227245 | FI
15.21 | SAC - Lifting devices - PTS Purchasing Technical Specification | UNDER DEVELOPMENT | RPDU5.PA.315 | UNDER DEVELOPMENT | FI
15.22 | FGD - Flue Gas Duct (including supporting structures, stairs and platforms) - PTS Purchasing Technical Specification | S21001- TS01 - 05UVZ- 227246 | RPDU5.PA.009 | S21001- TS01 - 05UVZ- 227246 | FI
15.23 | FGD - Linings - PTS Purchasing Technical Specification | S21001-TS01-05HSD-22 | RPDU5.PA.015 | S21001-TS01-05HSD-22 | FI
15.24 | SAC - Linings - PTS Purchasing Technical Specification | UNDER DEVELOPMENT | RPDU5.PA.315 | UNDER DEVELOPMENT | FI
15.25 | FGD - Paintings - PTS Purchasing Technical Specification | S21001- TS01 - 05HSD- 227247 | RPDU5.PA.016 | S21001- TS01 - 05HSD- 227247 | FI
15.26 | SAC - Paintings - PTS Purchasing Technical Specification | UNDER DEVELOPMENT | RPDU5.PA.316 | UNDER DEVELOPMENT | FI
15.27 | FGD - Heat Insulations - PTS Purchasing Technical Specification | S21001- TS01- 05HSD- 227248 | RPDU5.PA.017 | S21001- TS01- 05HSD- 227248 | FI
15.28 | SAC - Heat Insulations - PTS Purchasing Technical Specification | UNDER DEVELOPMENT | RPDU5.PA.317 | UNDER DEVELOPMENT | FI
15.29 | FGD - Piping - PTS Purchasing Technical Specification | S21001- TS01- 05HSD- 227249 | RPDU5.PA.018 | S21001- TS01- 05HSD- 227249 | FI
15.30 | SAC - Piping - PTS Purchasing Technical Specification | UNDER DEVELOPMENT | RPDU5.PA.318 | UNDER DEVELOPMENT | FI
15.31 | FGD - Piping Support - PTS Purchasing Technical Specification | S21001- TS01- 05HSD- 227250 | RPDU5.PA.019 | S21001- TS01- 05HSD- 227250 | FI
15.32 | SAC - Piping Support - PTS Purchasing Technical Specification | UNDER DEVELOPMENT | RPDU5.PA.319 | UNDER DEVELOPMENT | FI
15.33 | FGD - Control System - PTS Purchasing Technical Specification | S21001- TS01- 05HSD- 337226 | RPDU5.PA.020 | S21001- TS01- 05HSD- 337226 | FI
15.34 | SAC - Control System - PTS Purchasing Technical Specification | UNDER DEVELOPMENT | RPDU5.PA.320 | UNDER DEVELOPMENT | FI
15.35 | FGD - Instrumentation - PTS Purchasing Technical Specification | S21001- TS01- 05HSD-337227 | RPDU5.PA.021 | S21001- TS01- 05HSD-337227 | FI
15.36 | SAC - Instrumentation - PTS Purchasing Technical Specification | UNDER DEVELOPMENT | RPDU5.PA.321 | UNDER DEVELOPMENT | FI
15.37 | FGD - Electrical & Control Cables - PTS Purchasing Technical Specification | S21001- TS01- 05HSD- 337228 (POWERCABLES) S21001- TS01- 05HSD- 447205 (CONTROL CABLES) | RPDU5.PA.022 | S21001- TS01- 05HSD- 337228 (POWERCABLES) S21001- TS01- 05HSD- 447205 (CONTROL CABLES) | FI
15.38 | SAC - Electrical & Control Cables - PTS Purchasing Technical Specification | UNDER DEVELOPMENT | RPDU5.PA.322 | UNDER DEVELOPMENT | FI
15.39 | FGD - Cable Trays and Conduit - PTS Purchasing Technical Specification | S21001- TS01- 05HSD- 337229 (TRAYS) S21001- TS01- 05HSD- 337230 (CONDUITS) | RPDU5.PA.023 | S21001- TS01- 05HSD- 337229 (TRAYS) S21001- TS01- 05HSD- 337230 (CONDUITS) | FI
15.40 | SAC - Cable Trays and Conduit - PTS Purchasing Technical Specification | UNDER DEVELOPMENT | RPDU5.PA.323 | UNDER DEVELOPMENT | FI
15.41 | FGD - Switchboard, Distribution and Utilities Boards - PTS Purchasing Technical Specification | S21001- TS01- 05HSD- 337231 | RPDU5.PA.024 | S21001- TS01- 05HSD- 337231 | FI
15.42 | SAC - Switchboard, Distribution and Utilities Boards - PTS Purchasing Technical Specification | UNDER DEVELOPMENT | RPDU5.PA.324 | UNDER DEVELOPMENT | FI
15.43 | FGD - Illumination/Lighting (Outside and inside) - PTS Purchasing Technical Specification | WILL DEVELOP IF REQUIRED | RPDU5.PA.025 | WILL DEVELOP IF REQUIRED | FI
15.44 | SAC - Illumination/Lighting (Outide and inside) - PTS Purchasing Technical Specification | WILL DEVELOP IF REQUIRED | RPDU5.PA.325 | WILL DEVELOP IF REQUIRED | FI
15.45 | FGD - Earthing Material and Lightning System - PTS Purchasing Technical Specification | WILL DEVELOP IF REQUIRED | RPDU5.PA.026 | WILL DEVELOP IF REQUIRED | FI
15.46 | SAC - Earthing Material and Lightning System - PTS Purchasing Technical Specification | WILL DEVELOP IF REQUIRED | RPDU5.PA.326 | WILL DEVELOP IF REQUIRED | FI
15.47 | FGD - Fire Fighting System - PTS Purchasing Technical Specification (if any) | S21001- TS01- 05SGA- 772007 | RPDU5.PA.027 | S21001- TS01- 05SGA- 772007 | FI
15.48 | SAC - Fire Fighting System - PTS Purchasing Technical Specification (if any) | WILL DEVELOP IF REQUIRED | RPDU5.PA.327 | WILL DEVELOP IF REQUIRED | FI
15.49 | FGD & SAC - Foundations Piling Works - PTS Purchasing Technical Specification (if piling is required) (No piling work) | WILL DEVELOP IF REQUIRED | RPDU5.PA.500 | WILL DEVELOP IF REQUIRED | FI
15.50 | FGD & SAC - Civil Works Procedure - PTS Purchasing Technical Specification | S21001- TS01- 05CPP- 555001 | RPDU5.PA.501 | S21001- TS01- 05CPP- 555001 | FI
15.51 | FGD & SAC - Mechanical Erection Works Procedure - PTS Purchasing Technical Specification | S21001- PS01- 05CPP- 225001 | RPDU5.PA.502 | S21001- PS01- 05CPP- 225001 | FI
15.52 | FGD & SAC - Electrical, Instrumentation and Control Installation Works Procedure- PTS Purchasing Technical Specification | S21001- PS01- 05CPP- 335001 | RPDU5.PA.503 | S21001- PS01- 05CPP- 335001 | FI
16 | FGD & SAC - QUALITY ASSURANCE
16.1 | FGD & SAC - Project Quality Control Manual (with Job Organization Chart) | S21001- QA01- 05CPP- 662001 | RPDU5.QB.501 | S21001- QA01- 05CPP- 662001 | FI
16.2 | FGD & SAC - Quality Control Plan | S21001- QA01- 05CPP- 662002 | RPDU5.QB.502 | S21001- QA01- 05CPP- 662002 | FI
16.3 | FGD & SAC - Overall Inspection and Test Plan | S21001- QA01- 05CPP- 662003 | RPDU5.QF.500 | S21001- QA01- 05CPP- 662003 | FA
16.4 | FGD & SAC - Final Quality Dossier | S21001- QA01- 05CPP- 662004 | RPDU5.QB.550 | S21001- QA01- 05CPP- 662004 | FI
16.5 | FGD & SAC - HAZOP study and ARM analysis (Availability, Reliability & Maintainability) | S21001- QA01- 05CPP- 662005 | RPDU5.QB.505 | S21001- QA01- 05CPP- 662005 | FI
17 | FGD & SAC - QUALITY CONTROL FOR FABRICATION
17.1 | FGD & SAC - ITP Inspection and Test Plans for Fabrication | S21001- IT01- 05CPP- 664001 | RPDU5.QB.503 | S21001- IT01- 05CPP- 664001 | FI
17.2 | FGD & SAC - Ball Valves - ITP Inspection and Test Plan for Fabrication | S21001- IT01- 05CPP- 664002 | RPDU5.QF.501 | S21001- IT01- 05CPP- 664002 | FI
17.3 | FGD & SAC - Butterfly Valves - ITP Inspection and Test Plan for Fabrication | S21001- IT01- 05CPP- 664003 | RPDU5.QF.502 | S21001- IT01- 05CPP- 664003 | FI
17.4 | FGD & SAC - Check Valves - ITP Inspection and Test Plan for Fabrication | S21001- IT01- 05CPP- 664004 | RPDU5.QF.503 | S21001- IT01- 05CPP- 664004 | FI
17.5 | FGD & SAC - Fiberglass Piping Prefabricated - ITP Inspection and Test Plan for Fabrication | S21001- IT01- 05CPP- 664005 | RPDU5.QF.504 | S21001- IT01- 05CPP- 664005 | FI
17.6 | FGD & SAC - Piping Expansion Joint - ITP Inspection and Test Plan for Fabrication | S21001- IT01- 05CPP- 664006 | RPDU5.QF.505 | S21001- IT01- 05CPP- 664006 | FI
17.7 | FGD & SAC - Carbon Steel Tanks - ITP Inspection and Test Plan for Fabrication | S21001- IT01- 05CPP- 664007 | RPDU5.QF.506 | S21001- IT01- 05CPP- 664007 | FI
17.8 | FGD & SAC - Pressure Vessels - ITP Inspection and Test Plan for Fabrication (No Pressure Vessels) | WILL DEVELOP IF REQUIRED | RPDU5.QF.507 | WILL DEVELOP IF REQUIRED | FI
17.9 | FGD & SAC - Fiberglass Tanks - ITP Inspection and Test Plan for Fabrication | S21001- IT01- 05CPP- 664008 | RPDU5.QF.508 | S21001- IT01- 05CPP- 664008 | FI
17.10 | FGD & SAC - Spray Nozzles - ITP Inspection and Test Plan for Fabrication | S21001- IT01- 05CPP- 664009 | RPDU5.QF.509 | S21001- IT01- 05CPP- 664009 | FI
17.11 | FGD & SAC - Booster Fan - ITP Inspection and Test Plan for Fabrication | S21001- IT01- 05CPP- 664010 | RPDU5.QF.510 | S21001- IT01- 05CPP- 664010 | FI
17.12 | FGD & SAC - Blowers - ITP Inspection and Test Plan for Fabrication | S21001- IT01- 05CPP- 664011 | RPDU5.QF.511 | S21001- IT01- 05CPP- 664011 | FI
17.13 | FGD & SAC - Fans - ITP Inspection and Test Plan for Fabrication | S21001- IT01- 05CPP- 664012 | RPDU5.QF.512 | S21001- IT01- 05CPP- 664012 | FI
17.14 | FGD & SAC - Centrifugal Pumps - ITP Inspection and Test Plan for Fabrication | S21001- IT01- 05CPP- 664013 | RPDU5.QF.513 | S21001- IT01- 05CPP- 664013 | FI
17.15 | SAC - Evaporators - ITP Inspection and Test Plan for Fabrication | S21001- IT01- 05CPP- 664014 | RPDU5.QF.514 | S21001- IT01- 05CPP- 664014 | FI
17.16 | SAC - Heat Exchangers - ITP Inspection and Test Plan for Fabrication | S21001- IT01- 05CPP- 664015 | RPDU5.QF.515 | S21001- IT01- 05CPP- 664015 | FI
17.17 | FGD & SAC - Carbon Steel Plates Painted - ITP Inspection and Test Plan for Fabrication | S21001- IT01- 05CPP- 664016 | RPDU5.QF.516 | S21001- IT01- 05CPP- 664016 | FI
17.18 | FGD & SAC - Alloy Steel Plates - ITP Inspection and Test Plan for Fabrication | S21001- IT01- 05CPP- 664017 | RPDU5.QF.517 | S21001- IT01- 05CPP- 664017 | FI
17.19 | FGD & SAC - Main Steel Structures - ITP Inspection and Test Plan for Fabrication | S21001- IT01- 05CPP- 664018 | RPDU5.QF.518 | S21001- IT01- 05CPP- 664018 | FI
17.20 | FGD & SAC - Flue Gas Duct - ITP Inspection and Test Plan for Fabrication | S21001- IT01- 05CPP- 664019 | RPDU5.QF.519 | S21001- IT01- 05CPP- 664019 | FI
17.21 | FGD & SAC - Flue Gas Dampers - ITP Inspection and Test Plan for Fabrication | S21001- IT01- 05CPP- 664020 | RPDU5.QF.520 | S21001- IT01- 05CPP- 664020 | FI
17.22 | FGD & SAC - Instrumentation - ITP Inspection and Test Plan for Fabrication | S21001- IT01- 05CPP- 664021 | RPDU5.QF.521 | S21001- IT01- 05CPP- 664021 | FI
17.23 | FGD & SAC - Analytical Instrument - ITP Inspection and Test Plan for Fabrication | S21001- IT01- 05CPP- 664022 | RPDU5.QF.522 | S21001- IT01- 05CPP- 664022 | FI
17.24 | FGD & SAC - Instrument Frames - ITP Inspection and Test Plan for Fabrication | S21001- IT01- 05CPP- 664023 | RPDU5.QF.523 | S21001- IT01- 05CPP- 664023 | FI
17.25 | FGD & SAC - Cables - ITP Inspection and Test Plan for Fabrication | S21001- IT01- 05CPP- 664024 | RPDU5.QF.524 | S21001- IT01- 05CPP- 664024 | FI
17.26 | FGD & SAC - PLC Local Control Panels - ITP Inspection and Test Plan for Fabrication | S21001- IT01- 05CPP- 664025 | RPDU5.QF.525 | S21001- IT01- 05CPP- 664025 | FI
17.27 | FGD -Ash Filters-ITP Inspection and Test Plan for Fabrication | S21001- IT01- 05CPP- 664045 |  | S21001- IT01- 05CPP- 664045 | FI
18 | FGD & SAC - QUALITY CONTROL FOR ERECTION AND CIVIL WORKS
18.1 | FGD & SAC - ITP Inspection and Test Plans for Civil & Erection Works | S21001- IT01- 05CPP- 664026 | RPDU5.QB.504 | S21001- IT01- 05CPP- 664026 | FI
18.2 | FGD & SAC - Booster Fan - ITP Inspection and Test Plan for Erection Works | S21001- IT01- 05CPP- 664027 | RPDU5.QM.501 | S21001- IT01- 05CPP- 664027 | FI
18.3 | FGD & SAC - Flue Gas Duct - ITP Inspection and Test Plan for Erection Works | S21001- IT01- 05CPP- 664028 | RPDU5.QM.502 | S21001- IT01- 05CPP- 664028 | FI
18.4 | FGD & SAC - Equipment Mechanical - ITP Inspection and Test Plan for Erection Works | S21001- IT01- 05CPP- 664029 | RPDU5.QM.503 | S21001- IT01- 05CPP- 664029 | FI
18.6 | FGD & SAC - Electrical Equipment - ITP Inspection and Test Plan for Erection Works | S21001- IT01- 05CPP- 664030 | RPDU5.QM.504 | S21001- IT01- 05CPP- 664030 | FI
18.7 | FGD & SAC - Instrumentation - ITP Inspection and Test Plan for Erection Works | S21001- IT01- 05CPP- 664031 | RPDU5.QM.505 | S21001- IT01- 05CPP- 664031 | FI
18.8 | FGD & SAC - Piping - ITP Inspection and Test Plan for Erection Works | S21001- IT01- 05CPP- 664032 | RPDU5.QM.506 | S21001- IT01- 05CPP- 664032 | FI
18.9 | FGD & SAC - Cables - ITP Inspection and Test Plan for Erection Works | S21001- IT01- 05CPP- 664033 | RPDU5.QM.507 | S21001- IT01- 05CPP- 664033 | FI
18.10 | FGD & SAC - Insulation - ITP Inspection and Test Plan for Erection Works | S21001- IT01- 05CPP- 664034 | RPDU5.QM.508 | S21001- IT01- 05CPP- 664034 | FI
18.11 | FGD & SAC - Mist Cooling Unit (MCU) - ITP Inspection and Test Plan for Erection Works | S21001- IT01- 05CPP- 664035 | RPDU5.QM.509 | S21001- IT01- 05CPP- 664035 | FI
18.11 | FGD & SAC - Flue Gas Treatment Reactor (FGTR) - ITP Inspection and Test Plan for Erection Works | S21001- IT01- 05CPP- 664036 | RPDU5.QM.510 | S21001- IT01- 05CPP- 664036 | FI
18.12 | FGD & SAC - Tanks - ITP Inspection and Test Plan for Erection Works | S21001- IT01- 05CPP- 664037 | RPDU5.QM.511 | S21001- IT01- 05CPP- 664037 | FI
18.13 | FGD & SAC - Site Painting - ITP Inspection and Test Plan for Erection Works | S21001- IT01- 05CPP- 664038 | RPDU5.QM.512 | S21001- IT01- 05CPP- 664038 | FI
18.14 | FGD & SAC - Glass Flake Lining - ITP Inspection and Test Plan for Erection Works | S21001- IT01- 05CPP- 664039 | RPDU5.QM.513 | S21001- IT01- 05CPP- 664039 | FI
18.15 | FGD & SAC - Concrete Works - ITP Inspection and Test Plan for Civil Works | S21001- IT01- 05CPP- 664040 | RPDU5.QM.514 | S21001- IT01- 05CPP- 664040 | FI
18.26 | FGD & SAC - System Deluge-Sprinkler - ITP Inspection and Test Plan for Civil Works | S21001- IT01- 05CPP- 664041 | RPDU5.QM.515 | S21001- IT01- 05CPP- 664041 | FI
18.28 | SAC - Earthing Lighting Protection System Installation - ITP Inspection and Test Plan for Civil Works | S21001- IT01- 05CPP- 664042 | RPDU5.QM.516 | S21001- IT01- 05CPP- 664042 | FI
18.28 | SAC - Roof and Cladding - ITP Inspection and Test Plan for Civil Works | S21001- IT01- 05CPP- 664043 | RPDU5.QM.517 | S21001- IT01- 05CPP- 664043 | FI
18.29 | FGD -Ash Filters-ITP Inspection and Test Plan for Erection | S21001- IT01- 05CPP- 664044 |  | S21001- IT01- 05CPP- 664044 | FI
19 | FGD & SAC - PROCEDURES AND MANUALS
19.1 | FGD - Flue Gas Duct - Erection Procedure | S21001-PS01- 05HTA- 225002 | RPDU5.PM.001 | S21001-PS01- 05HTA- 225002 | FI
19.2 | FGD - MCU Mist Cooling Unit - Erection Procedure | S21001-PS01- 05HTH- 225003 | RPDU5.PM.002 | S21001-PS01- 05HTH- 225003 | FI
19.3 | FGD - FGTR Flue Gas Treatment Reactor - Erection Procedure | S21001-PS01- 05HSD- 225004 | RPDU5.PM.003 | S21001-PS01- 05HSD- 225004 | FI
19.4 | FGD - Booster Fan including VFD system/panel - Erection Procedure | S21001-PS01- 05HSC- 225005 | RPDU5.PM.004 | S21001-PS01- 05HSC- 225005 | FI
19.5 | FGD & SAC - Tanks & Vessels - Erection Procedure | S21001-PS01-05CPP- 225001 | RPDU5.PM.005 | S21001-PS01-05CPP- 225001 | FI
19.6 | FGD & SAC - Piping - Erection Procedure | S21001-PS01- 05CPP- 225002 | RPDU5.PM.006 | S21001-PS01- 05CPP- 225002 | FI
19.7 | SAC - Erection Procedure | UNDER DEVELOPMENT | RPDU5.PM.007 | UNDER DEVELOPMENT | FI
19.8 | FGD - MCU Mist Cooling Unit - Commissioning Procedure | S21001-CC01-05HTH-228500 | RPDU5.PM.010 | S21001-CC01-05HTH-228500 | FI
19.9 | FGD - FGTR Flue Gas Treatment Reactor - Commissioning Procedure | S21001-CC01-05HSD-228501 | RPDU5.PM.011 | S21001-CC01-05HSD-228501 | FI
19.10 | FGD - Booster Fan - Commissioning Procedure | S21001-CC01-05HSC-228502 | RPDU5.PM.012 | S21001-CC01-05HSC-228502 | FI
19.11 | FGD & SAC - Pumps - Commissioning Procedure | S21001-CC01-05HSD-228503 S21001-CC01-05GNE-998503 | RPDU5.PM.013 | S21001-CC01-05HSD-228503 S21001-CC01-05GNE-998503 | FI
19.12 | SAC - Comissioning Procedure | UNDER DEVELOPMENT | RPDU5.PM.014 | UNDER DEVELOPMENT | FI
19.13 | FGD & SAC - Fire Fighting System - Commissioning Procedure | S21001- CC01- 05SGA- 778500 | RPDU5.PM.015 | S21001- CC01- 05SGA- 778500 | FI
19.14 | FGD - Performance Test Procedure | S21001-CC01-05HSD-228510 | RPDU5.PM.100 | S21001-CC01-05HSD-228510 | FA
19.15 | SAC - Performance Test Procedure | UNDER DEVELOPMENT | RPDU5.PM.300 | UNDER DEVELOPMENT | FA
19.16 | FGD - Operation & Maintenance Manual | S21001-MA01-05HSD-228511 | RPDU5.PM.110 | S21001-MA01-05HSD-228511 | FI
19.17 | SAC - Operation & Manintenance Manual | UNDER DEVELOPMENT | RPDU5.PM.310 | UNDER DEVELOPMENT | FI
20 | FGD & SAC - PROCEDURES AND MANUALS
20.1 | FGD & SAC- Master Project Schedule | S21001-MS01-05CPP-118400 | RPDU5.BA.001 | S21001-MS01-05CPP-118400 | FI
20.2 | FGD & SAC- Engineering Document List(EDL/MDL) | S21001-EN01-05CPP-221030 | RPDU5.BA.002 | S21001-EN01-05CPP-221030 | FI
| FGD & SAC KKS identification system | S21001- PM01-05CPP-121004
| FGD & SAC Drawing Standard Sheet and Document Cover Sheet | S21001- PM01-05CPP-121005
| SMARTLuth Organization Chart | S21001-PM01-05CPP- 121003
Note on C22: suman das: BOOSTER FAN RELATED WILL BE MARKED AS "HSC" "HNC" TO BE UPDATED AS "HSC"

## 5.1.2022
Engineering Document List / Master Document List
Project No: S21001 |  |  |  |  | APPROVAL CAT | 78
Project Name: FGD Treatment (SPC Technology) U5 - 1 x 80 MWe Renusagar Captive Power Plant, Hindalco –by W.L.Gore & Associates |  |  |  |  | INFORMATION CAT | 289
DOCUMENT NO: S21001-EN01-05CPP-221030_REV 0 DATED 6.1.2022
Pos |  | Initial Release (Void VERSION) | SMARTLUTH DRAWING NO./DOCUMENT NO. | GORE Document Number | HINDALCO Document Number | Based on B&V Experience Document type "FA" for approval or "FI" for information by HINDALCO
1 | FGD & SAC - PROCESS
1.1 | FGD - Process Flow Diagram with Mass Balance | S21001- XF01 - 05HSD- 227001 SHEET X OF XX | S21001- XF01 - 05HSD- 227001 SHEET X OF XX | RPDU5.MP.001 | S21001- XF01 - 05HSD- 227001 SHEET X OF XX | FA
1.2 | SAC - Process Flow Diagram with Mass Balance |  | UNDER DEVELOPMENT | RPDU5.MP.301 | UNDER DEVELOPMENT | FA
1.3 | FGD & SAC - Media Specification |  | S21001-EN01-05CPP-111001 | RPDU5.MP.500 | S21001-EN01-05CPP-111001 | FI
1.4 | FGD - Process and Instrumentation Diagrams (with KKS or other Hindalco numbering System) |  | S21001- XG01 - 05HSD- 227101 SHEET X OF XX | RPDU5.MP.010 | S21001- XG01 - 05HSD- 227101 SHEET X OF XX | FA
1.5 | SAC - Process and Instrumentation Diagrams (with KKS or other Hindalco numbering System) |  | UNDER DEVELOPMENT | RPDU5.MP.310 | UNDER DEVELOPMENT | FA
1.6 | FGD & SAC -Equipment List |  | S21001-EN01-05CPP-111002 INCLUDES S21001- EN01 - 05HSD- 221001 S21001-EN01-05GNE-XXXXXX | RPDU5.MM.000 | S21001-EN01-05CPP-111002 INCLUDES S21001- EN01 - 05HSD- 221001 S21001-EN01-05GNE-XXXXXX | FI
1.7 | FGD - Technical Specification with equipment sizing |  | S21001- TS01 - 05HSD- 227201 | RPDU5.PG.001 | S21001- TS01 - 05HSD- 227201 | FA
1.8 | SAC - Technical Specification with equipment sizing | S21001-TS01- 05GNE- 997201 | S21001-TS01- 05GNE- 997201 | RPDU5.PG.301 | S21001-TS01- 05GNE- 997201 | FA
1.9 | FGD - Computerized Fluid-dynamic Simulation (CFD) |  | S21001- EN01 - 05HSD- 221002 | RPDU5.MA.001 | S21001- EN01 - 05HSD- 221002 | FA
1.10 | FGD - Performance Curve Inlet SOx vs. Outlet SOx |  | S21001- EN01 - 05CPP- 221003 | RPDU5.PG.002 | S21001- EN01 - 05CPP- 221003 | FI
1.11 | FGD - Specification of Performance Guaranteed Parameters |  | S21001- EN01 - 05CPP- 221004 | RPDU5.PG.003 | S21001- EN01 - 05CPP- 221004 | FA
1.12 | SAC - Specification of Performance Guaranteed Parameters |  | UNDER DEVELOPMENT | RPDU5.PG.303 | UNDER DEVELOPMENT | FA
21.1 | Interface with customer equipment, facilities - Mechanical |  | S21001-EE01-05CPP-22001 to 221000 |  | S21001-EE01-05CPP-22001 to 221000 | FA
2 | FGD & SAC - EQUIPMENT TECHNICAL SPECIFICATIONS
2.1 | FGD - Booster Fan - Technical Specification | S21001-TS01- 05HNC- 227202 | S21001- TS01 - 05HSC- 227202 | RPDU5.PG.030 | S21001- TS01 - 05HSC- 227202 | FI
2.2 | FGD - Flue Gas Duct Expansion Joint - Technical Specification |  | S21001- TS01 - 05HTA- 227203 | RPDU5.PG.031 | S21001- TS01 - 05HTA- 227203 | FI
2.3 | FGD - Flue Gas Duct Dampers - Technical Specification |  | S21001- TS01 - 05HTA- 227204 SHEET X OF XX | RPDU5.PG.032 | S21001- TS01 - 05HTA- 227204 SHEET X OF XX | FI
2.4 | FGD - Hot Air Sealing Package for Dampers - Technical Specification |  | IT IS NOT REQUIRED | RPDU5.PG.033 | IT IS NOT REQUIRED | FI
2.5 | FGD - Process Recycle Pumps - Technical Specification |  | S21001- TS01 - 05GNK- 227205 | RPDU5.PG.034 | S21001- TS01 - 05GNK- 227205 | FI
2.6 | FGD - Ash Filters - Technical Specification |  | S21001- TS01 - 05HSM- 227206 | RPDU5.PG.035 | S21001- TS01 - 05HSM- 227206 | FI
2.7 | FGD - Hopper Cleaning Pumps - Technical Specification |  | S21001- TS01 - 05GNK- 227207 | RPDU5.PG.036 | S21001- TS01 - 05GNK- 227207 | FI
2.8 | FGD - Wash Recycle Pumps - Technical Specification |  | S21001- TS01 - 05HSM- 227208 | RPDU5.PG.037 | S21001- TS01 - 05HSM- 227208 | FI
2.9 | FGD - Wash Recycle Ash Filters - Technical Specification |  | S21001- TS01 - 05HSM- 227209 | RPDU5.PG.038 | S21001- TS01 - 05HSM- 227209 | FI
2.10 | FGD - Process Water Pumps - Technical Specification |  | S21001- TS01 - 05GNK- 227210 | RPDU5.PG.039 | S21001- TS01 - 05GNK- 227210 | FI
2.11 | FGD - Acid Transfer Pumps - Technical Specification |  | S21001- TS01 - 05HSM- 227211 | RPDU5.PG.040 | S21001- TS01 - 05HSM- 227211 | FI
2.12 | FGD - FGTR Washing Grid and Nozzles of SPC Modules - Technical Specification |  | S21001- TS01 - 05HTD- 227213 S21001- TS01 - 05HTD- 227214 | RPDU5.PG.041 | S21001- TS01 - 05HTD- 227213 S21001- TS01 - 05HTD- 227214 | FI
2.13 | FGD - MCU Flue Gas Cooling Grid and Nozzles - Technical Specification | S21001-TS01- 05HTH- 227212 | S21001-TS01- 05HTH- 227212 S21001-TS01- 05HSQ-XXXXX | RPDU5.PG.043 | S21001-TS01- 05HTH- 227212 S21001-TS01- 05HSQ-XXXXX | FI
2.14 | SAC - Vapour-Liquid Separator - Technical Specification |  | UNDER DEVELOPMENT | RPDU5.PG.330 | UNDER DEVELOPMENT | FI
2.15 | SAC - Reboiler Heater Exchanger - Technical Specification |  | UNDER DEVELOPMENT | RPDU5.PG.331 | UNDER DEVELOPMENT | FI
2.16 | SAC - Acid Condenser - Technical Specification |  | UNDER DEVELOPMENT | RPDU5.PG.332 | UNDER DEVELOPMENT | FI
2.17 | SAC - Circulation Pumps - Technical Specification |  | UNDER DEVELOPMENT | RPDU5.PG.333 | UNDER DEVELOPMENT | FI
2.18 | SAC - Vacuum System - Technical Specification |  | UNDER DEVELOPMENT | RPDU5.PG.334 | UNDER DEVELOPMENT | FI
3 | FGD & SAC - MCU, FGTR, TANKS, VESSELS AND STEEL STRUCTURES DRAWINGS
3.1 | FGD - Structural Steel Materials - Technical Specification |  | S21001-TS01-05HSD-227252 | RPDU5.PA.100 | S21001-TS01-05HSD-227252 | FI
3.2 | SAC - Structural Steel Materials - Technical Specification |  | S21001-TS01-05GNE-XXXXXX | RPDU5.PA.300 | S21001-TS01-05GNE-XXXXXX | FI
3.3 | FGD - MCU Mist Cooling Unit - Mechanical Calculation according to Indian Standard (latest edition) |  | S21001- EN01 - 05HTH - 221005 | RPDU5.MA.001 | S21001- EN01 - 05HTH - 221005 | FA
3.4 | FGD - MCU Mist Cooling Unit - Outline Drawing (including hoppers, supporting steel structure, stairs and platforms) with design data, nozzles chart and loads on foundation |  | S21001- EN01 - 05HTH - 221006 & S21001- EN01 - 05UVX - 221007 (For Structural steel, Galleries, Stairs & Platforms) | RPDU5.MV.001 | S21001- EN01 - 05HTH - 221006 & S21001- EN01 - 05UVX - 221007 (For Structural steel, Galleries, Stairs & Platforms) | FA
3.5 | FGD - MCU Mist Cooling Unit - Construction Drawings (including hoppers, supporting steel structure, stairs and platforms) |  | S21001- EN01 - 05HTH - 221008 & S21001- EN01 - 05UVX - 221009 (For Structural steel, Galleries, Stairs & Platforms) | RPDU5.MV.002 | S21001- EN01 - 05HTH - 221008 & S21001- EN01 - 05UVX - 221009 (For Structural steel, Galleries, Stairs & Platforms) | FI
3.6 | FGD - FGTR Flue Gas Treatment Reactor - Mechanical Calculation according to Indian Standard (latest edition) |  | S21001- EN01 - 05HSD - 221010 | RPDU5.MA.002 | S21001- EN01 - 05HSD - 221010 | FA
3.7 | FGD - FGTR Flue Gas Treatment Reactor - Outline Drawing (including hoppers, supporting steel structure, , stairs and platforms) with design data, nozzles chart and loads on foundation |  | S21001- EN01 - 05HSD - 221011 & S21001- EN01 - 05UVC - 221012(For Structural steel, Galleries, Stairs & Platforms) | RPDU5.MV.003 | S21001- EN01 - 05HSD - 221011 & S21001- EN01 - 05UVC - 221012(For Structural steel, Galleries, Stairs & Platforms) | FA
3.8 | FGD - FGTR Flue Gas Treatment Reactor - Construction Drawings (including hoppers, supporting steel structure, stairs and platforms) |  | S21001- EN01 - 05HSD - 221013 & S21001- EN01 - 05UVC - 221014 (For Structural steel, Galleries, Stairs & Platforms) | RPDU5.MV.004 | S21001- EN01 - 05HSD - 221013 & S21001- EN01 - 05UVC - 221014 (For Structural steel, Galleries, Stairs & Platforms) | FI
3.9 | FGD - MCU & FGTR - Slider Bearings Details |  | S21001- EN01 - 05HSD - 221015 for FGTR S21001- EN01 - 05HTH - 221016 for MCU | RPDU5.MV.501 | S21001- EN01 - 05HSD - 221015 for FGTR S21001- EN01 - 05HTH - 221016 for MCU | FI
3.10 | FGD - MCU & FGTR - Spring Details |  | S21001- EN01 - 05HSD - 221017 for FGTR S21001- EN01 - 05HTH - 221018 for MCU | RPDU5.MV.502 | S21001- EN01 - 05HSD - 221017 for FGTR S21001- EN01 - 05HTH - 221018 for MCU | FI
3.11 | FGD - Wet Stack - Mechanical Calculation according to Indian Standard (latest edition) |  | S21001- EN01 - 05HNE - 221019 | RPDU5.MA.005 | S21001- EN01 - 05HNE - 221019 | FA
3.12 | FGD - Wet Stack - Outline Drawing (including hoppers, supporting steel structure, , stairs and platforms) with design data, nozzles chart and loads |  | S21001- EN01 - 05HNE - 221020 & S21001- EN01 - 05UHN - 221021 (For Structural steel, Galleries, Stairs & Platforms) | RPDU5.MV.005 | S21001- EN01 - 05HNE - 221020 & S21001- EN01 - 05UHN - 221021 (For Structural steel, Galleries, Stairs & Platforms) | FA
3.13 | FGD - Wet Stack - Construction Drawings (including hoppers, supporting steel structure, , stairs and platforms) |  | S21001- EN01 - 05HNE - 221022 & S21001- EN01 - 05UHN - 221023 (For Structural steel, Galleries, Stairs & Platforms) | RPDU5.MV.006 | S21001- EN01 - 05HNE - 221022 & S21001- EN01 - 05UHN - 221023 (For Structural steel, Galleries, Stairs & Platforms) | FI
3.14 | FGD - Process Water Tank - Outline Drawing with design data, nozzles chart and loads |  | S21001- EN01 - 05GNK - 221024 | RPDU5.MV.010 | S21001- EN01 - 05GNK - 221024 | FA
3.15 | FGD - Process Water Tank - Construction Drawings |  | S21001- EN01 - 05GNK - 221025 | RPDU5.MV.011 | S21001- EN01 - 05GNK - 221025 | FI
3.16 | FGD - Waste Recycle Tank - Outline Drawing with design data, nozzles chart and loads |  | S21001- EN01 - 05HSM - 221026 | RPDU5.MV.012 | S21001- EN01 - 05HSM - 221026 | FA
3.17 | FGD - Waste Recycle Tank - Construction Drawings |  | S21001- EN01 - 05HSM - 221029 | RPDU5.MV.013 | S21001- EN01 - 05HSM - 221029 | FI
3.18 | SAC - Equipment Supporting Steel Structures (including stairs and platforms) - Outline Drawings |  | UNDER DEVELOPMENT | RPDU5.MV.301 | UNDER DEVELOPMENT | FA
3.19 | SAC - Equipment Supporting Steel Structures (including stairs and platforms) - Construction Drawings |  | UNDER DEVELOPMENT | RPDU5.MV.302 | UNDER DEVELOPMENT | FI
4 | FGD & SAC - GENERAL ARRANGEMENTS
4.1 | FGD - General Arrangement Drawing (Overall Plot Plan) | S21001-EN01- 05HSD- 221027 | S21001- EN01 - 05HSD - 221027 | RPDU5.ML.000 | S21001- EN01 - 05HSD - 221027 | FA
4.2 | SAC- General Arrangement Drawing (Overall Plot Plan) |  | UNDER DEVELOPMENT | RPDU5.ML.300 | UNDER DEVELOPMENT | FA
4.3 | FGD - General Arrangement Drawings (Plans and Sections) |  | S21001- EN01 - 05HSD - 221028 | RPDU5.ML.001 | S21001- EN01 - 05HSD - 221028 | FA
4.4 | SAC - General Arrangement Drawings (Plans and Sections) |  | UNDER DEVELOPMENT | RPDU5.ML.301 | UNDER DEVELOPMENT | FA
5 | FGD & SAC - BUILDINGS
5.1 | FGD Electrical Buildings - Architectural Outline Drawings (Plans and Sections) |  | S21001- EN01 - 05UCA - 551006 | RPDU5.ML.501 | S21001- EN01 - 05UCA - 551006 | FI
5.2 | FGD Electrical Buildings - HVAC - Technical Specification |  | S21001- TS01 - 05UCA- 337201 | RPDU5.PG.501 | S21001- TS01 - 05UCA- 337201 | FI
5.3 | FGD Electrical Buildings - Lighting - Technical Specification |  | S21001- TS01 - 05UCA- 337202 | RPDU5.PG.502 | S21001- TS01 - 05UCA- 337202 | FI
5.4 | FGD Electrical Buildings - Earthing Material and Lightning Arrestor - Technical Specification |  | S21001- TS01 - 05UCA- 337203 | RPDU5.PG.503 | S21001- TS01 - 05UCA- 337203 | FI
5.5 | SAC Buildings - Architectural Outline Drawings (Plans and Sections) |  | UNDER DEVELOPMENT | RPDU5.ML.551 | UNDER DEVELOPMENT | FI
5.6 | SAC Buildings - HVAC - Technical Specification |  | UNDER DEVELOPMENT | RPDU5.PG.551 | UNDER DEVELOPMENT | FI
5.7 | SAC Buildings - Lighting - Technical Specification |  | UNDER DEVELOPMENT | RPDU5.PG.552 | UNDER DEVELOPMENT | FI
5.8 | SAC Buildings - Earthing Material and Lightning Arrestor - Technical Specification |  | UNDER DEVELOPMENT | RPDU5.PG.553 | UNDER DEVELOPMENT | FI
6 | FGD & SAC - LIFTING EQUIPMENT SPECIFICATIONS
6.1 | FGD - Lifting device for SPC modules maintenance - Technical Specification |  | S21001- TS01 - 05HSD- 227215 | RPDU5.PG.050 | S21001- TS01 - 05HSD- 227215 | FI
6.2 | SAC - Lifting device for SAC equipment maintenance - Technical Specification |  | UNDER DEVELOPMENT | RPDU5.PG.350 | UNDER DEVELOPMENT | FI
7 | FGD - FLUE GAS DUCTS
7.1 | FGD - Flue Gas Duct (including supporting structures, stairs and platforms) - Outline Drawings |  | S21001- EN01 - 05UVZ - 221030 | RPDU5.MU.001 | S21001- EN01 - 05UVZ - 221030 | FA
7.2 | FGD - Flue Gas Duct Supporting Steel Structures (including supporting structures, stairs and platforms) - Construction Drawings |  | S21001- EN01 - 05UVZ- 221031 | RPDU5.MU.002 | S21001- EN01 - 05UVZ- 221031 | FI
8 | FGD & SAC - LININGS, PAINTINGS AND HEAT INSULATIONS
8.1 | FGD - Glass Flake Linings - Technical Specification |  | S21001- TS01 - 05HSD- 227216 | RPDU5.PG.020 | S21001- TS01 - 05HSD- 227216 | FI
8.2 | FGD - Paintings - Technical Specification |  | S21001- TS01 - 05HSD- 227217 | RPDU5.PG.021 | S21001- TS01 - 05HSD- 227217 | FI
8.3 | SAC - Paintings - Technical Specification |  | UNDER DEVELOPMENT | RPDU5.PG.321 | UNDER DEVELOPMENT | FI
8.4 | FGD - Heat Insulations - Technical Specification |  | S21001- TS01 - 05HSD- 227218 | RPDU5.PG.022 | S21001- TS01 - 05HSD- 227218 | FI
8.5 | SAC - Heat Insulations - Technical Specification |  | UNDER DEVELOPMENT | RPDU5.PG.322 | UNDER DEVELOPMENT | FI
9 | FGD & SAC - CIVIL
9.1 | FGD - Civil Materials - Technical Specification |  | S21001- TS01 - 05HSD- 557201 | RPDU5.PA.550 | S21001- TS01 - 05HSD- 557201 | FI
9.2 | SAC - Civil Materials - Technical Specification |  | UNDER DEVELOPMENT / CIVIL MATERIAL MAY BE USED AS COMMON FOR FGD AND SAC, HENCE 9.1 SERVES BOTH | RPDU5.PA.551 | UNDER DEVELOPMENT / CIVIL MATERIAL MAY BE USED AS COMMON FOR FGD AND SAC, HENCE 9.1 SERVES BOTH | FI
9.3 | FGD - Foundation Layout Drawings with equipment loads and embedded part |  | S21001- EN01 - 05HSD - 551001 | RPDU5.MC.001 | S21001- EN01 - 05HSD - 551001 | FA
9.4 | SAC - Foundation Layout Drawings with equipment loads and embedded part |  | UNDER DEVELOPMENT | RPDU5.MC.301 | UNDER DEVELOPMENT | FA
9.5 | FGD - Seismic Calculation Report of the foundations |  | S21001- EN01 - 05CPP - 551002 | RPDU5.MA.001 | S21001- EN01 - 05CPP - 551002 | FA
9.6 | SAC - Seismic Calculation Report of the foundations |  | UNDER DEVELOPMENT | RPDU5.MA.301 | UNDER DEVELOPMENT | FA
9.7 | FGD - Piling Outline Drawing (if piling is required) |  | WILL DEVELOP IF REQUIRED | RPDU5.MC.002 | WILL DEVELOP IF REQUIRED | FA
9.8 | SAC - Piling Outline Drawing (if piling is required) |  | WILL DEVELOP IF REQUIRED | RPDU5.MC.302 | WILL DEVELOP IF REQUIRED | FA
9.9 | FGD - Piling Specification (if piling is required) |  | WILL DEVELOP IF REQUIRED | RPDU5.PG.507 | WILL DEVELOP IF REQUIRED | FA
9.10 | SAC - Piling Specification (if piling is required) |  | WILL DEVELOP IF REQUIRED | RPDU5.PG.508 | WILL DEVELOP IF REQUIRED | FA
9.11 | FGD & SAC - Drainages drawings (funnels, trenches, sumps, etc.) |  | S21001- EN01 - 05CPP - 551005 | RPDU5.MC.501 | S21001- EN01 - 05CPP - 551005 | FI
9.12 | FGD & SAC - Cable trenches - Outline Drawings |  | S21001-EN01-05CPP-XXXXX | RPDU5.MC.502 | S21001-EN01-05CPP-XXXXX | FI
9.13 | FGD & SAC - Excavation and backfillings (with bill of quantitites) |  | S21001- EN01 - 05HSD - 551003 | RPDU5.MC.503 | S21001- EN01 - 05HSD - 551003 | FI
9.14 | FGD - Equipment foundations - Formworks drawings (with bill of quantities) |  | WILL DEVELOP IF REQUIRED | RPDU5.MC.310 | WILL DEVELOP IF REQUIRED | FI
9.15 | SAC - Equipment foundations - Formworks drawings (with bill of quantities) |  | WILL DEVELOP IF REQUIRED | RPDU5.MC.510 | WILL DEVELOP IF REQUIRED | FI
9.16 | FGD - Equipment foundations - Steel bars and reinforcement drawings (with bill of quantities) |  | S21001- EN01 - 05HSD - 551004 | RPDU5.MC.350 | S21001- EN01 - 05HSD - 551004 | FI
9.17 | SAC - Equipment foundations - Formworks drawings (with bill of quantities) - Steel bars and reinforcement drawings (with bill of quantities) |  | WILL DEVELOP IF REQUIRED | RPDU5.MC.550 | WILL DEVELOP IF REQUIRED | FI
21.8 | Booster Fan Foundation - Design Drawings and Calculations |  | S21001-EN01-05HSC-551007 |  | S21001-EN01-05HSC-551007 | FA
21.9 | Geotechnical procedures | RPD-U5-FGD-C-SPC-01 | RPD-U5-FGD-C-SPC-01 | Hindalco Scope of Work | RPD-U5-FGD-C-SPC-01 | FA
21.10 | Geotechnical layout | RPD-U5-BHM-001 | RPD-U5-BHM-001 | Hindalco Scope of Work | RPD-U5-BHM-001 | FA
21.11 | Geotechnical report |  | Hindalco Scope of Work | Hindalco Scope of Work | Hindalco Scope of Work | FA
10 | FGD & SAC - PIPING
10.1 | FGD - Piping Materials Technical Specification |  | S21001- TS01- 05HSD- 227219 SHEET X OF XX | RPDU5.PG.010 | S21001- TS01- 05HSD- 227219 SHEET X OF XX | FI
10.2 | SAC - Piping Materials Specification |  | UNDER DEVELOPMENT | RPDU5.PG.310 | UNDER DEVELOPMENT | FI
10.3 | FGD - Piping Line List |  | S21001- EN01 - 05HSD- 221032 | RPDU5.MM.001 | S21001- EN01 - 05HSD- 221032 | FI
10.4 | SAC - Piping Line List |  | UNDER DEVELOPMENT | RPDU5.MM.301 | UNDER DEVELOPMENT | FI
10.5 | FGD - Piping Layout (Plans and Sections) with pipe support location identification |  | S21001- EN01 - 05HSD- 221033 | RPDU5.ML.010 | S21001- EN01 - 05HSD- 221033 | FI
10.6 | SAC - Piping Layout (Plans and Sections) with pipe support location identification |  | UNDER DEVELOPMENT | RPDU5.ML.310 | UNDER DEVELOPMENT | FI
10.7 | FGD - Pipe Racks and Access Platforms for Maintenance - Drawings with bill of quantities |  | S21001- EN01 - 05HSD- 221034 | RPDU5.MU.010 | S21001- EN01 - 05HSD- 221034 | FI
10.8 | SAC - Pipe Racks and Access Platforms for Maintenance - Drawings with bill of quantitites |  | UNDER DEVELOPMENT | RPDU5.MU.310 | UNDER DEVELOPMENT | FI
10.9 | FGD - Pipe Support - Drawings with bill of quantities |  | S21001- EN01 - 05HSD- 221035 | RPDU5.MU.050 | S21001- EN01 - 05HSD- 221035 | FI
10.10 | SAC - Pipe Support - Drawings with bill of quantities |  | UNDER DEVELOPMENT | RPDU5.MU.350 | UNDER DEVELOPMENT | FI
10.11 | FGD - Piping Isometric Drawings with bill of quantities and support location identification |  | S21001- EN01 - 05HSD- 221036 | RPDU5.MS.010 | S21001- EN01 - 05HSD- 221036 | FI
10.12 | SAC - Piping Isometric Drawings with bill of quantities and support location identification |  | UNDER DEVELOPMENT | RPDU5.MS.310 | UNDER DEVELOPMENT | FI
10.13 | FGD - Piping Painting Technical Specification (primer + final at site) |  | S21001- TS01 - 05HSD- 227220 | RPDU5.PG.011 | S21001- TS01 - 05HSD- 227220 | FI
10.14 | SAC - Piping Painting Specification (primer + final at site) |  | UNDER DEVELOPMENT | RPDU5.PG.311 | UNDER DEVELOPMENT | FI
10.15 | FGD - Piping Heat Insulation Technical Specification |  | S21001- TS01 - 05HSD- 227221 SHEET X OF XX | RPDU5.PG.012 | S21001- TS01 - 05HSD- 227221 SHEET X OF XX | FI
10.16 | SAC - Piping Heat Insulation Specification |  | UNDER DEVELOPMENT | RPDU5.PG.312 | UNDER DEVELOPMENT | FI
10.17 | FGD - Expansion Joint Technical Specification |  | S21001- TS01 - 05HSD- 227251 | RPDU5.PG.013 | S21001- TS01 - 05HSD- 227251 | FI
10.18 | SAC - Expansion Joint Technical Specification |  | UNDER DEVELOPMENT | RPDU5.PG.313 | UNDER DEVELOPMENT | FI
10.19 | SAC - Stress Analysis Calculation of piping steam lines |  | UNDER DEVELOPMENT | RPDU5.MA.302 | UNDER DEVELOPMENT | FI
11 | FGD & SAC - VALVES
11.1 | FGD - Valve List |  | S21001- VS01 - 05HSD- 228400 | RPDU5.MM.002 | S21001- VS01 - 05HSD- 228400 | FI
11.2 | SAC - Valve List |  | UNDER DEVELOPMENT | RPDU5.MM.302 | UNDER DEVELOPMENT | FI
11.3 | FGD - On/Off Valves - Data Sheet |  | S21001- TS01 - 05HSD- 447201 | RPDU5.PG.060 | S21001- TS01 - 05HSD- 447201 | FI
11.4 | SAC - On/Off Valves - Data Sheet |  | UNDER DEVELOPMENT | RPDU5.PG.360 | UNDER DEVELOPMENT | FI
11.5 | FGD - Control Valves - Data Sheet |  | S21001- TS01 - 05HSD- 447202 | RPDU5.PG.061 | S21001- TS01 - 05HSD- 447202 | FI
11.6 | SAC - Control Valves - Data Sheet |  | UNDER DEVELOPMENT | RPDU5.PG.361 | UNDER DEVELOPMENT | FI
12 | FGD & SAC - INSTRUMENTATION AND CONTROL SYSTEM
12.1 | FGD - Operations & Controls Description |  | S21001- EN01 - 05HSD- 441001 | RPDU5.PG.070 | S21001- EN01 - 05HSD- 441001 | FA
12.2 | SAC - Operations & Controls Description |  | UNDER DEVELOPMENT | RPDU5.PG.370 | UNDER DEVELOPMENT | FA
12.3 | FGD - Instrument List |  | S21001- EN01 - 05HSD- 441002 | RPDU5.EM.001 | S21001- EN01 - 05HSD- 441002 | FI
12.4 | SAC - Instrument List |  | UNDER DEVELOPMENT | RPDU5.EM.301 | UNDER DEVELOPMENT | FI
12.5 | FGD - Measurement List |  | S21001- EN01 - 05HSD- 441003 | RPDU5.EM.002 | S21001- EN01 - 05HSD- 441003 | FI
12.6 | SAC - Measurement List |  | UNDER DEVELOPMENT | RPDU5.EM.302 | UNDER DEVELOPMENT | FI
12.7 | FGD - Input/Output List |  | S21001- EN01 - 05HSD- 441004 | RPDU5.EM.003 | S21001- EN01 - 05HSD- 441004 | FA
12.8 | SAC - Input/Output List |  | UNDER DEVELOPMENT | RPDU5.EM.303 | UNDER DEVELOPMENT | FA
12.9 | FGD - Instrument Data Sheet |  | S21001- EN01 - 05HSD- 441005 | RPDU5.ES.001 | S21001- EN01 - 05HSD- 441005 | FA
12.10 | SAC - Instrument Data Sheet |  | UNDER DEVELOPMENT | RPDU5.ES.301 | UNDER DEVELOPMENT | FI
12.11 | FGD - Technical Specification for PLC |  | S21001- TS01 - 05HSD- 447203 | RPDU5.PE.001 | S21001- TS01 - 05HSD- 447203 | FI
12.12 | SAC - Technical Specification for PLC |  | UNDER DEVELOPMENT | RPDU5.PE.301 | UNDER DEVELOPMENT | FI
12.13 | FGD - Loop Diagrams of main process sections |  | S21001- EN01 - 05HSD- 441006 | RPDU5.EL.001 | S21001- EN01 - 05HSD- 441006 | FI
12.14 | SAC - Loop Diagrams of main process sections |  | UNDER DEVELOPMENT | RPDU5.EL.301 | UNDER DEVELOPMENT | FI
12.15 | FGD - Logic Diagrams |  | S21001- EN01 - 05HSD- 441007 | RPDU5.EL.010 | S21001- EN01 - 05HSD- 441007 | FI
12.16 | SAC - Logic Diagrams |  | UNDER DEVELOPMENT | RPDU5.EL.310 | UNDER DEVELOPMENT | FI
12.17 | FGD - Control Architecture Scheme |  | S21001- EN01 - 05HSD- 441008 | RPDU5.EL.050 | S21001- EN01 - 05HSD- 441008 | FA
12.18 | SAC - Control Architecture Scheme |  | UNDER DEVELOPMENT | RPDU5.EL.350 | UNDER DEVELOPMENT | FA
12.19 | FGD - Control Cables Sizing - Technical Specification |  | S21001- TS01 - 05HSD- 447204 | RPDU5.PE.050 | S21001- TS01 - 05HSD- 447204 | FI
12.20 | SAC - Control Cables Sizing - Technical Specification |  | UNDER DEVELOPMENT | RPDU5.PE.350 | UNDER DEVELOPMENT | FI
12.21 | FGD - Hook-Up Diagrams |  | S21001- EN01 - 05HSD- 441009 | RPDU5.EL.051 | S21001- EN01 - 05HSD- 441009 | FI
12.22 | SAC - Hook-Up Diagrams |  | UNDER DEVELOPMENT | RPDU5.EL.351 | UNDER DEVELOPMENT | FI
12.23 | FGD - Control Room Layout Drawing |  | S21001- EN01 - 05UCA- 441010 | RPDU5.EL.052 | S21001- EN01 - 05UCA- 441010 | FA
12.24 | SAC - Control Room Layout Drawing |  | UNDER DEVELOPMENT | RPDU5.EL.352 | UNDER DEVELOPMENT | FA
12.25 | FGD - Instrument Location Plan Drawing |  | S21001- EN01 - 05HSD- 441011 | RPDU5.EL.353 | S21001- EN01 - 05HSD- 441011 | FI
12.26 | SAC - Instrument Location Plan Drawing |  | UNDER DEVELOPMENT | RPDU5.EL.553 | UNDER DEVELOPMENT | FI
12.27 | FGD - Junction Boxes Location Plan Drawing |  | S21001- EN01 - 05HSD- 441012 | RPDU5.EL.054 | S21001- EN01 - 05HSD- 441012 | FI
12.28 | SAC - Junction Boxes Location Plan Drawing |  | UNDER DEVELOPMENT | RPDU5.EL.354 | UNDER DEVELOPMENT | FI
21.6 | Interface with customer equipment, facilities - Instrumentation and control |  | S21001-EE01-05CPP-44001 to 441000 |  | S21001-EE01-05CPP-44001 to 441000 | FA
21.12 | Control System Graphic/Mimic (Design document of GUI Pages) |  | S21001- EN01-05CPP-441013 |  | S21001- EN01-05CPP-441013 | FA
21.13 | FAT Procedure of Control System |  | S21001- EN01-05HSD-441014 |  | S21001- EN01-05HSD-441014 | FI
21.14 | PLC FAT Report |  | S21001- EN01-05HSD-441015 |  | S21001- EN01-05HSD-441015 | FI
21.15 | PLC Power Supply & Grounding Scheme |  | S21001- EN01-05HSD-441016 |  | S21001- EN01-05HSD-441016 | FI
21.23 | Drive Control and Control Interfacing philosophy |  | S21001-EN01-05HSD-441017 |  | S21001-EN01-05HSD-441017 | FI
13 | FGD & SAC - ELECTRICAL SYSTEM
13.1 | FGD - Electrical Load List |  | S21001- EN01 - 05HSD - 331001 | RPDU5.EM.000 | S21001- EN01 - 05HSD - 331001 | FI
13.2 | SAC - Electrical Load List |  | UNDER DEVELOPMENT | RPDU5.EM.300 | UNDER DEVELOPMENT | FI
13.3 | FGD - Electrical & Control Cables List |  | S21001- EN01 - 05HSD - 331002 & S21001- EN01 - 05HSD - 331003 FOR CONTROL CABLES | RPDU5.EM.004 | S21001- EN01 - 05HSD - 331002 & S21001- EN01 - 05HSD - 331003 FOR CONTROL CABLES | FI
13.4 | SAC - Electrical & Control Cables List |  | UNDER DEVELOPMENT | RPDU5.EM.304 | UNDER DEVELOPMENT | FI
13.5 | FGD - Cable Trays / Conduit Layout with bill of quantities |  | S21001- EN01 - 05HSD - 331004 | RPDU5.EV.001 | S21001- EN01 - 05HSD - 331004 | FI
13.6 | SAC - Cable Trays / Conduit Layout with bill of quantities |  | UNDER DEVELOPMENT | RPDU5.EV.301 | UNDER DEVELOPMENT | FI
13.7 | FGD - Junction Boxes - Technical Specification |  | S21001- TS01 - 05HSD- 337204 | RPDU5.ED.001 | S21001- TS01 - 05HSD- 337204 | FI
13.8 | SAC - Junction Boxes - Technical Specification |  | UNDER DEVELOPMENT | RPDU5.ED.301 | UNDER DEVELOPMENT | FI
13.9 | FGD - PMCC, MCC, ACDB , DCDB and Booster Fan VFD Panel - Technical Specification |  | S21001- TS01 - 05HSD- 337205 | RPDU5.ED.002 | S21001- TS01 - 05HSD- 337205 | FI
13.10 | SAC - PMCC, MCC, ACDB and DCDB - Technical Specification |  | UNDER DEVELOPMENT | RPDU5.ED.302 | UNDER DEVELOPMENT | FI
13.11 | FGD - MOV - Technical Specification |  | S21001- TS01 - 05HSD- 337206 | RPDU5.ED.003 | S21001- TS01 - 05HSD- 337206 | FI
13.12 | SAC - MOV - Technical Specification |  | UNDER DEVELOPMENT | RPDU5.ED.303 | UNDER DEVELOPMENT | FI
13.13 | FGD - LT/HT motors - Technical Specification |  | S21001- TS01 - 05HSD- 337207 | RPDU5.ED.004 | S21001- TS01 - 05HSD- 337207 | FI
13.14 | SAC- LT/HT cables - Technical Specification |  | UNDER DEVELOPMENT | RPDU5.ED.304 | UNDER DEVELOPMENT | FI
13.15 | FGD - Electrical Single Line Diagram including Emergency Power Supply Bus from Existing DG set |  | S21001- EN01 - 05HSD - 331005 | RPDU5.EG.001 | S21001- EN01 - 05HSD - 331005 | FA
13.16 | SAC- Electrical Single Line Diagram |  | UNDER DEVELOPMENT | RPDU5.EG.301 | UNDER DEVELOPMENT | FA
13.17 | FGD - Cable Sizing - Technical Specification |  | S21001- TS01 - 05HSD- 337208 | RPDU5.ED.005 | S21001- TS01 - 05HSD- 337208 | FI
13.18 | SAC- Cable Sizing - Technical Specification |  | UNDER DEVELOPMENT | RPDU5.ED.305 | UNDER DEVELOPMENT | FI
13.19 | FGD - Individual Distribution Schemes/Control Schemes Drawing |  | S21001- EN01 - 05HSD - 331006 | RPDU5.EG.002 | S21001- EN01 - 05HSD - 331006 | FI
13.20 | SAC - Individual Distribution Schemes/Control Schemes Drawing |  | UNDER DEVELOPMENT | RPDU5.EG.302 | UNDER DEVELOPMENT | FI
13.21 | FGD - Illumination Scheme Drawing |  | S21001- EN01 - 05HSD - 331007 | RPDU5.EG.003 | S21001- EN01 - 05HSD - 331007 | FI
13.22 | SAC - Illumination Scheme Drawing |  | UNDER DEVELOPMENT | RPDU5.EG.303 | UNDER DEVELOPMENT | FI
13.23 | FGD - Plant lighting Layout Drawing |  | S21001- EN01 - 05HSD - 331008 | RPDU5.EG.004 | S21001- EN01 - 05HSD - 331008 | FI
13.24 | SAC - Plant lighting Layout Drawing |  | UNDER DEVELOPMENT | RPDU5.EG.304 | UNDER DEVELOPMENT | FI
13.25 | FGD - Grounding and Lightening System - Technical Specification |  | S21001-TS01-05HSD-337232 | RPDU5.ED.006 | S21001-TS01-05HSD-337232 | FI
13.26 | SAC - Grounding and Lightening System - Technical Specification |  | UNDER DEVELOPMENT | RPDU5.ED.306 | UNDER DEVELOPMENT | FI
13.27 | FGD - Grounding Scheme Drawing |  | S21001- EN01 - 05HSD - 331009 | RPDU5.EG.006 | S21001- EN01 - 05HSD - 331009 | FA
13.28 | SAC - Grounding Scheme Drawing |  | UNDER DEVELOPMENT | RPDU5.EG.306 | UNDER DEVELOPMENT | FA
13.29 | FGD - Lightening Protection Drawing |  | S21001- EN01 - 05HSD - 331010 | RPDU5.EG.007 | S21001- EN01 - 05HSD - 331010 | FA
13.30 | SAC - Lightening Protection Drawing |  | UNDER DEVELOPMENT | RPDU5.EG.307 | UNDER DEVELOPMENT | FA
13.31 | FGD - Plant Area Grounding and Lightening Protection Layout |  | S21001- EN01 - 05HSD - 331011 | RPDU5.EG.008 | S21001- EN01 - 05HSD - 331011 | FA
13.32 | SAC - Plant Area Grounding and Lightening Protection Layout |  | UNDER DEVELOPMENT | RPDU5.EG.308 | UNDER DEVELOPMENT | FA
13.33 | FGD - Electrical Equipment Layout including Booster Fan VFD Panel |  | S21001- EN01 - 05HSD - 331012 | RPDU5.EG.009 | S21001- EN01 - 05HSD - 331012 | FA
13.34 | SAC - Electrical Equipment Layout |  | UNDER DEVELOPMENT | RPDU5.EG.309 | UNDER DEVELOPMENT | FA
13.35 | FGD - Electrical Room Layout (Plan and Sections) |  | S21001- EN01 - 05HSD - 331013 | RPDU5.EG.010 | S21001- EN01 - 05HSD - 331013 | FA
13.36 | SAC - Electrical Room Layout (Plan and Sections) |  | UNDER DEVELOPMENT | RPDU5.EG.310 | UNDER DEVELOPMENT | FA
13.37 | FGD – Electrical/Control Cables and Glands - Technical Specification |  | S21001- TS01- 05HSD - 337209 | RPDU5.ED.007 | S21001- TS01- 05HSD - 337209 | FI
13.38 | SAC – Electrical/Control Cables and Glands - Technical Specification |  | UNDER DEVELOPMENT | RPDU5.ED.307 | UNDER DEVELOPMENT | FI
13.39 | FGD – Cable Trays - Technical Specification |  | S21001- TS01- 05HSD - 337210 | RPDU5.ED.008 | S21001- TS01- 05HSD - 337210 | FI
13.40 | SAC – Cable Trays - Technical Specification |  | UNDER DEVELOPMENT | RPDU5.ED.308 | UNDER DEVELOPMENT | FI
13.41 | FGD – LT Motors - Technical Specification |  | S21001- TS01- 05HSD - 337211 | RPDU5.ED.009 | S21001- TS01- 05HSD - 337211 | FI
13.42 | SAC – LT Motors - Technical Specification |  | UNDER DEVELOPMENT | RPDU5.ED.309 | UNDER DEVELOPMENT | FI
13.43 | FGD – HT Motors - Technical Specification |  | S21001- TS01- 05HSD - 337212 | RPDU5.ED.010 | S21001- TS01- 05HSD - 337212 | FI
13.44 | SAC – HT Motors - Technical Specification |  | UNDER DEVELOPMENT | RPDU5.ED.310 | UNDER DEVELOPMENT | FI
13.45 | FGD – LT & HT Switchgears - Technical Specification |  | S21001- TS01- 05HSD - 337213 | RPDU5.ED.011 | S21001- TS01- 05HSD - 337213 | FI
13.46 | SAC – LT & HT Switchgears - Technical Specification |  | UNDER DEVELOPMENT | RPDU5.ED.311 | UNDER DEVELOPMENT | FI
13.47 | FGD – Electrical Panels and Junction Boxes - Technical Specification |  | S21001- TS01- 05HSD - 337214 | RPDU5.ED.012 | S21001- TS01- 05HSD - 337214 | FI
13.48 | SAC – Electrical Panels and Junction Boxes - Technical Specification |  | UNDER DEVELOPMENT | RPDU5.ED.312 | UNDER DEVELOPMENT | FI
13.49 | FGD – LTMCC / Switchboard - Technical Specification |  | S21001- TS01- 05HSD - 337215 | RPDU5.ED.013 | S21001- TS01- 05HSD - 337215 | FI
13.50 | SAC – LTMCC / Switchboard - Technical Specification |  | UNDER DEVELOPMENT | RPDU5.ED.313 | UNDER DEVELOPMENT | FI
13.51 | FGD – UPS - Technical Specification |  | S21001- TS01- 05HSD - 337216 | RPDU5.ED.014 | S21001- TS01- 05HSD - 337216 | FI
13.52 | SAC – UPS - Technical Specification |  | UNDER DEVELOPMENT | RPDU5.ED.314 | UNDER DEVELOPMENT | FI
13.53 | FGD – UPS - Line Diagram |  | S21001- EN01 - 05HSD - 331014 | RPDU5.EG.011 | S21001- EN01 - 05HSD - 331014 | FA
13.54 | SAC – UPS - Line Diagram |  | UNDER DEVELOPMENT | RPDU5.EG.311 | UNDER DEVELOPMENT | FA
13.55 | FGD & SAC - Auxiliary power calculation for continuous running of FGD plant including SAC at full load. |  | S21001- EN01 - 05CPP - 331015 | RPDU5.ED.500 | S21001- EN01 - 05CPP - 331015 | FA
21.7 | Interface with customer equipment, facilities - Electrical |  | S21001-EE01-05CPP-33001 to 331000 |  | S21001-EE01-05CPP-33001 to 331000 | FA
21.16 | Design calculation for power, control, instrument and any special cables |  | S21001-EN01-05HSD-331016 |  | S21001-EN01-05HSD-331016 | FI
21.17 | Design calculation for LT bus duct |  | S21001-EN01-05HSD-331017 |  | S21001-EN01-05HSD-331017 | FI
21.18 | Design calculation for lighting system |  | S21001-EN01-05HSD-331018 |  | S21001-EN01-05HSD-331018 | FI
21.19 | Design calculation for lightening protection system |  | S21001-EN01-05HSD-331019 |  | S21001-EN01-05HSD-331019 | FI
21.20 | Design calculation for earthing system |  | S21001-EN01-05HSD-331020 |  | S21001-EN01-05HSD-331020 | FI
21.21 | Schematic and wiring diagrams for medium voltage system |  | S21001-EN01-05HSD-331021 |  | S21001-EN01-05HSD-331021 | FI
21.22 | Schematic and wiring diagrams for low voltage system |  | S21001-EN01-05HSD-331022 |  | S21001-EN01-05HSD-331022 | FI
21.24 | List of electrical equipment and materials (Bill of materials) |  | S21001-EN01-05HSD-331023 |  | S21001-EN01-05HSD-331023 | FI
14 | FGD & SAC - FIRE FIGHTING SYSTEM
14.1 | FGD Fire Fighting - Fire Fighting & Detection System Technical Specification |  | S21001- TS01- 05SGA - 772001 | RPDU5.ED.800 | S21001- TS01- 05SGA - 772001 | FI
14.2 | SAC Fire Fighting - Fire Fighting & Detection System Technical Specification |  | UNDER DEVELOPMENT | RPDU5.ED.830 | UNDER DEVELOPMENT | FI
14.2 | FGD Fire Fighting - Hydrant and Water Spray System - Schematic Diagram |  | S21001- EN01- 05SGA - 771001 | RPDU5.EL.800 | S21001- EN01- 05SGA - 771001 | FA
14.3 | SAC Fire Fighting - Alarm System - Schematic Diagram |  | UNDER DEVELOPMENT | RPDU5.EL.830 | UNDER DEVELOPMENT | FA
14.4 | FGD Fire Fighting - Hydrant and Water Spray System - Layout Drawing |  | S21001- EN01- 05SGA - 771002 | RPDU5.ML.800 | S21001- EN01- 05SGA - 771002 | FA
14.4 | SAC Fire Fighting - Hydrant and Water Spray System - Layout Drawing |  | UNDER DEVELOPMENT | RPDU5.ML.830 | UNDER DEVELOPMENT | FA
14.5 | FGD Fire Fighting - Hydrant System - Hydraulic Calculation |  | S21001- EN01- 05SGA - 771003 | RPDU5.MA.800 | S21001- EN01- 05SGA - 771003 | FI
14.5 | SAC Fire Fighting - Hydrant System - Hydraulic Calculation |  | UNDER DEVELOPMENT | RPDU5.MA.830 | UNDER DEVELOPMENT | FI
14.6 | FGD Fire Fighting - Water Spray System - Hydraulic Calculation |  | S21001- EN01- 05SGA - 771004 | RPDU5.MA.801 | S21001- EN01- 05SGA - 771004 | FI
14.6 | SAC Fire Fighting - Water Spray System - Hydraulic Calculation |  | UNDER DEVELOPMENT | RPDU5.MA.831 | UNDER DEVELOPMENT | FI
14.7 | FGD Fire Fighting - Component Data Sheet |  | S21001- EN01- 05SGA - 771005 | RPDU5.PA.800 | S21001- EN01- 05SGA - 771005 | FA
14.7 | SAC Fire Fighting - Component Data Sheet |  | UNDER DEVELOPMENT | RPDU5.PA.830 | UNDER DEVELOPMENT | FA
14.8 | FGD Fire Fighting - Alarm System at MCC and Control Room - General Arrangement Drawing |  | S21001- EN01- 05SGA - 771006 | RPDU5.ML.801 | S21001- EN01- 05SGA - 771006 | FA
14.9 | SAC Fire Fighting - Alarm System at MCC and Control Room - General Arrangement Drawing |  | UNDER DEVELOPMENT | RPDU5.ML.831 | UNDER DEVELOPMENT | FA
14.10 | FGD Fire Fighting - Fire Detection Alarm System - Data Sheet |  | S21001- EN01- 05SGA - 771007 | RPDU5.PA.801 | S21001- EN01- 05SGA - 771007 | FA
14.11 | SAC Fire Fighting - Fire Detection Alarm System - Data Sheet |  | UNDER DEVELOPMENT | RPDU5.PA.831 | UNDER DEVELOPMENT | FA
14.12 | FGD Fire Fighting - Fire Detection Alarm System - Layout |  | S21001- EN01- 05SGA - 771008 | RPDU5.ML.802 | S21001- EN01- 05SGA - 771008 | FA
14.13 | SAC Fire Fighting - Fire Detection Alarm System - Layout |  | UNDER DEVELOPMENT | RPDU5.ML.832 | UNDER DEVELOPMENT | FA
14.14 | FGD Fire Fighting - Fire Detection Alarm System - Schematic Drawing |  | S21001- EN01- 05SGA - 771009 | RPDU5.ML.803 | S21001- EN01- 05SGA - 771009 | FI
14.15 | SAC Fire Fighting - Fire Detection Alarm System - Schematic Drawing |  | UNDER DEVELOPMENT | RPDU5.ML.833 | UNDER DEVELOPMENT | FI
14.16 | FGD Fire Fighting - Fire Detection Alarm Equipment - Technical Specification |  | S21001-TS01- 05SGA- 772002 SHEET X OF XX | RPDU5.PA.802 | S21001-TS01- 05SGA- 772002 SHEET X OF XX | FI
14.17 | SAC Fire Fighting - Fire Detection Alarm Equipment - Technical Specification |  | UNDER DEVELOPMENT | RPDU5.PA.832 | UNDER DEVELOPMENT | FI
14.18 | FGD Fire Fighting - Fire Extinguishers - Technical Specification |  | S21001- TS01- 05SGA- 772003 SHEET X OF XX | RPDU5.PA.803 | S21001- TS01- 05SGA- 772003 SHEET X OF XX | FI
14.19 | SAC Fire Fighting - Fire Extinguishers - Technical Specification |  | UNDER DEVELOPMENT | RPDU5.PA.833 | UNDER DEVELOPMENT | FI
14.20 | FGD Fire Fighting - ERW steel pipes and fittings - Technical Specification |  | S21001- TS01- 05SGA- 772004 SHEET X OF XX | RPDU5.PA.804 | S21001- TS01- 05SGA- 772004 SHEET X OF XX | FI
14.21 | SAC Fire Fighting - ERW steel pipes and fittings - Technical Specification |  | UNDER DEVELOPMENT | RPDU5.PA.834 | UNDER DEVELOPMENT | FI
14.22 | FGD Fire Fighting - Pumps - Technical Specification |  | S21001- TS01- 05SGA- 772005 SHEET X OF XX | RPDU5.PA.805 | S21001- TS01- 05SGA- 772005 SHEET X OF XX | FI
14.23 | SAC Fire Fighting - Pumps - Technical Specification |  | UNDER DEVELOPMENT | RPDU5.PA.835 | UNDER DEVELOPMENT | FI
14.24 | FGD Fire Fighting - Sprinklers - Technical Specification |  | S21001- TS01- 05SGA- 772006 SHEET X OF XX | RPDU5.PA.806 | S21001- TS01- 05SGA- 772006 SHEET X OF XX | FI
14.25 | SAC Fire Fighting - Sprinklers - Technical Specification |  | UNDER DEVELOPMENT | RPDU5.PA.836 | UNDER DEVELOPMENT | FI
15 | FGD & SAC - PURCHASING TECHNICAL SPECIFICATIONS
15.1 | FGD - Booster Fan along with VFD sysytem - PTS Purchasing Technical Specification |  | S21001- TS01 - 05HSC- 227222 | RPDU5.PA.001 | S21001- TS01 - 05HSC- 227222 | FI
15.2 | FGD - Flue Gas Duct Expansion Joints - PTS Purchasing Technical Specification (Duplicate) |  | S21001- TS01 - 05HTA- 227223 | RPDU5.PA.002 | S21001- TS01 - 05HTA- 227223 | FI
15.3 | FGD - Flue Gas Duct Dampers - PTS Purchasing Technical Specification |  | S21001- TS01 - 05HTA- 227223 | RPDU5.PA.003 | S21001- TS01 - 05HTA- 227223 | FI
15.4 | FGD - Pumps - PTS Purchasing Technical Specification |  | S21001- TS01 - 05PBL- 227224 (FOR BACKWASH & DEMISTER) S21001- TS01 - 05PBL- 227225 (FOR FRESH WATER & MAKE UP WATER) S21001- TS01 - 05GNK- 227226 (FOR HCP) S21001- TS01 - 05HSM- 227227 (FOR WRP) S21001- TS01 - 05GNK- 227228 (FOR PWP) S21001- TS01 - 05HSM- 227229 (FOR WWTP) S21001- TS01 - 05GNK- 227230 (FOR PRP) S21001- TS01 - 05HSM- 227231 (FOR ATP) S21001- TS01 - 05HSM- 227232 (FOR RWRP) S21001- TS01 - 05XXX- 227233 (FOR ALP) | RPDU5.PA.005 | S21001- TS01 - 05PBL- 227224 (FOR BACKWASH & DEMISTER) S21001- TS01 - 05PBL- 227225 (FOR FRESH WATER & MAKE UP WATER) S21001- TS01 - 05GNK- 227226 (FOR HCP) S21001- TS01 - 05HSM- 227227 (FOR WRP) S21001- TS01 - 05GNK- 227228 (FOR PWP) S21001- TS01 - 05HSM- 227229 (FOR WWTP) S21001- TS01 - 05GNK- 227230 (FOR PRP) S21001- TS01 - 05HSM- 227231 (FOR ATP) S21001- TS01 - 05HSM- 227232 (FOR RWRP) S21001- TS01 - 05XXX- 227233 (FOR ALP) | FI
15.5 | SAC - Pumps - PTS Purchasing Technical Specification |  | S21001- TS01 - 05GNE- 997201 | RPDU5.PA.305 | S21001- TS01 - 05GNE- 997201 | FI
15.6 | FGD - Ash Filters - PTS Purchasing Technical Specification |  | S21001- TS01 - 05HSM- 227234 (WRPFS) S21001- TS01 - 05HSM- 227235 (WWTPFS) | RPDU5.PA.006 | S21001- TS01 - 05HSM- 227234 (WRPFS) S21001- TS01 - 05HSM- 227235 (WWTPFS) | FI
15.7 | FGD - MCU Flue Gas Cooling Nozzles and FGTR Washing Nozzles of SPC Modules - PTS Purchasing Technical Specification | MCU-S21001-TS01- 05HTH- 227243 | FGTR-S21001- TS01 - 05HTD- 227236 MCU-S21001-TS01- 05HTH- 227243 | RPDU5.PA.007 | FGTR-S21001- TS01 - 05HTD- 227236 MCU-S21001-TS01- 05HTH- 227243 | FI
15.8 | SCA - Vapour-Liquid Separator, Reboiler Heater Exchanger, Acid Condenser, Circulation Pumps and Vacuum System - PTS Purchasing Technical Specification |  | UNDER DEVELOPMENT | RPDU5.PA.301 | UNDER DEVELOPMENT | FI
15.9 | FGD - MCU Mist Cooling Unit, FGTR Flue Gas Treatment Unit and Wet Stack - PTS Purchasing Technical Specification |  | S21001- TS01 - 05HSF- 227238 | RPDU5.PA.008 | S21001- TS01 - 05HSF- 227238 | FI
15.10 | FGD - Steel Tanks - PTS Purchasing Technical Specification |  | S21001- TS01 - 05PBL- 227239 (FRESH WATER) S21001- TS01 - 05PBL- 227240 (PROCESS WATER) S21001- TS01 - 05HSM- 227241(WASTE WATER TANK) S21001- TS01 - 05HSM- 227242 (RECOVERED WATER RETURN TANK) S21001- TS01 - 05XXX- 227237 (CONCENTRATED ACID TANK) | RPDU5.PA.010 | S21001- TS01 - 05PBL- 227239 (FRESH WATER) S21001- TS01 - 05PBL- 227240 (PROCESS WATER) S21001- TS01 - 05HSM- 227241(WASTE WATER TANK) S21001- TS01 - 05HSM- 227242 (RECOVERED WATER RETURN TANK) S21001- TS01 - 05XXX- 227237 (CONCENTRATED ACID TANK) | FI
15.11 | SAC - Steel Tanks - PTS Purchasing Technical Specification |  | UNDER DEVELOPMENT | RPDU5.PA.310 | UNDER DEVELOPMENT | FI
15.12 | FGD - FRP Tanks - PTS Purchasing Technical Specification |  | S21001- TS01 - 05HSD- 227244 | RPDU5.PA.011 | S21001- TS01 - 05HSD- 227244 | FI
15.13 | SAC - FRP Tanks - PTS Purchasing Technical Specification |  | UNDER DEVELOPMENT | RPDU5.PA.311 | UNDER DEVELOPMENT | FI
15.14 | FGD Electrical Buildings - HVAC - PTS Purchasing Technical Specification |  | S21001- TS01 - 05UCA- 337223 | RPDU5.PA.012 | S21001- TS01 - 05UCA- 337223 | FI
15.15 | SAC Buildings - HVAC - PTS Purchasing Technical Specification |  | UNDER DEVELOPMENT | RPDU5.PA.312 | UNDER DEVELOPMENT | FI
15.16 | FGD Electrical Buildings - Lighting - PTS Purchasing Technical Specification |  | S21001- TS01 - 05UCA- 337224 | RPDU5.PA.013 | S21001- TS01 - 05UCA- 337224 | FI
15.17 | SAC Buildings - Lighting - PTS Purchasing Technical Specification |  | UNDER DEVELOPMENT | RPDU5.PA.313 | UNDER DEVELOPMENT | FI
15.18 | FGD Electrical Buildings - Earthing Material and Lightning Arrestor - PTS Purchasing Technical Specification |  | S21001- TS01 - 05UCA- 337225 | RPDU5.PA.014 | S21001- TS01 - 05UCA- 337225 | FI
15.19 | SAC Buildings - Earthing Material and Lightning Arrestor - PTS Purchasing Technical Specification |  | UNDER DEVELOPMENT | RPDU5.PA.314 | UNDER DEVELOPMENT | FI
15.20 | FGD - Lifting devices - PTS Purchasing Technical Specification |  | S21001- TS01 - 05HSD- 227245 | RPDU5.PA.015 | S21001- TS01 - 05HSD- 227245 | FI
15.21 | SAC - Lifting devices - PTS Purchasing Technical Specification |  | UNDER DEVELOPMENT | RPDU5.PA.315 | UNDER DEVELOPMENT | FI
15.22 | FGD - Flue Gas Duct (including supporting structures, stairs and platforms) - PTS Purchasing Technical Specification |  | S21001- TS01 - 05UVZ- 227246 | RPDU5.PA.009 | S21001- TS01 - 05UVZ- 227246 | FI
15.23 | FGD - Linings - PTS Purchasing Technical Specification |  | S21001-TS01-05HSD-22 | RPDU5.PA.015 | S21001-TS01-05HSD-22 | FI
15.24 | SAC - Linings - PTS Purchasing Technical Specification |  | UNDER DEVELOPMENT | RPDU5.PA.315 | UNDER DEVELOPMENT | FI
15.25 | FGD - Paintings - PTS Purchasing Technical Specification |  | S21001- TS01 - 05HSD- 227247 | RPDU5.PA.016 | S21001- TS01 - 05HSD- 227247 | FI
15.26 | SAC - Paintings - PTS Purchasing Technical Specification |  | UNDER DEVELOPMENT | RPDU5.PA.316 | UNDER DEVELOPMENT | FI
15.27 | FGD - Heat Insulations - PTS Purchasing Technical Specification |  | S21001- TS01- 05HSD- 227248 | RPDU5.PA.017 | S21001- TS01- 05HSD- 227248 | FI
15.28 | SAC - Heat Insulations - PTS Purchasing Technical Specification |  | UNDER DEVELOPMENT | RPDU5.PA.317 | UNDER DEVELOPMENT | FI
15.29 | FGD - Piping - PTS Purchasing Technical Specification |  | S21001- TS01- 05HSD- 227249 | RPDU5.PA.018 | S21001- TS01- 05HSD- 227249 | FI
15.30 | SAC - Piping - PTS Purchasing Technical Specification |  | UNDER DEVELOPMENT | RPDU5.PA.318 | UNDER DEVELOPMENT | FI
15.31 | FGD - Piping Support - PTS Purchasing Technical Specification |  | S21001- TS01- 05HSD- 227250 | RPDU5.PA.019 | S21001- TS01- 05HSD- 227250 | FI
15.32 | SAC - Piping Support - PTS Purchasing Technical Specification |  | UNDER DEVELOPMENT | RPDU5.PA.319 | UNDER DEVELOPMENT | FI
15.33 | FGD - Control System - PTS Purchasing Technical Specification |  | S21001- TS01- 05HSD- 337226 | RPDU5.PA.020 | S21001- TS01- 05HSD- 337226 | FI
15.34 | SAC - Control System - PTS Purchasing Technical Specification |  | UNDER DEVELOPMENT | RPDU5.PA.320 | UNDER DEVELOPMENT | FI
15.35 | FGD - Instrumentation - PTS Purchasing Technical Specification |  | S21001- TS01- 05HSD-337227 | RPDU5.PA.021 | S21001- TS01- 05HSD-337227 | FI
15.36 | SAC - Instrumentation - PTS Purchasing Technical Specification |  | UNDER DEVELOPMENT | RPDU5.PA.321 | UNDER DEVELOPMENT | FI
15.37 | FGD - Electrical & Control Cables - PTS Purchasing Technical Specification |  | S21001- TS01- 05HSD- 337228 (POWERCABLES) S21001- TS01- 05HSD- 447205 (CONTROL CABLES) | RPDU5.PA.022 | S21001- TS01- 05HSD- 337228 (POWERCABLES) S21001- TS01- 05HSD- 447205 (CONTROL CABLES) | FI
15.38 | SAC - Electrical & Control Cables - PTS Purchasing Technical Specification |  | UNDER DEVELOPMENT | RPDU5.PA.322 | UNDER DEVELOPMENT | FI
15.39 | FGD - Cable Trays and Conduit - PTS Purchasing Technical Specification |  | S21001- TS01- 05HSD- 337229 (TRAYS) S21001- TS01- 05HSD- 337230 (CONDUITS) | RPDU5.PA.023 | S21001- TS01- 05HSD- 337229 (TRAYS) S21001- TS01- 05HSD- 337230 (CONDUITS) | FI
15.40 | SAC - Cable Trays and Conduit - PTS Purchasing Technical Specification |  | UNDER DEVELOPMENT | RPDU5.PA.323 | UNDER DEVELOPMENT | FI
15.41 | FGD - Switchboard, Distribution and Utilities Boards - PTS Purchasing Technical Specification |  | S21001- TS01- 05HSD- 337231 | RPDU5.PA.024 | S21001- TS01- 05HSD- 337231 | FI
15.42 | SAC - Switchboard, Distribution and Utilities Boards - PTS Purchasing Technical Specification |  | UNDER DEVELOPMENT | RPDU5.PA.324 | UNDER DEVELOPMENT | FI
15.43 | FGD - Illumination/Lighting (Outside and inside) - PTS Purchasing Technical Specification |  | WILL DEVELOP IF REQUIRED | RPDU5.PA.025 | WILL DEVELOP IF REQUIRED | FI
15.44 | SAC - Illumination/Lighting (Outide and inside) - PTS Purchasing Technical Specification |  | WILL DEVELOP IF REQUIRED | RPDU5.PA.325 | WILL DEVELOP IF REQUIRED | FI
15.45 | FGD - Earthing Material and Lightning System - PTS Purchasing Technical Specification |  | WILL DEVELOP IF REQUIRED | RPDU5.PA.026 | WILL DEVELOP IF REQUIRED | FI
15.46 | SAC - Earthing Material and Lightning System - PTS Purchasing Technical Specification |  | WILL DEVELOP IF REQUIRED | RPDU5.PA.326 | WILL DEVELOP IF REQUIRED | FI
15.47 | FGD - Fire Fighting System - PTS Purchasing Technical Specification (if any) |  | S21001- TS01- 05SGA- 772007 | RPDU5.PA.027 | S21001- TS01- 05SGA- 772007 | FI
15.48 | SAC - Fire Fighting System - PTS Purchasing Technical Specification (if any) |  | WILL DEVELOP IF REQUIRED | RPDU5.PA.327 | WILL DEVELOP IF REQUIRED | FI
15.49 | FGD & SAC - Foundations Piling Works - PTS Purchasing Technical Specification (if piling is required) (No pilling work) |  | WILL DEVELOP IF REQUIRED | RPDU5.PA.500 | WILL DEVELOP IF REQUIRED | FI
15.50 | FGD & SAC - Civil Works Procedure - PTS Purchasing Technical Specification |  | S21001- TS01- 05CPP- 555001 | RPDU5.PA.501 | S21001- TS01- 05CPP- 555001 | FI
15.51 | FGD & SAC - Mechanical Erection Works Procedure - PTS Purchasing Technical Specification |  | S21001- PS01- 05CPP- 225001 | RPDU5.PA.502 | S21001- PS01- 05CPP- 225001 | FI
15.52 | FGD & SAC - Electrical, Instrumentation and Control Installation Works Procedure- PTS Purchasing Technical Specification |  | S21001- PS01- 05CPP- 335001 | RPDU5.PA.503 | S21001- PS01- 05CPP- 335001 | FI
16 | FGD & SAC - QUALITY ASSURANCE
16.1 | FGD & SAC - Project Quality Control Manual (with Job Organization Chart) | S21001- QA01- 05CPP- 662001 | S21001- QA01- 05CPP- 662001 | RPDU5.QB.501 | S21001- QA01- 05CPP- 662001 | FI
16.2 | FGD & SAC - Quality Control Plan | S21001- QA01- 05CPP- 662002 | S21001- QA01- 05CPP- 662002 | RPDU5.QB.502 | S21001- QA01- 05CPP- 662002 | FI
16.3 | FGD & SAC - Overall Inspection and Test Plan |  | S21001- QA01- 05CPP- 662003 | RPDU5.QF.500 | S21001- QA01- 05CPP- 662003 | FA
16.4 | FGD & SAC - Final Quality Dossier |  | S21001- QA01- 05CPP- 662004 | RPDU5.QB.550 | S21001- QA01- 05CPP- 662004 | FI
16.5 | FGD & SAC - HAZOP study and ARM analysis (Availability, Reliability & Maintainability) |  | S21001- QA01- 05CPP- 662005 | RPDU5.QB.505 | S21001- QA01- 05CPP- 662005 | FI
17 | FGD & SAC - QUALITY CONTROL FOR FABRICATION
17.1 | FGD & SAC - ITP Inspection and Test Plans for Fabrication |  | S21001- IT01- 05CPP- 664001 | RPDU5.QB.503 | S21001- IT01- 05CPP- 664001 | FI
17.2 | FGD & SAC - Ball Valves - ITP Inspection and Test Plan for Fabrication |  | S21001- IT01- 05CPP- 664002 | RPDU5.QF.501 | S21001- IT01- 05CPP- 664002 | FI
17.3 | FGD & SAC - Butterfly Valves - ITP Inspection and Test Plan for Fabrication |  | S21001- IT01- 05CPP- 664003 | RPDU5.QF.502 | S21001- IT01- 05CPP- 664003 | FI
17.4 | FGD & SAC - Check Valves - ITP Inspection and Test Plan for Fabrication |  | S21001- IT01- 05CPP- 664004 | RPDU5.QF.503 | S21001- IT01- 05CPP- 664004 | FI
17.5 | FGD & SAC - Fiberglass Piping Prefabricated - ITP Inspection and Test Plan for Fabrication |  | S21001- IT01- 05CPP- 664005 | RPDU5.QF.504 | S21001- IT01- 05CPP- 664005 | FI
17.6 | FGD & SAC - Piping Expansion Joint - ITP Inspection and Test Plan for Fabrication |  | S21001- IT01- 05CPP- 664006 | RPDU5.QF.505 | S21001- IT01- 05CPP- 664006 | FI
17.7 | FGD & SAC - Carbon Steel Tanks - ITP Inspection and Test Plan for Fabrication |  | S21001- IT01- 05CPP- 664007 | RPDU5.QF.506 | S21001- IT01- 05CPP- 664007 | FI
17.8 | FGD & SAC - Pressure Vessels - ITP Inspection and Test Plan for Fabrication (No Pressure Vessels) |  | WILL DEVELOP IF REQUIRED | RPDU5.QF.507 | WILL DEVELOP IF REQUIRED | FI
17.9 | FGD & SAC - Fiberglass Tanks - ITP Inspection and Test Plan for Fabrication |  | S21001- IT01- 05CPP- 664008 | RPDU5.QF.508 | S21001- IT01- 05CPP- 664008 | FI
17.10 | FGD & SAC - Spray Nozzles - ITP Inspection and Test Plan for Fabrication |  | S21001- IT01- 05CPP- 664009 | RPDU5.QF.509 | S21001- IT01- 05CPP- 664009 | FI
17.11 | FGD & SAC - Booster Fan - ITP Inspection and Test Plan for Fabrication |  | S21001- IT01- 05CPP- 664010 | RPDU5.QF.510 | S21001- IT01- 05CPP- 664010 | FI
17.12 | FGD & SAC - Blowers - ITP Inspection and Test Plan for Fabrication |  | S21001- IT01- 05CPP- 664011 | RPDU5.QF.511 | S21001- IT01- 05CPP- 664011 | FI
17.13 | FGD & SAC - Fans - ITP Inspection and Test Plan for Fabrication |  | S21001- IT01- 05CPP- 664012 | RPDU5.QF.512 | S21001- IT01- 05CPP- 664012 | FI
17.14 | FGD & SAC - Centrifugal Pumps - ITP Inspection and Test Plan for Fabrication |  | S21001- IT01- 05CPP- 664013 | RPDU5.QF.513 | S21001- IT01- 05CPP- 664013 | FI
17.15 | SAC - Evaporators - ITP Inspection and Test Plan for Fabrication |  | S21001- IT01- 05CPP- 664014 | RPDU5.QF.514 | S21001- IT01- 05CPP- 664014 | FI
17.16 | SAC - Heat Exchangers - ITP Inspection and Test Plan for Fabrication |  | S21001- IT01- 05CPP- 664015 | RPDU5.QF.515 | S21001- IT01- 05CPP- 664015 | FI
17.17 | FGD & SAC - Carbon Steel Plates Painted - ITP Inspection and Test Plan for Fabrication |  | S21001- IT01- 05CPP- 664016 | RPDU5.QF.516 | S21001- IT01- 05CPP- 664016 | FI
17.18 | FGD & SAC - Alloy Steel Plates - ITP Inspection and Test Plan for Fabrication |  | S21001- IT01- 05CPP- 664017 | RPDU5.QF.517 | S21001- IT01- 05CPP- 664017 | FI
17.19 | FGD & SAC - Main Steel Structures - ITP Inspection and Test Plan for Fabrication |  | S21001- IT01- 05CPP- 664018 | RPDU5.QF.518 | S21001- IT01- 05CPP- 664018 | FI
17.20 | FGD & SAC - Flue Gas Duct - ITP Inspection and Test Plan for Fabrication |  | S21001- IT01- 05CPP- 664019 | RPDU5.QF.519 | S21001- IT01- 05CPP- 664019 | FI
17.21 | FGD & SAC - Flue Gas Dampers - ITP Inspection and Test Plan for Fabrication |  | S21001- IT01- 05CPP- 664020 | RPDU5.QF.520 | S21001- IT01- 05CPP- 664020 | FI
17.22 | FGD & SAC - Instrumentation - ITP Inspection and Test Plan for Fabrication |  | S21001- IT01- 05CPP- 664021 | RPDU5.QF.521 | S21001- IT01- 05CPP- 664021 | FI
17.23 | FGD & SAC - Analytical Instrument - ITP Inspection and Test Plan for Fabrication |  | S21001- IT01- 05CPP- 664022 | RPDU5.QF.522 | S21001- IT01- 05CPP- 664022 | FI
17.24 | FGD & SAC - Instrument Frames - ITP Inspection and Test Plan for Fabrication |  | S21001- IT01- 05CPP- 664023 | RPDU5.QF.523 | S21001- IT01- 05CPP- 664023 | FI
17.25 | FGD & SAC - Cables - ITP Inspection and Test Plan for Fabrication |  | S21001- IT01- 05CPP- 664024 | RPDU5.QF.524 | S21001- IT01- 05CPP- 664024 | FI
17.26 | FGD & SAC - PLC Local Control Panels - ITP Inspection and Test Plan for Fabrication |  | S21001- IT01- 05CPP- 664025 | RPDU5.QF.525 | S21001- IT01- 05CPP- 664025 | FI
17.27 | FGD -Ash Filters-ITP Inspection and Test Plan for Fabrication |  | S21001- IT01- 05CPP- 664045 |  | S21001- IT01- 05CPP- 664045 | FI
18 | FGD & SAC - QUALITY CONTROL FOR ERECTION AND CIVIL WORKS
18.1 | FGD & SAC - ITP Inspection and Test Plans for Civil & Erection Works |  | S21001- IT01- 05CPP- 664026 | RPDU5.QB.504 | S21001- IT01- 05CPP- 664026 | FI
18.2 | FGD & SAC - Booster Fan - ITP Inspection and Test Plan for Erection Works |  | S21001- IT01- 05CPP- 664027 | RPDU5.QM.501 | S21001- IT01- 05CPP- 664027 | FI
18.3 | FGD & SAC - Flue Gas Duct - ITP Inspection and Test Plan for Erection Works |  | S21001- IT01- 05CPP- 664028 | RPDU5.QM.502 | S21001- IT01- 05CPP- 664028 | FI
18.4 | FGD & SAC - Equipment Mechanical - ITP Inspection and Test Plan for Erection Works |  | S21001- IT01- 05CPP- 664029 | RPDU5.QM.503 | S21001- IT01- 05CPP- 664029 | FI
18.6 | FGD & SAC - Electrical Equipment - ITP Inspection and Test Plan for Erection Works |  | S21001- IT01- 05CPP- 664030 | RPDU5.QM.504 | S21001- IT01- 05CPP- 664030 | FI
18.7 | FGD & SAC - Instrumentation - ITP Inspection and Test Plan for Erection Works |  | S21001- IT01- 05CPP- 664031 | RPDU5.QM.505 | S21001- IT01- 05CPP- 664031 | FI
18.8 | FGD & SAC - Piping - ITP Inspection and Test Plan for Erection Works |  | S21001- IT01- 05CPP- 664032 | RPDU5.QM.506 | S21001- IT01- 05CPP- 664032 | FI
18.9 | FGD & SAC - Cables - ITP Inspection and Test Plan for Erection Works |  | S21001- IT01- 05CPP- 664033 | RPDU5.QM.507 | S21001- IT01- 05CPP- 664033 | FI
18.10 | FGD & SAC - Insulation - ITP Inspection and Test Plan for Erection Works |  | S21001- IT01- 05CPP- 664034 | RPDU5.QM.508 | S21001- IT01- 05CPP- 664034 | FI
18.11 | FGD & SAC - Mist Cooling Unit (MCU) - ITP Inspection and Test Plan for Erection Works |  | S21001- IT01- 05CPP- 664035 | RPDU5.QM.509 | S21001- IT01- 05CPP- 664035 | FI
18.11 | FGD & SAC - Flue Gas Treatment Reactor (FGTR) - ITP Inspection and Test Plan for Erection Works |  | S21001- IT01- 05CPP- 664036 | RPDU5.QM.510 | S21001- IT01- 05CPP- 664036 | FI
18.12 | FGD & SAC - Tanks - ITP Inspection and Test Plan for Erection Works |  | S21001- IT01- 05CPP- 664037 | RPDU5.QM.511 | S21001- IT01- 05CPP- 664037 | FI
18.13 | FGD & SAC - Site Painting - ITP Inspection and Test Plan for Erection Works |  | S21001- IT01- 05CPP- 664038 | RPDU5.QM.512 | S21001- IT01- 05CPP- 664038 | FI
18.14 | FGD & SAC - Glass Flake Lining - ITP Inspection and Test Plan for Erection Works |  | S21001- IT01- 05CPP- 664039 | RPDU5.QM.513 | S21001- IT01- 05CPP- 664039 | FI
18.15 | FGD & SAC - Concrete Works - ITP Inspection and Test Plan for Civil Works |  | S21001- IT01- 05CPP- 664040 | RPDU5.QM.514 | S21001- IT01- 05CPP- 664040 | FI
18.26 | FGD & SAC - System Deluge-Sprinkler - ITP Inspection and Test Plan for Civil Works |  | S21001- IT01- 05CPP- 664041 | RPDU5.QM.515 | S21001- IT01- 05CPP- 664041 | FI
18.28 | SAC - Earthing Lighting Protection System Installation - ITP Inspection and Test Plan for Civil Works |  | S21001- IT01- 05CPP- 664042 | RPDU5.QM.516 | S21001- IT01- 05CPP- 664042 | FI
18.28 | SAC - Roof and Cladding - ITP Inspection and Test Plan for Civil Works |  | S21001- IT01- 05CPP- 664043 | RPDU5.QM.517 | S21001- IT01- 05CPP- 664043 | FI
18.29 | FGD -Ash Filters-ITP Inspection and Test Plan for Erection |  | S21001- IT01- 05CPP- 664044 |  | S21001- IT01- 05CPP- 664044 | FI
19 | FGD & SAC - PROCEDURES AND MANUALS
19.1 | FGD - Flue Gas Duct - Erection Procedure |  | S21001-PS01- 05HTA- 225002 | RPDU5.PM.001 | S21001-PS01- 05HTA- 225002 | FI
19.2 | FGD - MCU Mist Cooling Unit - Erection Procedure |  | S21001-PS01- 05HTH- 225003 | RPDU5.PM.002 | S21001-PS01- 05HTH- 225003 | FI
19.3 | FGD - FGTR Flue Gas Treatment Reactor - Erection Procedure |  | S21001-PS01- 05HSD- 225004 | RPDU5.PM.003 | S21001-PS01- 05HSD- 225004 | FI
19.4 | FGD - Booster Fan including VFD system/panel - Erection Procedure |  | S21001-PS01- 05HSC- 225005 | RPDU5.PM.004 | S21001-PS01- 05HSC- 225005 | FI
19.5 | FGD & SAC - Tanks & Vessels - Erection Procedure |  | S21001-PS01-05CPP- 225001 | RPDU5.PM.005 | S21001-PS01-05CPP- 225001 | FI
19.6 | FGD & SAC - Piping - Erection Procedure |  | S21001-PS01- 05CPP- 225002 | RPDU5.PM.006 | S21001-PS01- 05CPP- 225002 | FI
19.7 | SAC - Erection Procedure |  | UNDER DEVELOPMENT | RPDU5.PM.007 | UNDER DEVELOPMENT | FI
19.8 | FGD - MCU Mist Cooling Unit - Commissioning Procedure |  | S21001-CC01-05HTH-228500 | RPDU5.PM.010 | S21001-CC01-05HTH-228500 | FI
19.9 | FGD - FGTR Flue Gas Treatment Reactor - Commissioning Procedure |  | S21001-CC01-05HSD-228501 | RPDU5.PM.011 | S21001-CC01-05HSD-228501 | FI
19.10 | FGD - Booster Fan - Commissioning Procedure |  | S21001-CC01-05HSC-228502 | RPDU5.PM.012 | S21001-CC01-05HSC-228502 | FI
19.11 | FGD & SAC - Pumps - Commissioning Procedure |  | S21001-CC01-05HSD-228503 S21001-CC01-05GNE-998503 | RPDU5.PM.013 | S21001-CC01-05HSD-228503 S21001-CC01-05GNE-998503 | FI
19.12 | SAC - Comissioning Procedure |  | UNDER DEVELOPMENT | RPDU5.PM.014 | UNDER DEVELOPMENT | FI
19.13 | FGD & SAC - Fire Fighting System - Commissioning Procedure |  | S21001- CC01- 05SGA- 778500 | RPDU5.PM.015 | S21001- CC01- 05SGA- 778500 | FI
19.14 | FGD - Performance Test Procedure |  | S21001-CC01-05HSD-228510 | RPDU5.PM.100 | S21001-CC01-05HSD-228510 | FA
19.15 | SAC - Performance Test Procedure |  | UNDER DEVELOPMENT | RPDU5.PM.300 | UNDER DEVELOPMENT | FA
19.16 | FGD - Operation & Maintenance Manual |  | S21001-MA01-05HSD-228511 | RPDU5.PM.110 | S21001-MA01-05HSD-228511 | FI
19.17 | SAC - Operation & Manintenance Manual |  | UNDER DEVELOPMENT | RPDU5.PM.310 | UNDER DEVELOPMENT | FI
20 | FGD & SAC - PROCEDURES AND MANUALS
20.1 | FGD & SAC- Master Project Schedule | S21001-MS01-05CPP-118400 | S21001-MS01-05CPP-118400 | RPDU5.BA.001 | S21001-MS01-05CPP-118400 | FI
20.2 | FGD & SAC- Engineering Document List(EDL/MDL) | S21001-EN01-05CPP-221030 | S21001-EN01-05CPP-111003 | RPDU5.BA.002 | S21001-EN01-05CPP-111003 | FI
| FGD & SAC KKS identification system | S21001- PM01-05CPP-121004 | S21001- PM01-05CPP-121004
| FGD & SAC Drawing Standard Sheet and Document Cover Sheet | S21001- PM01-05CPP-121005 | S21001- PM01-05CPP-121005
| SMARTLuth Organization Chart | S21001-PM01-05CPP- 121003 | S21001-PM01-05CPP- 121003
Note on D22: suman das: BOOSTER FAN RELATED WILL BE MARKED AS "HSC" "HNC" TO BE UPDATED AS "HSC"

## NUMBERS
| DISCIPLINE CODE | 11 |  |  | 22 |  |  | 55 |  |  | 66 |  |  | 99
| NAME OF DISCIPLINE | General/CPP |  |  | MECH |  |  | CIVIL |  |  | QA/QC |  |  | SULPHURIC ACID PLANT
| DOCUMENT TYPE | START NO | ALLOCATED | FINISH NO | START NO | ALLOCATED | FINISH NO | START NO | ALLOCATED | FINISH NO | START NO | ALLOCATED | FINISH NO | START NO | ALLOCATED | FINISH NO
| EN01= Engineering Documents and Drawings. | 111001 | 999 | 112000 | 221001 | 999 | 222000 | 551001 | 999 | 552000 | 661001 | 999 | 662000 | 991001 | 999 | 992000
| QA01= QA Documents. | 112001 | 999 | 113000 | 222001 | 999 | 223000 | 552001 | 999 | 553000 | 662001 | 999 | 663000 | 992001 | 999 | 993000
| QC01= Quality Control Document. | 113001 | 999 | 114000 | 223001 | 999 | 224000 | 553001 | 999 | 554000 | 663001 | 999 | 664000 | 993001 | 999 | 994000
REV 0 | IT01= Inspection Test Plan. | 114001 | 999 | 115000 | 224001 | 999 | 225000 | 554001 | 999 | 555000 | 664001 | 999 | 665000 | 994001 | 999 | 995000
| PS01= Erection Procedure/Work Method Statement. | 115001 | 999 | 116000 | 225001 | 999 | 226000 | 555001 | 999 | 556000 | 665001 | 999 | 666000 | 995001 | 999 | 996000
| MA01= Manual/ OPERATING/ GENERAL | 116001 | 999 | 117000 | 226001 | 999 | 227000 | 556001 | 999 | 557000 | 666001 | 999 | 667000 | 996001 | 999 | 997000
| XF01= PFD Diagram. | 117001 | 99 | 117100 | 227001 | 99 | 227100 | 557001 | 99 | 557100 | 667001 | 99 | 667100 | 997001 | 99 | 997100
| XG01= P& I Diagram. | 117101 | 99 | 117200 | 227101 | 99 | 227200 | 557101 | 99 | 557200 | 667101 | 99 | 667200 | 997101 | 99 | 997200
| TS01= Technical Specification. | 117201 | 999 | 118200 | 227201 | 999 | 228200 | 557201 | 999 | 558200 | 667201 | 999 | 668200 | 997201 | 999 | 998200
| MS01= Master Project Schedule. | 118400
CS01= Cable Schedule.
| VS01= Valve Schedule |  |  |  | 228400
| PM01= Project management | 121001 | 999 | 122000
REV 0 | IP01= information technology/Software
| EE01= Engineering Issues | 110001 | 999 | 111000 | 220001 | 999 | 221000 | 550001 | 999 | 551000 | 660001 | 999 | 661000 | 990001 | 999 | 991000
| CC01= Commissioning Procedure | 118500 | 999 | 119499 | 228500 | 999 | 229499 | 558500 | 999 | 559499 | 668500 | 999 | 669499 | 998500 | 999 | 999499
|  | 33 |  |  | 44 |  |  | 77 |  |  | 88
|  | ELEC |  |  | C&I |  |  | FIRE |  |  | SOFTWARE
|  | START NO | ALLOCATED | FINISH NO | START NO | ALLOCATED | FINISH NO | START NO | ALLOCATED | FINISH NO | START NO | ALLOCATED | FINISH NO
| EN01= Engineering Documents and Drawings. | 331001 | 999 | 332000 | 441001 | 999 | 442000 | 771001 | 999 | 772000 | 881001 | 999 | 882000
| QA01= QA Documents. | 332001 | 999 | 333000 | 442001 | 999 | 443000 | 772001 | 999 | 773000 | 882001 | 999 | 883000
| QC01= Quality Control Document. | 333001 | 999 | 334000 | 443001 | 999 | 444000 | 773001 | 999 | 774000 | 883001 | 999 | 884000
REV 0 | IT01= Inspection Test Plan. | 334001 | 999 | 335000 | 444001 | 999 | 445000 | 774001 | 999 | 775000 | 884001 | 999 | 885000
| PS01= Erection Procedure/Work Method Statement. | 335001 | 999 | 336000 | 445001 | 999 | 446000 | 775001 | 999 | 776000 | 885001 | 999 | 886000
| MA01= Manual/ OPERATING/ GENERAL | 336001 | 999 | 337000 | 446001 | 999 | 447000 | 776001 | 999 | 777000 | 886001 | 999 | 887000
| XF01= PFD Diagram. | 337001 | 99 | 337100 | 447001 | 99 | 447100 | 777001 | 99 | 777100 | 887001 | 99 | 887100
| XG01= P& I Diagram. | 337101 | 99 | 337200 | 447101 | 99 | 447200 | 777101 | 99 | 777200 | 887101 | 99 | 887200
| TS01= Technical Specification. | 337201 | 999 | 338200 | 447201 | 999 | 448200 | 777201 | 999 | 778200 | 887201 | 999 | 888200
MS01= Master Project Schedule.
| CS01= Cable Schedule. | 338400 |  |  | 441001
VS01= Valve Schedule
PM01= Project management
REV 0 | IP01= information technology/Software
| EE01= Engineering Issues | 330001 | 999 | 331000 | 440001 | 999 | 441000 | 770001 | 999 | 771000 | 880001 | 999 | 881000
| CC01= Commissioning Procedure | 338500 | 999 | 339499 | 448500 | 999 | 449499 | 778500 | 999 | 779499 | 888500 | 999 | 889499