## Sheet1
Hindalco Project No: S21001
Owner: Hindalco Industries Limited (HIL); Consultant: Black & Veatch (B&V)
Project Name: HIL RENUSAGAR - 1 X 75kW FGD Project
Drawing No: |  | S21001 – QA01 – 05CPP - 662002 (RPDU5.QB.502)
Drawing Revision No: |  | 0
Drawing Title: |  | Project Quality Plan
| HIL & BV's Comments dt. 17.01.22 | SL's Response dt.19.01.22
HIL
1 | Attached quality plan in General and not specific. | This is basically a Quality Procedure to be used as a guideline. All details will be in the Inspetion and test plan (ITP) for respective items. Please see the Quality Document Hierarchy shown in the Project Quality Manual no. S21001 - QA01 - 05CPP - 662001 (RPDU5.QB.501), Rev.0 already submitted. The same is also shown below for your ready reference.
2 | A quality plan should have: What are the Quality parameters? what are their permissible limits, and what is the frequency of the testing? what is the action plan if any item is rejected/did not meet the required parameters? | All details will be in the ITP for each item.
3 | Quality plan should be job-specific and materials specific It should cover raw materials, equipment, services separately. | All details will be in the ITP for each item
4 | Hand over and take over protocol should be part of the quality plan. | All details will be in the ITP for each item
5 | Quality checks of Safety-related points of any equipment should be addressed in the quality plan. | All details will be in the ITP for each item
Document Hierarchy
Hierarchy for the project documents pertaining to Quality Assurance and Control is shown below.
CLIENT CONTRACT / ORDER
PROJECT QUALITY MANUAL (PQM)
INSPECTION AND TEST PLAN (ITP)
VENDOR
ERECTION CONTRACTOR
DOCUMENTATION/ CERTIFICATION RECORDS
PROJECT QUALITY PLAN (QCP)