## ITP - Flue Gas Dampers
|  |  |  | INSPECTION AND TEST PLAN . |  |  |  | Client Doc. No. S21001- IT01- 05CPP- 664020
|  |  |  | For: FGD - Flue Gas Dampers - ITP Inspection and Test Plan for Fabrication |  |  |  | Gore Doc. No. RPDU5.QF.519 |  |  | Rev. 00 - 18.2.22
| Plant: | Hindalco Renusagar U5 1 x 80 MW PF Captive Power Plant - Flue Gas Desulfurization Project with GORETM SPC technology | [5 empty] | File: | RPDU5.QF.519_00_180222.xls
| Supplier: |  | Order No: |  | P.T.S. No: RPDU5.PA.003 / S21001 - TS01 - 05HTA- 227255 |  |  |  |  | ITEM No.
POS. |  | INSPECTIONS AND TESTS |  | PROCEDURES | CODES & | 1) | QUALITY SURVEILLANCE - % OF INSPECTION
|  |  |  | DRAWINGS - D/S | STANDARDS |  | SUPPLIER | GORE | HINDALCO |  |  | NOTE
INTERMEDIATE INSPECTIONS
|  | Pre Fabbrication Meeting (PFM) |  |  |  |  | H | H | W | R |  | PFM Report
I. | 10 | Order, drawings, procedures, specifications, WPS, |  | Order
PQR, document list and ITP review.
[6 empty] | YES | H | R | R | R
I. | 20 | Material certificate review |  | See Drawing List | EN10088 | 3.1
EN 10204
|  | Motors |  |  |  | YES | H | R | R | R
I. | 21 | - Routin test |  | approved supplier procedure |  | 3.1
- type test
[7 empty] | H | R | R | R
I. | 30 | Welding documents rewiev (WPS/PQR/WQ) |  |  | EN 15614 or
ASME IX
|  | LP or MT on 100% of welds |  |  | DIN EN 571-1 | YES | H | W | W | W |  | blades and int. Struct., frame:
[6 empty] | 3.1 | [5 empty] | 100% butt w. - 25% others
I. | 40 | [10 empty] | cladding (frame&shaft): 100%
other parts: 25%
|  | Visual inspection of welds |  |  | EN ISO 5817 | YES | H | W | W | W |  | 100%
I. | 50 |  |  |  |  | 3.1
FINAL INSPECTIONS
|  | Visual and dimensional inspection |  | drawing |  | YES | H | W | W | W |  | 100%
F. | 10 |  |  |  |  | 3.1
|  | Function test and tightness check |  |  |  | YES | H | W | W | W
F. | 20 |  |  | approved supplier procedure |  | 3.1
|  | Painting inspection |  |  |  | YES | H | W | R | R
F. | 30 |  |  | painting procedure |  | 3.1
|  | Final inspection before shipment |  |  |  |  | H | H | W | W
|  | - QC certificates review |  | Order
F. | 40 | - Completeness of the supply
|  | - Issue of FIR |  |  |  | YES
LIST OF APPLICABLE DRAWINGS:
SUPPLIER DRAWING