## Cover
Owner: HINDALCO INDUSTRIES LIMITED Ahura Centre, 1st Floor, B Wing, Mahakali Caves Road, Andheri (East), Mumbai - 400 093, India
EPCM Contractor: W. L. GORE & ASSOCIATES (Pacific) Pte, Ltd. India Branch 703, A-Wing, 215 Atrium, Andheri Kurla Road, Mumbai 400059, India
Nominated Subcontractor - Engineering, Quality Control, Supervision: SMARTLuth Solution and Service Pvt. Ltd. Unit No: 503, 5th Floor, ECO Centre,. EM-4 Sector-V, Salt Lake City, Kolkata - 700091, India
Hindalco Renusagar U5 1 x 80 MW PF Captive Power Plant
Flue Gas Desulfurization Project (FGD) with GORETM SO2 Control System
FGD & SAC
Centrifugal Pumps - ITP Inspection and Test Plan for Fabrication
ISSUED FOR |  | APPROVAL ☒ |  |  | INFORMATION □ | MANUFACTURING □ |  | CONSTRUCTION □ |  |  | AS-BUILT □
00 | 03/12/21 |  | First Issue |  |  |  | Smartluth |  |  | Gore |  | Gore
Rev. | Date |  | Description of revision |  |  |  | Prepared |  |  | Checked |  | Approved
Hindalco Renusagar U5 1 x 80 MW PF Captive Power Plant | [6 empty] | Client Doc. No. : S21001- IT01- 05CPP- 664013
Flue Gas Desulfurization Project (FGD) with GORETM SO2 Control System | [6 empty] | Gore Doc. No.: RPDU5.QF.513 |  |  |  | page 1 of | 0 | of | 2
FGD & SAC | [6 empty] | GORE Job : RPDU5 |  |  |  | Rev. : | 00
Centrifugal Pumps - ITP Inspection and Test Plan for Fabrication | [6 empty] | File: |  | RPDU5QF513_00_031221.xls
This document is a property of W.L. GORE & ASSOCIATES (Pacific) Pte, Ltd. and it may contain trade secrets or privileged, undisclosed or otherwise confidential information. If you have received this document in error, you are hereby notified that any review, copying or distribution of it is strictly prohibited.
PRELIMINARY
NOT VALID FOR CONSTRUCTION

## ITP - Centrifugal Pumps
|  |  |  | INSPECTION AND TEST PLAN . |  |  |  | Client Doc. No. S21001 - IT01- 05CPP- 664047
|  |  |  | For: CENTRIFUGAL PUMPS (Non-Metallic) |  |  |  | Gore Doc. No. |  | Rev. 00
| Plant: | Hindalco Renusagar U5 1 x 80 MW PF Captive Power Plant - Flue Gas Desulfurization Project with GORETM SPC technology | [5 empty] | File:
| Supplier: |  | Order No: |  | P.T.S. No: |  |  |  | ITEM No.
POS. |  | INSPECTIONS AND TESTS |  | PROCEDURES | CODES & | 1) | QUALITY SURVEILLANCE - % OF INSPECTION
|  |  |  | DRAWINGS - D/S | STANDARDS |  | SUPPLIER | GORE | HINDALCO |  | NOTE
INTERMEDIATE INSPECTIONS
|  | Pre Fabbrication Meeting (PFM) |  |  |  |  | H | H |  |  | PFM Report
I. | 10 | Order, drawings, procedures, specifications |  | Order
|  | document list and ITP review |  |  |  |  | 100%
[6 empty] | YES | H | R
I. | 20 | Material certificate review |  | See Drawings List | Material Specification
100%
[6 empty] | YES | H | R
I. | 30 | Hardness check |  | Supplier approved procedure
100%
H
I | 31 | Other tests (to specify by manufacturer) |  | Supplier approved procedure
100%
[6 empty] | YES | H | R
I. | 40 | Hydrostatic test |  | Supplier approved procedure
[7 empty] | 100% | 100%
[6 empty] | YES | H | R
I. | 50 | Lining check (if any) |  | Supplier approved procedure
100%
FINAL INSPECTIONS
[6 empty] | YES | H | W
F. | 10 | Balancing test |  | Supplier approved procedure
100%
[6 empty] | YES | H | W
F. | 20 | Performance test |  | Supplier approved procedure
100%
[6 empty] | YES | H | W
F. | 30 | NPSH test |  | Supplier approved procedure
100%
[6 empty] | YES | H | W
F. | 40 | Vibration test |  | Supplier approved procedure
100%
[6 empty] | YES | H | R
F. | 50 | Noise measurement |  | Supplier approved procedure
100%
[6 empty] | YES | H | W
F. | 60 | Visual and dimensional check |  | Supplier approved procedure
100%
[6 empty] | YES | H | W
F. | 70 | Painting check |  | Supplier approved procedure
100%
[6 empty] | YES | R | R
F. | 80 | Electric motor certificate |  | Supplier approved procedure | IEC/CEI
|  | Final inspection before shipment |  |  |  |  | H | H | H
F. | 90 | - QC certificates review |  | Order
- Completeness of the supply
- Issue of FIR
Note:
1) R=Documents review W=Witness Point H=Hold point YES=Certificate required FIR=Final Inspection Report TPI=Third Party Inspection Agency
This is a draft ITP. Please prepare ITP in this for format as per supplier manufacturing process