## ITP Ash Filters
|  |  |  | INSPECTION AND TEST PLAN . |  |  |  | Client Doc. No. S21001- IT01- 05CPP- 664045
|  |  |  | For: Ash Filters |  |  |  | Gore Doc. No. |  | Rev. 00 - Date
| Plant: | Hindalco Renusagar U5 1 x 80 MW PF Captive Power Plant - Flue Gas Desulfurization Project with GORETM SPC technology | [5 empty] | File:
| Supplier: |  | Order No: |  | P.T.S. No: |  |  |  | ITEM No.
POS. |  | INSPECTIONS AND TESTS |  | PROCEDURES | CODES & | 1) | QUALITY SURVEILLANCE - % OF INSPECTION
|  |  |  | DRAWINGS - D/S | STANDARDS |  | SUPPLIER | GORE | HINDALCO |  | NOTE
INTERMEDIATE INSPECTIONS
|  | Pre Fabbrication Meeting (PFM) |  |  |  |  | H | H |  |  | PFM Report
I. | 10 | Order, drawings, procedures, specifications, WPS, |  | Order
PQR, document list and ITP rewiev.
|  |  |  | ASTM standard | EN | YES | R | R
I. | 20 | Chemical analysis |  |  | DIN | 3.1
[5 empty] | ASTM |  | 100%
|  |  |  | ASTM standard | EN | YES | R | R
I. | 30 | Mechanical properties |  |  | DIN | 3.1
[5 empty] | ASTM |  | 100%
|  | N.D.T : M.T / P.T |  |  | ASTM standard | YES | H | R |  |  | Supplier standard
I. | 40 | ( magnetoscopic/penetrant test ) |  | Supplier approved procedures | EN standard | 3.1
100%
FINAL INSPECTIONS
|  | Visual Dimensional & Operated check |  |  | ASME B1634 | YES | H | W
F. | 10 |  |  | Supplier approved drawing |  | 3.1
[7 empty] | 100% | 30%
|  | Hydraulic and Pneumatic test |  |  | ASME B16.34 | YES | H | W
F. | 20 |  |  | Supplier approved procedures |  | 3.1
[7 empty] | 100% | 30%
|  | Assembly and functional test |  | Data sheets |  | YES | H | W
F. | 40 |  |  | Supplier approved drawing |  | 3.1
[7 empty] | 100% | 30%
|  | Painting |  |  |  | YES | H | W
F. | 30 |  |  | Supplier approved procedures | EN / ISO | 3.1
[7 empty] | 100% | 30%
|  | Final inspection before shipment |  |  |  |  | H | H
F. | 50 | - QC certificates review |  | Order
- Completeness of the supply
- Issue of FIR
LIST OF APPLICABLE DRAWINGS:
SUPPLIER DRAWING